## Publication - PP Template
S000713 Construction of Dual Gauge Railway Line from Bogura to Sirajganj Project
Project Country: | Bangladesh | Bank's Approval Date of the Initial Procurement Plan: | 07-07-2026
Project Sector: | Transport | Approved PP Update No.: | Version 1
AIIB Loan (USD Million): |  | Bank's Approval Date of the PP Update: | 07-07-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
Bangladesh Railway | BSRLP/GRT/ESDD/SD4 | Updating Environment, Social, Gender study performing Climate Study of the Project. | 286,112.00 | 85.00 | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) |  | Post |  | 07-15-2026 | 09-12-2026 | 180 | Cleared
Bangladesh Railway | BSRLP/GRT/ICS/SD9 | Procurement of Individual consultant (Senior Financial Management specialist) | 13,243.00 | 75.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 07-15-2026 | 08-22-2026 | 180 | Cleared
Bangladesh Railway | BSRLP/GRT/ICS/SD8 | Procurement of Individual consultant (Senior Procurement specialist) | 39,729.00 | 75.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 07-15-2026 | 08-22-2026 | 180 | Cleared
Bangladesh Railway | BSRLP/GRT/ICS/SD7 | Procurement of Individual consultant (Senior Environmental safeguards specialist) | 19,864.00 | 75.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 07-15-2026 | 08-22-2026 | 180 | Cleared
Bangladesh Railway | BSRLP/GRT/ICS/SD6 | Procurement of Individual consultant (Senior Social safeguards and Communications specialist) | 19,864.00 | 75.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 07-15-2026 | 08-22-2026 | 180 | Cleared
|  | Total: | 378,812.00