## Publication - PP Template
P001105 Construction of Dual Gauge Railway Line from Bogura to Sirajganj
Project Country: | Bangladesh | Bank's Approval Date of the Initial Procurement Plan: | 07-06-2026
Project Sector: | Transport | Approved PP Update No.: | Version 1
AIIB Loan (USD Million): |  | Bank's Approval Date of the PP Update: | 07-06-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
Bangladesh Railway | BSRLP/GDS/GD3 | Procurement of one Motor Trolley | 68,667.00 | 85.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 03-01-2027 | 05-01-2027 | 150 | Cleared
Bangladesh Railway | BSRLP/GDS/GD2 | Supply and Commissioning of BG Track car with Two Trailers. | 1,977,180.00 | 85.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 03-01-2027 | 05-01-2027 | 150 | Cleared
Bangladesh Railway | BSRLP/GDS/GD1 | Supply and Commissioning of BG Ballast Tamping Machine | 10,734,490.00 | 85.00 | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 03-01-2027 | 07-13-2027 | 365 | Cleared
Bangladesh Railway | BSRLP/WKS/WD3 | Supply, Installation, Testing & Commissioning of Computer Based Signaling & Interlocking System for 11 stations with other ancillary works. | 34,167,080.00 | 94.00 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 07-20-2026 | 12-01-2026 | 960 | Cleared
Bangladesh Railway | BSRLP/WKS/WD2 | Construction of DG Railway Track from Chandaikona to Sirajganj (upto Up Outer Signal of Saidabad Station) including Construction/Reconstruction of Station Buildings with associate works, Bridges, one Rail flyover (RFO) as well as other ancillary works including supply of all requisite materials, labor and equipment. | 338,169,424.00 | 94.00 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 07-20-2026 | 12-01-2026 | 960 | Cleared
Bangladesh Railway | BSRLP/WKS/WD1 | Construction of DG Railway Track from Bogura to Chandaikona and Y connection from Ranirhat to Kahaloo including Construction/Reconstruction of Station Buildings with associate works, Bridges, One Road Over Bridge (ROB) and other anchillary works including supply of all requisite materials, labor and equipment. | 294,517,583.00 | 94.00 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 07-20-2026 | 12-01-2026 | 960 | Cleared
Bangladesh Railway | BSRLP/CSC/SD2 | Construction Supervision Services for Construction of New Dual Gauge Railway Line from Bogura to Sirajganj of Bangladesh Railway. | 14,602,689.00 | 79.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 07-08-2026 | 12-02-2026 | 1440 | Cleared
|  | Total: | 694,237,113.00