## Publication - PP
S000703 PPSF for Agriculture Commercialization and Diversification Project Phase 2 (PACD2)
Project Country: | Papua New Guinea | Bank's Approval Date of the Initial Procurement Plan: | 05-17-2026
Project Sector: | Rural Infrastructure and Agriculture Development | Approved PP Update No.: | Version 2
AIIB Loan (USD Million): |  | Bank's Approval Date of the PP Update: | 05-22-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
Department of Agriculture & Livestock | 008 | Driver & Logistics Officer | 8,300.00 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Prior |  |  | 06-27-2026 | 14 | Cleared
Department of Agriculture & Livestock | 007 | Senior Engineer (Cocoa) | 38,000.00 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Prior |  |  | 06-27-2026 | 14 | Cleared
Department of Agriculture & Livestock | 006 | Senior Engineer (Coffee) | 38,000.00 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Prior |  |  | 06-27-2026 | 14 | Cleared
Department of Agriculture & Livestock | 005 | Value Chains Coordinator 2 (Previously Cocoa PMU Manager) | 89,000.00 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Prior |  |  | 06-27-2026 | 14 | Cleared
Department of Agriculture & Livestock | 004 | Value Chains Coordinator 1 (Previously Coffee PMU Manager) | 69,000.00 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Prior |  |  | 06-27-2026 | 14 | Cleared
Department of Agriculture & Livestock | 003 | Procurement & Contract Administration Specialist | 27,400.00 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Prior |  |  | 06-27-2026 | 14 | Cleared
Department of Agriculture & Livestock | 002 | Financial Management & Disbursement Officer | 18,000.00 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Prior |  |  | 06-27-2026 | 14 | Cleared
Department of Agriculture & Livestock | 001 | Project Coordinator -PCU | 56,500.00 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Prior |  |  | 06-27-2026 | 14 | Cleared
Department of Agriculture & Livestock | QCBS 001 | Feasibility Study (FS) and Detailed Engineering Design (DED) of Productive Infrastructure | 1,300,000.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 05-20-2026 | 10-14-2026 | 14 | Cleared
|  | Total: | 1,644,200.00