TERMS OF REFERENCE

for Consulting Services to Support Project Preparation and Early Implementation of the Uzbekistan Resilient Electricity Transmission Project with the participation of the Asian Infrastructure Investment Bank

1. INTRODUCTION

The Republic of Uzbekistan is experiencing sustained economic growth accompanied by a rapid increase in electricity demand. In parallel, the Government of Uzbekistan has adopted ambitious energy sector reform and decarbonization objectives, including the development of up to 25 GW of renewable energy capacity by 2030, with renewable energy expected to account for approximately 40% of total installed generation capacity. Achieving these objectives requires a resilient, reliable, and modernized power transmission network capable of integrating large volumes of intermittent renewable generation, much of which is located far from major load centers.

To meet these challenges, the Government of Uzbekistan has prioritized the strengthening and expansion of the national transmission system, including the construction of new high-voltage transmission lines, new substations, and extensions of existing substations. These investments are critical to ensuring energy security, improving system stability, reducing losses, and enabling the efficient evacuation of power from new generation sources.

In this context, the Joint-Stock Company “National Electric Grid of Uzbekistan” (NEGU), the state-owned enterprise responsible for the ownership, operation, and development of the country’s transmission network, is preparing the Uzbekistan Resilient Electricity Transmission Project (hereinafter referred to as the Project) with financing support from the Asian Infrastructure Investment Bank (AIIB).

The Project comprises a portfolio of transmission infrastructure investments to be implemented in two phases, covering the period 2026–2030, and includes the construction of new 220 kV and 500 kV transmission lines, new substations and switching stations; and extension/reinforcement of existing substations. The preliminary budget for this Project is approximately USD 300 million, expected to be financed by a sovereign loan from AIIB.

The Government of Uzbekistan has obtained Project Preparation Special Fund (PPSF) financing from AIIB to support comprehensive project preparation activities. These activities include technical, environmental, social, climate, economic, financial, and procurement due diligence, as well as the preparation of the Project Concept (PC), Project Appraisal Document (PAD), and associated documents required for national approvals and AIIB financing.

Project preparation and implementation shall be carried out in accordance with:

- The Presidential Resolution No. PP-51 dated 11 February 2025, “On Additional Measures to Improve Mechanisms for Preparation and Implementation of Projects with Participation of International Financial Institutions and Foreign Government Financial Organizations”;

- AIIB’s Environmental and Social Framework (ESF);

- AIIB’s Procurement Policy (June 26, 2024) and Directive on Procurement Instructions for Recipients (July 26, 2024); and

- Relevant laws and regulations of the Republic of Uzbekistan.

The Project’s main investment components are expected to be implemented predominantly under Engineering, Procurement and Construction (EPC) / Design-Build contracts, whereby contractors will be responsible for detailed design, procurement, construction, testing, and commissioning of the facilities in accordance with Employer’s Requirements prepared during project preparation.

To support NEGU and AIIB in preparing and early implementation of the Project, NEGU intends to engage a qualified consulting firm (the Consultant) to provide comprehensive professional services as defined in these Terms of Reference.

The Consultant shall be selected using Quality- and Cost-Based Selection (QCBS) with a weighting of 90% for quality and 10% for cost (90:10), in accordance with the AIIB’s Directive on Procurement Instructions for Recipients (2024).

2. OBJECTIVE OF THE PROJECT

The overall objective of the Project is to strengthen the resilience, reliability, and efficiency of Uzbekistan’s national power transmission system, thereby enabling secure electricity supply and large-scale integration of renewable energy in line with the country’s long-term energy strategy.

Specifically, the Project seeks to enhance transmission capacity between generation centers and load centers, improve system stability and operational reliability, reduce network congestion and technical losses, increase the resilience of the transmission system to climate-related and operational risks, and support Uzbekistan’s transition toward a low-carbon energy system.

3. SCOPE OF THE PROJECT

The Project comprises a portfolio of priority transmission infrastructure investments aimed at strengthening Uzbekistan’s national power grid and enabling reliable integration of new generation capacity, including renewable energy sources. It includes the construction of new high-voltage transmission lines, the development of new substations and switching stations, and the reinforcement of existing substations. It is structured into two implementation phases based on implementation readiness, financing availability, system priorities, and institutional capacity. The Project will be implemented by NEGU as the Executing and Implementing Agency.

Phase I (2026-2028) consists of priority transmission system investments that are at an advanced stage of readiness and are critical for the near-term system reinforcement. The Consultant shall prioritize Phase I activities during the early stages of the assignment.

Table 1: Phase I – Activities Planned for Implementation in 2026–2028

| No. | Project Name | Scope of Works | Implementation Period |
| --- | --- | --- | --- |
| 1 | Extension of Tepakurgan switching station to 220 kV substation and construction of a new 220 kV 2×15 km transmission line | Expansion of the existing SS to 220 kV substation, as well as connection to the outdoor switchyard of the Turakurgan HPP through the construction of a 2×15 km overhead transmission line (OHL), including the selection of electrical equipment. | 2026-2028 |
| 2 | Construction of new 220 kV “Kashgar” substation and associated 220 kV transmission lines | Construction of one new 220 kV, 500 MVA substation as well as the construction of a 2×10 km overhead transmission line (OHL) to the Uzbekistan substation and a 40 km OHL to the Obi hayot substation, including the selection of electrical equipment and arrangements for connection through the construction of these transmission lines. | 2026-2028 |

Phase II (2026-2030) consists of major backbone transmission line investments aimed at strengthening long-distance power transfer capability and supporting large-scale renewable energy integration. These projects are technically complex and require extensive system studies, environmental and social assessments, and climate resilience analysis.

Table 2: Phase II – Activities Planned for Implementation in 2026–2030

| No. | Project Name | Scope of Works | Implementation Period |
| --- | --- | --- | --- |
| 1 | Construction of a new 500 kV Transmission Line between “Nurabad” substation and “Surkhan” substation | Construction of a new 500 kV overhead transmission line with an approximate length of 275 km (Development of all necessary measures for interconnecting these substations through newly constructed overhead transmission lines (OHL), including the selection of electrical equipment) | 2027-2030 |
| 2 | Construction of a new 500 kV transmission line between “New Angren” thermal power plant and “Namangan” substation | Construction of a new 500 kV overhead transmission line with an approximate length of 180 km (Development of all necessary measures for interconnecting these substations through newly constructed overhead transmission lines (OHL), including the selection of electrical equipment) | 2027-2030 |
| 3 | Construction of a new 220 kV transmission line between “Namangan” substation and “Yulduz” substation | Construction of a new 220 kV overhead transmission line with an approximate length of 91.5 km (Development of all necessary measures for interconnecting these substations through newly constructed overhead transmission lines (OHL), including the selection of electrical equipment) | 2027-2030 |
| 4 | Construction of a new 220 kV transmission line between “Namangan” substation and “Turakurgan” thermal power plant | Construction of a new 220 kV overhead transmission line with an approximate length of 71.3 km (Development of all necessary measures for interconnecting these substations through newly constructed overhead transmission lines (OHL), including the selection of electrical equipment) | 2027-2030 |

Phase I project preparation shall be undertaken as a priority, and Phase II preparation activities shall commence only after satisfactory progress on Phase I, and approval of Project Concept for Phase I, unless otherwise authorized in writing by NEGU and AIIB. The Consultant shall structure all studies, deliverables, and reporting in a manner that clearly differentiates Phase I and Phase II while ensuring overall system coherence, and all due diligence outputs for Phase II shall build upon the system studies, methodologies, and frameworks developed under Phase I.

The Project’s main investment components are expected to be implemented primarily under EPC / Design-Build contracts, under which contractors will be responsible for detailed design, procurement, construction, testing, and commissioning. Accordingly, the scope of consulting services under this TOR focuses on pre-EPC activities, including feasibility-level engineering, preparation of Employer’s Requirements and EPC-compatible technical specifications, and support to NEGU during procurement and early implementation.

4. SCOPE OF CONSULTING SERVICES

The Consultant shall provide comprehensive professional services to support the preparation and early implementation of the Project. The scope of services covers technical, environmental, social, climate, economic, financial, institutional, and procurement due diligence, including the preparation of supporting environmental and social documents, as well as the preparation of the PC, PAD, and EPC-oriented project documentation.

The Project Concept (PC) shall be prepared in accordance with the requirements of Presidential Resolution No. PP-51 and shall present a structured preliminary assessment of the proposed Project. The PC shall cover the strategic context and justification of the Project, including national, sectoral, and institutional capacity; alignment with national development strategies; and the expected objectives and outcomes. It shall define the Project’s purpose, key stakeholders, and lessons learned from similar projects, and provide a clear description of the Project’s location, scale, components, indicative cost, financing structure, and sources of loan repayment. The PC shall also include an initial technical justification, preliminary economic and financial analysis, an assessment of social aspects, and compliance with national policies and the environmental and social requirements of international financial institutions. In addition, the PC shall present indicative unit cost benchmarks based on comparable projects, a preliminary results matrix with target indicators by year, and an overall assessment of key project risks together with proposed risk mitigation measures.

The Consultant shall support the review and approval of the PC by revising the document as necessary in response to comments received from NEGU, AIIB, and relevant government authorities and by providing assistance throughout the PC review and clearance process.

The Project Appraisal Document (PAD) shall be prepared on the basis of the approved PC, in accordance with the requirements of Presidential Resolution No. PP-51 and in alignment with AIIB’s operational requirements and best international practices. The PAD shall provide a comprehensive and detailed assessment of the proposed Project, including key project parameters and financing arrangements; the Project’s strategic relevance in the national, sectoral, and institutional context; clearly defined objectives, implementation strategy, and stakeholders; and lessons learned from similar investments. It shall include a detailed description of Project components, costs, and financing sources; implementation arrangements and institutional responsibilities; monitoring and evaluation mechanisms; sustainability considerations; and a thorough evaluation of technical feasibility, procurement approach, climate and disaster resilience, financial management and debt service capacity, and economic and financial viability. The PAD shall also assess social and environmental impacts and compliance with national policies and the safeguard requirements of international financial institutions, identify key project risks and corresponding mitigation measures, and include all required supporting annexes. The detailed structure and content requirements of the PAD are provided in Annex 1 to these Terms of Reference.

As a key deliverable under this assignment, the PAD shall serve as the principal decision-making document for both the Government of Uzbekistan and AIIB. The PAD shall be suitable for submission to and approval by the Ministry of Investment, Industry and Trade (MIIT), the Ministry of Economy and Finance (MOEF), NEGU, and other relevant government authorities, and shall also form the basis for AIIB loan approval. The Consultant shall provide all necessary support during the state expertise and approval process, including coordination with concerned ministries and agencies, and shall revise the PAD as required to address comments received from NEGU, AIIB, and the relevant government authorities.

Technical due diligence. The Consultant shall undertake full technical due diligence for all Project components at a level sufficient to support PAD and EPC procurement. For each transmission line project, the Consultant shall carry out desktop and field-based transmission routing studies, assess at least two to three alternative route options where feasible, and recommend the optimal route taking into account technical, environmental, and social constraints. Transmission routing studies shall include environmental and social sensitivity mapping and avoidance-first evaluation, demonstrating how routing alternatives minimize impacts on settlements, agricultural land, vulnerable groups, cultural heritage, and environmentally sensitive areas.

The Consultant shall identify right-of-way requirements and key crossing points such as roads, railways, rivers, and utilities, develop preliminary transmission line configurations including voltage level, conductor type, bundle configuration, insulation coordination, OPGW, and tower types, prepare preliminary tower spotting and span optimization, and assess constructability and logistics considerations. All routing and survey outputs shall be provided in appropriate digital formats (GIS and/or AutoCAD), as agreed with NEGU.

For new and existing substations and switching stations, the Consultant shall assess site conditions, land availability, and access constraints; develop preliminary layouts and configurations; define primary and secondary equipment arrangements; evaluate AIS versus GIS options where applicable; define bay extensions and interfaces with existing facilities; consider future expandability and system development plans; and prepare preliminary cost estimates and construction phasing concepts.

Power system analysis. The Consultant shall carry out comprehensive power system studies to ensure system reliability and effective integration of the Project assets, including load flow analysis, short-circuit studies, transient and dynamic stability analysis, contingency analysis, and reactive power compensation studies. All system studies shall be performed using DigSILENT PowerFactory or an equivalent industry-standard software, and all models, assumptions, and results shall be shared with NEGU and AIIB.

The project cost estimates. The Consultant shall prepare comprehensive project cost estimates for all Project components under Phase I and Phase II, based on the results of technical due diligence and engineering studies, at a level sufficient to support government approval, AIIB appraisal, and EPC procurement planning. Cost estimates shall cover all Project components and cost categories, be prepared separately for Phase I and Phase II with aggregation at the Project level and be structured in a manner compatible with EPC / Design-Build lump-sum principles. The Consultant shall benchmark costs against comparable projects in Uzbekistan, the region, and relevant international markets, document key assumptions and cost drivers, identify areas of uncertainty, and support NEGU and AIIB during cost validation and appraisal discussions.

Implementation planning. The Consultant shall also support implementation planning by preparing an overall implementation schedule for Phase I and Phase II, identifying critical path activities and key milestones, assessing implementation risks and proposing mitigation measures, and ensuring alignment of the implementation schedule with procurement and financing timelines.

Economic and financial analyses. The Consultant shall carry out comprehensive economic and financial analyses of the Project in accordance with AIIB requirements and international best practices for power transmission projects, in order to assess the Project’s economic viability, financial sustainability, and affordability. The economic analysis shall evaluate the Project’s costs and benefits over its full economic life, quantify benefits such as improved system reliability, reduced losses, increased transmission capacity, enhanced renewable energy integration, and avoided outage costs, calculate key economic indicators including the Economic Internal Rate of Return (EIRR), Economic Net Present Value (ENPV), Benefit–Cost Ratio, and include sensitivity analysis and assessment of risks and uncertainties affecting economic performance. The financial analysis shall assess capital investment requirements and financing structure, evaluate operating and maintenance cost implications, analyze the financial impact on NEGU including cash flow and debt service capacity, identify financial risks and mitigation measures, and support AIIB’s financial due diligence and appraisal requirements. All economic and financial analyses shall be presented in a transparent and auditable manner, with all models, assumptions, and calculation files provided to NEGU and AIIB in editable electronic format and consistent with the assumptions used in the PAD.

Procurement support. Procurement of goods, works, and consulting services under the Project shall be carried out in accordance with the AIIB Procurement Policy (June 26, 2024), the AIIB Directive on Procurement Instructions for Recipients (July 26, 2024), Presidential Resolution No. PP-51 dated 11 February 2025, and the applicable laws and regulations of the Republic of Uzbekistan. As required by NEGU and AIIB, the Consultant shall provide technical and advisory inputs to the Project Delivery Strategy (PDS) and the Procurement Plan (PP), including inputs related to the selection of EPC / Design-Build delivery arrangements, indicative contract packaging and sequencing for Phase I and Phase II, procurement methods and timelines, and identification of major EPC and consulting service packages. The Consultant’s inputs to the PDS and PP shall be limited to those necessary to support PAD preparation and AIIB appraisal and shall be consistent with the Project’s technical characteristics, implementation schedule, and financing arrangements.

In line with the Project’s EPC delivery model, the Consultant shall provide technical support for EPC procurement, focusing primarily on the preparation of technical inputs to EPC bidding documents, including Employer’s Requirements (Section 6), performance-based technical specifications, reference layouts and conceptual drawings, interface and responsibility matrices, construction, testing, commissioning, and performance requirements, and environmental, social, health, and safety obligations. Where applicable under the selected bidding documents, the Consultant shall also prepare bills of quantities and/or priced schedules of activities consistent with EPC procurement requirements. At NEGU’s request, the Consultant shall support the technical aspects of the procurement process, including responding to technical clarification requests, supporting technical evaluation of EPC bids, and participation in pre-bid meetings and clarification stages. If required, the Consultant shall also provide technical inputs to the preparation of Terms of Reference for the Project Implementation Consultant (PIC) and other related consulting services.

Environmental and Social documentation. The Consultant shall identify, assess, and support the management of all environmental, social, and gender-related risks and impacts associated with the Project, in accordance with the AIIB Environmental and Social Framework (ESF), applicable legislation of the Republic of Uzbekistan, international good practice for high-voltage transmission projects, and the requirements of Presidential Resolution No. PP-51 dated 11 February 2025. Given the Project’s two-phase structure, the Consultant shall prepare (i) framework documents applicable to the entire Project, followed by (ii) full environmental and social assessment and planning documents for Phase I, and (iii) full environmental and social assessment and planning documents for Phase II, consistent with the requirements of the AIIB ESF. Framework and Phase I documentation shall be prioritized to enable timely appraisal, approval, and early implementation.

Environmental and social due diligence shall support project approval, sustainable implementation, and positive outcomes for affected communities and the environment. It shall cover all transmission lines, substations, switching stations, access roads, temporary construction facilities and associated facilities under Phase I and Phase II of the Project.

1. Framework Level Documentation (Phase I and Phase II)

The Consultant shall prepare environmental and social framework-level instruments that provide the overarching methodologies, procedures, screening tools, and management principles applicable to both phases. These documents provide guidance and structure for subsequent component-specific E&S work:

- Environmental and Social Management Planning Framework (ESMPF) covering screening, assessment requirements, mitigation hierarchy, monitoring, and institutional arrangements;

- Resettlement Planning Framework (RPF) establishing procedures for census, valuation, compensation, cutoff dates, eligibility, livelihood restoration, and alignment between national legislation and AIIB ESF;

- Stakeholder Engagement Plan (SEP) applicable to the full Project, setting out stakeholder identification, engagement strategy, disclosure requirements, consultation methods, and GRM arrangements;

- Labor Management Procedures (LMP) for the Project, including worker Grievance Redress Mechanism (GRM) and workforce management requirements;

- Project-specific Gender Action Plan (GAP) applicable across both phases, which is complementary to the institution-wide Gender Action Plan being developed with ADB;

- Biodiversity Framework describing assessment methodology and seasonal requirements for fauna and habitat surveys, identification of sensitive habitats across all corridors; and

- Climate Risk Assessment guiding climate screening and hazard assessment for both phases.

These framework instruments shall guide the preparation of phase-specific E&S documentation and shall be incorporated into the Project Concept (PC), Project Appraisal Document (PAD), and EPC bidding documents.

2. Detailed E&S Documentation for Phase I

For Phase I components, the Consultant shall prepare full, component-specific environmental and social assessments and management plans sufficient for government review, AIIB appraisal, and EPC procurement. These include:

- Environmental and Social Impact Assessment(s) (ESIA) for each subproject;

- Environmental and Social Management Plan(s) (ESMP) and all required subplans, including but not limited: Occupational Health and Safety Management Plan, Community Health and Safety Plan, Traffic and Access Management Plan, Waste and Hazardous Materials Management Plan, Biodiversity Management Plan, Cultural Heritage ChanceFind Procedures, LMP (phase-specific), Gender Action Plan (GAP) (phase specific);

- Resettlement Action Plan(s) (RAP) for Phase I components involving land acquisition or restrictions on land use, based on: full census and socioeconomic surveys; inventory of losses; valuation at full replacement cost; gap analysis between national legislation and AIIB ESF with bridging measures; livelihood restoration measures; implementation arrangements and budget;

- Due Diligence Reports (DDR) for Phase I components where no land acquisition is anticipated, confirming absence of impacts and identifying any legacy issues; and

- Consultation Report(s) for Phase I, covering at least scoping and draft ESIA/RAP consultations, plus targeted engagement with vulnerable groups and women.

All Phase I assessments shall include routing alternatives and demonstrate application of the mitigation hierarchy during alignment optimization.

3. Detailed E&S Documentation for Phase II

For all Phase II components, the Consultant shall prepare the same full suite of environmental and social assessments and planning documents as required for Phase I, consistent with AIIB ESF but sequenced after Phase I. These include:

- Environmental and Social Impact Assessment(s) (ESIA) for all Phase II subprojects;

- Environmental and Social Management Plan(s) (ESMP) and all required subplans (including but not limited to OHS, CHS, traffic, waste & hazardous materials, biodiversity, cultural heritage, LMP, GAP);

- Resettlement Action Plan(s) (RAP) for all Phase II components requiring land acquisition or restrictions on land use;

- Due Diligence Reports (DDR) for components without land acquisition; and

- Consultation Reports for Phase II, covering scoping and draft ESIA/RAP consultations.

Phase II ESIA and RAP preparation shall be fully informed by baseline data, screening results, and methodologies defined in the framework level instruments.

4. Stakeholder Engagement and GRM

The Consultant shall prepare and implement a SEP covering both phases and conduct structured, inclusive, and gender-sensitive consultations throughout both phases. The Consultant shall design and support the operationalization of a Project-level Grievance Redress Mechanism (GRM) accessible to all stakeholders, including procedures for intake, screening, resolution, documentation, GBVH sensitive handling, and reporting.

5. Permits, Clearances, and Approvals

The Consultant shall support NEGU in securing all required environmental and social permits, clearances, and state expertise approvals for Phase I and Phase II.

6. Climate risk analysis. The Consultant shall conduct a climate risk and resilience assessment for the Project, including identification of climate-sensitive transmission and substation components; collection and analysis of observed and projected climate and hydrometeorological data under relevant climate and greenhouse gas emission scenarios; assessment of Project sensitivity and exposure to climate and natural hazards such as extreme temperatures, flooding, wind, and seismic events; identification and evaluation of climate-resilient design and operational measures; and assessment of residual climate risks after application of such measures. In addition, the Consultant shall estimate greenhouse gas emission reductions attributable to the Project.

All environmental, social, gender, labor, and climate findings shall be fully integrated into the PAD and reflected, as applicable, in the Employer’s Requirements and EPC contract documentation.

5. CONSULTANT’S QUALIFICATION REQUIREMENTS

The Consultant shall be a firm with proven experience in the preparation of large-scale energy projects, preferably involving the construction of substations and transmission networks. The Consultant shall have demonstrated experience in working with international financial institutions (IFIs), such as the Asian Infrastructure Investment Bank (AIIB), World Bank, Asian Development Bank, International Finance Corporation, or similar organizations.

The Consultant shall be familiar with the regulatory framework of the Republic of Uzbekistan governing the preparation, review, and state expertise of pre-project and project documentation, including requirements for the structure and approval of the PADs, as well as with the policies, standards, and procedures of international financial institutions, particularly AIIB policies on environmental and social safeguards, procurement, and financial management. The participation of international experts, combined with national experts familiar with local conditions, language, and regulatory requirements, is encouraged, including through a consortium or joint venture between international and local firms, to ensure effective implementation of the assignment.

In addition, the Consultant shall meet the following minimum eligibility criteria:

- the Consultant shall not be under reorganization, liquidation, or bankruptcy proceedings;

- the Consultant shall have a proven record of satisfactory performance on similar assignments, and the Client reserves the right to verify past performance in accordance with AIIB procurement procedures;

- the Consultant shall not be included in the Unified Register of Unfair Performers or any other applicable debarment or exclusion lists;

- the Consultant shall possess the technical, financial, material, and human resources necessary to carry out the assignment;

- the Consultant shall have no conflict of interest and shall comply with AIIB’s requirements on integrity, transparency, and ethical conduct.

General Experience. The Consultant shall have at least ten (10) years of experience in the preparation of feasibility studies, project appraisal documents, and EPC / Design-Build contract documentation for public infrastructure projects.

International/IFI Experience. The Consultant shall demonstrate experience in assignments financed by international financial institutions, such as AIIB, World Bank, Asian Development Bank, or similar organizations, with proven compliance with their operational policies, including environmental and social safeguards, procurement, and financial management frameworks.

Project Track Record. The Consultant, either individually or as part of a joint venture or consortium, shall demonstrate experience in at least four (4) completed assignments of a similar nature (220 kV or above substations and/or transmission lines), and at least one assignment having a contract value of at least USD 1,000,000, within the last five (5) years.

Technical and Engineering Expertise. The Consultant, either individually or through a Joint Venture or consortium, shall demonstrate experience in the preparation of EPC / Design-Build contract documentation for transmission lines and substations, including conceptual design, technical specifications and Employer’s Requirements.

Environmental and Social Expertise. The Consultant or its proposed sub-consultant, either individually or as part of a Joint Venture or consortium, shall demonstrate experience in preparing environmental and social impact assessments, environmental and social management plans, resettlement action plans, stakeholder engagement plans, and related safeguard instruments in accordance with IFI requirements.

For joint ventures or consortium, the experience and qualifications of all member firms may be aggregated to meet the minimum qualification requirements, provided that each member satisfies the eligibility requirements. The lead firm shall be clearly identified and shall be jointly and severally liable with the other members for the execution of the contract. The lead firm shall be responsible for coordination and overall contract management.

6. KEY EXPERTS’ QUALIFICATION REQUIREMENTS

The Consultant shall propose a multidisciplinary team of international and national experts with appropriate academic qualifications and proven experience in large-scale power transmission projects to carry out the assignment. The consulting firm shall be capable of providing the required key expert inputs and person-months for the assignment and, if necessary, deploying additional personnel to ensure timely and high-quality completion of the services, with international expertise complemented by national specialists possessing strong knowledge of local conditions and similar projects. A preliminary breakdown of experts is presented below:

Table 3: Key International and National Experts

| No | Job Title | Input (person-month) |
| --- | --- | --- |
|  | Key International Experts |  |
| 1 | Team Leader/ Transmission and Substation Engineer | 7 |
| 2 | Environmental /Climate Lead Specialist | 2 |
| 3 | Social Development Lead Specialist | 3 |
| 4 | Economist / Financial Analyst | 2 |
|  | Sub-Total for International Experts | 14 |
|  | Key National Experts |  |
| 1 | Transmission Line Engineer | 4 |
| 2 | Substation Engineer | 4 |
| 3 | Civil / Geotechnical Engineer | 7 |
| 4 | Environmental Safeguard Specialist | 4 |
| 5 | Social / Land Acquisition Specialist | 6 |
| 7 | Survey / GIS / Routing Specialist | 3 |
| 8 | Procurement / Contract Management Specialist | 3 |
| 10 | Biodiversity Specialist/Ornithologist | 2 |
|  | Sub-Total for National Experts | 33 |
|  | TOTAL KEY EXPERTS | 47 |

The deployment of such support staff shall be at the discretion of the Consultant and shall be commensurate with the scope, complexity, and schedule of the services.

All Key Experts shall possess relevant academic qualifications from recognized institutions and have professional experience commensurate with their respective roles. All international experts shall have demonstrated experience in donor- or IFI-financed infrastructure projects (AIIB, World Bank, ADB, or similar) and shall have fluency in English (written and spoken) sufficient for report writing and professional communication. Previous working experience in countries with comparable technical, regulatory, and institutional environments (such as CIS or similar regions) is desirable for international experts. Knowledge of Russian and/or Uzbek is considered an advantage.

All national experts shall have demonstrated experience in the preparation of project concepts, project appraisal documents, feasibility studies, or equivalent national project preparation documents, as relevant to their areas of expertise, and strong knowledge of Uzbekistan’s regulatory, institutional, and permitting framework, including state expertise procedures. For all national experts, fluency in Russian/Uzbek and working-level knowledge of English is required. All experts shall be able to work effectively within multidisciplinary teams and coordinate with government authorities, utilities, and international stakeholders, as applicable to their roles.

Team Leader / Transmission and Substation Engineer (International)

- Master’s degree or higher in electrical engineering, power engineering, or a related discipline from a recognized university.

- Minimum 15 years of professional experience in the planning, design, and preparation of high-voltage transmission lines and substations.

- At least 8 years of experience in leading or coordinating multidisciplinary teams for large-scale power transmission projects.

- Demonstrated experience in at least two (2) donor- or IFI-financed assignments (AIIB, World Bank, ADB, or similar), including preparation of feasibility studies for power transmission projects.

- Proven experience in the preparation of EPC / Design-Build–oriented technical documentation, including Employer’s Requirements and performance-based technical specifications for transmission lines and substations.

- Experience with transmission projects of 220 kV and above, including coordination between transmission lines and substations.

Environmental / Climate Lead Specialist (International)

- Master’s degree or higher in environmental engineering, environmental science, natural resources management, or a related discipline from a recognized university.

- Minimum 10 years of professional experience in leading environmental assessment, climate risk and resilience assessment and management for large-scale infrastructure projects.

- Demonstrated experience in at least five (5) IFI-financed assignments (AIIB, World Bank, ADB, or similar) involving environmental impact assessment and due diligence.

- Proven experience in leading the preparation, technical review and quality assurance of Environmental and Social Impact Assessments (ESIA), Environmental and Social Management Plans (ESMP), and related environmental management plans for power transmission or similar linear infrastructure projects.

- Proven experience in leading climate risk and vulnerability assessments, including identification of climate-sensitive assets and assessment of climate hazards such as extreme temperatures, flooding, wind, and seismic risks.

- Familiarity with the AIIB Environmental and Social Framework or equivalent safeguard policies of other multilateral development banks.

- Provide 2-3 referral contact person for point 3 and 4.

Social Development Lead Specialist (International)

- Master’s degree or higher in social sciences, sociology, anthropology, development studies, or a related discipline from a recognized university.

- Minimum 15 years of professional experience in leading social impact assessment and resettlement planning for large-scale, complex infrastructure projects, with substantial international experience across multiple countries or regions in addition to work in similar contexts.

Proven experience in leading the preparation, technical review and quality assurance of full ESIA/SIA, RAP, RPF, and LRP under the AIIB ESF or equivalent IFI safeguard frameworks such as WB ESF, IFC Performance Standards, ADB SPS, or EBRD Performance Requirements, specifically for projects financed by IFIs. Demonstrated experience in at least 5 assignments as Lead Social Specialist or Lead Resettlement Specialist for IFI-financed projects

Economist / Financial Analyst (International)

- Master’s degree or higher in economics, finance, engineering economics, or a related discipline from a recognized university.

- Minimum 8 years of professional experience in economic and financial analysis of large-scale infrastructure projects, preferably in the energy or power transmission sector.

- Demonstrated experience in at least two (2) donor- or IFI-financed assignments (AIIB, World Bank, ADB, or similar) involving economic and/or financial analysis for infrastructure projects.

- Proven experience in preparing economic and financial analyses for feasibility studies, including estimation of economic benefits, investment and operating costs, and calculation of key indicators such as EIRR, ENPV, and financial viability metrics.

Transmission Line Engineer (National)

- Master’s degree or higher in electrical engineering, power engineering, or a related discipline from a recognized university.

- Minimum 10 years of professional experience in the planning, design, and feasibility-level engineering of high-voltage overhead transmission lines.

- Demonstrated experience in at least two (2) donor- or IFI-financed assignments (AIIB, World Bank, ADB, or similar) involving transmission line projects.

- Proven experience with transmission lines of 220 kV and above, including route selection, preliminary line design, tower configuration, conductor and OPGW selection, insulation coordination, and right-of-way considerations.

- Experience in preparing EPC / Design-Build–oriented technical documentation, including feasibility-level designs, technical specifications, and input to Employer’s Requirements.

- Experience in assessing constructability, logistics, and interface issues for transmission line projects.

Substation Engineer (National)

- Master’s degree or higher in electrical engineering, power engineering, or a related discipline from a recognized university.

- Minimum 10 years of professional experience in the planning, design, and feasibility-level engineering of high-voltage substations and switching stations.

- Demonstrated experience in at least two (2) donor- or IFI-financed assignments (AIIB, World Bank, ADB, or similar) involving substation projects.

- Proven experience with substations of 220 kV and above, including primary and secondary equipment layout, protection and control concepts, AIS/GIS configuration, and interface with transmission lines.

- Experience in preparing EPC / Design-Build–oriented technical documentation, including feasibility-level designs, technical specifications, and technical inputs to Employer’s Requirements.

- Experience in evaluating constructability, site constraints, access arrangements, and future expandability of substations.

Civil / Geotechnical Engineer (National)

- Bachelor’s degree or higher in civil engineering, geotechnical engineering, or a related discipline from a recognized university.

- Minimum 10 years of professional experience in civil and geotechnical investigations and design for large-scale infrastructure projects.

- Proven experience in site investigations, geotechnical assessments, and constructability analysis for transmission lines, substations, and associated facilities.

- Demonstrated experience in feasibility studies and pre-construction assessments for power transmission or similar linear infrastructure projects.

Environmental Safeguard Specialist (National)

- Bachelor’s degree or higher in environmental engineering, environmental science, natural resource management, or a related discipline from a recognized university.

- Minimum 10 years of professional experience in implementing environmental assessment and management for large-scale infrastructure projects.

- Proven experience in preparing Environmental Impact Assessments (EIA/ESIA), Environmental and Social Management Plans (ESMP), and related environmental safeguard instruments in accordance with national legislation and IFI requirements.

- Familiarity with the AIIB Environmental and Social Framework or equivalent safeguard policies of other multilateral development banks such as World Bank, ADB, EBRD, NDB etc.

- Strong knowledge of Uzbekistan’s environmental legislation, regulatory procedures, and institutional arrangements applicable to power transmission projects.

- Provide 2-3 referral contact person for point 3 and 4.

Social / Land Acquisition Specialist (National)

- Bachelor’s degree or higher in social sciences, sociology, land management, or a related discipline from a recognized university.

- Minimum 8 years of professional experience in implementing social impact assessment, land acquisition, and involuntary resettlement for infrastructure projects in Uzbekistan.

- Proven experience in preparing Resettlement Action Plans (RAP), Resettlement Planning Frameworks (RPF), social impact assessments, and related social safeguard instruments in accordance with national legislation and IFI safeguard requirements and demonstrated experience preparing such instruments specifically for projects financed by IFIs (AIIB, World Bank, ADB, IFC, EBRD).

- Demonstrated experience in at least five (5) infrastructure projects involving land acquisition and resettlement, including preparation and/or implementation of RAPs and livelihood restoration measures for IFI-financed operations.

- Strong knowledge of Uzbekistan’s land acquisition, compensation, and resettlement legislation, including the Land Code, expropriation procedures, valuation rules, compensation eligibility, and administrative processes.

- Familiarity with AIIB ESF or equivalent safeguard policies of other multilateral development banks.

Survey / GIS / Routing Specialist (National)

- Bachelor’s degree or higher in geodesy, surveying, geomatics, GIS, civil engineering, or a related discipline from a recognized university.

- Minimum 7 years of professional experience in survey, GIS, and routing studies for linear infrastructure projects, including power transmission lines.

- Demonstrated experience in conducting desktop and field-based routing studies, corridor analysis, and alignment optimization using GIS and mapping tools.

- Experience in preparing and managing GIS databases, maps, profiles, and digital outputs (e.g., GIS, AutoCAD or equivalent formats) for transmission line projects.

Procurement / Contract Management Specialist (National)

- Bachelor’s degree or higher in procurement, engineering, business administration, law, economics, or a related discipline from a recognized university.

- Minimum 8 years of professional experience in procurement and contract management for large-scale public infrastructure projects.

- Proven experience in procurement of works, goods, and consulting services under national regulations and/or IFI-financed projects, including preparation or review of procurement strategies, procurement plans, and bidding documents.

- Experience with EPC / Design-Build procurement, including contract packaging, sequencing, and contract management during project preparation stages.

- Familiarity with AIIB procurement requirements or equivalent procurement frameworks of other multilateral development banks.

- Strong knowledge of Uzbekistan’s public procurement legislation, regulations, and approval procedures, including requirements related to state expertise.

Biodiversity Specialist / Ornithologist (National)

- Bachelor’s degree or higher in biology, ecology, zoology, environmental science, or a related discipline from a recognized university.

- Minimum 5 years of professional experience in biodiversity assessment, ecological surveys, or ornithological studies for infrastructure or energy projects.

- Proven experience in conducting field surveys and assessments related to biodiversity, habitats, and avifauna, particularly for linear infrastructure such as power transmission lines.

- Familiarity with Uzbekistan’s biodiversity legislation, protected area regulations, and environmental permitting requirements and Biodiversity software such as IBAT etc.

- Provide 2-3 referral contact person for point 3 and 4.

7. CONTRACT TYPE AND DURATION

The Consultant shall be engaged under a lump-sum contract, with an anticipated assignment duration of twelve (12) months from contract signature, comprising Phase I (five months) and Phase II (seven months), subject to adjustment based on Project phasing, review, and approval timelines. Subject to approval of the Project Concept for Phase I, the Consultant may commence selected Phase II activities prior to completion of Phase I, as agreed with the NEGU and the AIIB.

8. PLACE OF WORK

The primary location for the consultancy services shall be Tashkent, Republic of Uzbekistan. The Consultant shall also be required to undertake field visits to the locations of the proposed transmission lines, substations, switching stations, and associated facilities under Phase I and Phase II of the Project, as necessary for the performance of the services. Coordination of the PC, PAD, and related project documentation shall be carried out with NEGU and relevant government authorities, including the MIIT, MOEF and other concerned ministries and agencies located in Tashkent. Any extension of the duration of services shall be subject to mutual agreement between the parties and, where applicable, the consent of AIIB.

9. REPORTING REQUIREMENTS

All reports shall be concise, analytical, and clearly structured, with supporting technical details, calculations, drawings, and datasets provided in annexes. Where applicable, standard AIIB formats and templates shall be used. The Consultant shall submit regular progress updates, interim deliverables, and final reports in accordance with the reporting schedule defined in the approved work plan, and shall maintain continuous coordination with NEGU, relevant government authorities, and AIIB throughout the assignment.

All reports shall be prepared in English, and where required for national review and approval, key documents shall also be provided in Russian or Uzbek, which is applicable. All E&S reports shall be submitted in both English and Uzbek versions as required for national review and disclosure, together with field data, survey datasets, geotagged photographs, GIS layers, stakeholder engagement evidence, and grievance logs.

The Consultant shall submit hard copies of the Project Concepts and Project Appraisal Documents (two copies in English and three copies in Russian), together with electronic versions in editable and searchable formats. Textual documents shall be provided in Microsoft Word (DOC/DOCX) and PDF, data tables and financial models in Microsoft Excel, and presentations in Microsoft PowerPoint. Technical drawings, maps, and layouts shall be submitted in agreed digital formats (e.g., AutoCAD, GIS).

Reports shall generally be prepared in A4 format, with large tables, drawings, and maps presented in A3 format where necessary. Each volume shall clearly indicate the Project title and document name on the cover page and spine. All original data generated by the Consultant, including models, databases, drawings, photographs, survey data, and analysis files, shall be submitted to NEGU in an accessible electronic format. The Consultant shall be responsible for the accuracy, consistency, and completeness of all information presented.

The Consultant shall provide draft sections or preliminary materials upon request by NEGU or AIIB to facilitate early review and feedback. The Consultant shall work closely with AIIB’s expert team during quality review processes and shall duly consider and incorporate reasonable comments and recommendations received. All reporting shall observe principles of transparency and shall be subject to monitoring by NEGU and AIIB.

The major deliverables under this assignment are summarized in Table 4. The Consultant shall prepare and submit all deliverables in accordance with the scope, sequencing, and timelines indicated therein. All payments shall be subject to satisfactory completion of the relevant deliverables and formal acceptance by NEGU and, where applicable, AIIB.

The Consultant shall prepare and maintain separate cost estimates for Phase I and Phase II of the assignment. The payment percentages indicated in Table 4 apply to the cost of the relevant Phase only and shall not be interpreted as percentages of the total contract value. Payments shall be made progressively against approved deliverables for each Phase, in accordance with the lump-sum contract and the agreed payment schedule.

Table 4: Deliverables, Submission Deadlines, and Payment Schedule

| No. | Deliverables | Deadline (after start of related Phase) |  | Payment (% of related Phase cost) |
| --- | --- | --- | --- | --- |
|  |  | Phase I | Phase II |  |
| 1 | Inception Report and Detailed Work Plan, including methodology, sequencing, and coordination arrangements for environmental, social, gender, and climate due diligence, covering preparation of framework-level instruments and Phase I component-specific E&S documentation. | 2 weeks | 2 weeks | 10 |
| 2 | Draft Project Concept (Version for NEGU/AIIB for review) including preliminary environmental, social, gender, and climate screening findings and proposed scope of E&S documentation | 1 month | 1 month | 10 |
| 3 | Approved Project Concept (both in English and Russian) together with framework-level E&S documentation applicable to both phases, including: ESMPF, RPF, SEP, LMP, GAP, Biodiversity Framework, and Climate and Disaster Risk Assessment Framework; and Phase specific scoping outputs, including National Preliminary EIA Report, ESIA Scoping Report, and ESIA Baseline Survey Plan | 2 months | 3 months | 15 |
| 4 | Draft Project Appraisal Document (Version for NEGU/AIIB for review) together with Draft Phase-specific E&S documentation disclosed for consultation, including ESIA(s), ESMP(s) and associated sub-plans (OHS, Traffic and Access, Waste and Hazardous Materials, Biodiversity, LMP, GAP), Draft RAP(s) or Due Diligence Reports (as applicable), Consultation Reports, and updated Climate Risk Assessment | 4 months | 5 months | 25 |
| 5 | Technical inputs to EPC Tender Documents, including conceptual design, approved Section 6 (Employer’s Requirements) with EPC-oriented technical specifications, reference drawings, integration of E&S requirements, and priced schedule of activities and/or bill of quantities, as applicable | 4 months | 5 months | 5 |
| 6 | Final Project Appraisal Document (submission version in English and Russian), together with Final Phase specific E&S documentation, including final ESIA(s), ESMP(s), National EIA and all associated management plans, final RAP(s) or DDR(s), finalized consultation documentation, and Final Climate Risk Assessment Report | Within 3 weeks of receipt of consolidated comments | Within 3 weeks of receipt of consolidated comments | 20 |
| 7 | Completion Report / Final Feasibility Study, including incorporation of comments during government and AIIB approval processes and technical support to early-stage EPC procurement and advance contracting activities | Upon completion of services under the relevant Phase | Upon completion of services under the relevant Phase | 15 |

Note for Item 5: Where EPC procurement is divided into multiple contract packages, this payment may be disbursed in portions upon approval of technical inputs for individual packages, and the payment shall not be conditional upon bid outcomes or contract award.

10. FINAL PROVISIONS

All intellectual property, data, models, and reports produced under this assignment shall become the property of NEGU. The Consultant shall maintain confidentiality of all Project-related information in accordance with applicable laws and AIIB requirements.

ANNEX 1

Detailed Structure of the Project Appraisal Document (PAD)

(in accordance with Annex 4 to the Regulation on the Procedure for Preparation, Implementation, Monitoring and Post-Monitoring of Projects with Participation of International Financial Institutions and Foreign Government Financial Organizations)

I. Project Profile

This section shall present the key characteristics of the proposed Project, including the Project title, location, main technical and economic parameters, capacity and scale indicators, Project components, sources, terms and mechanisms of financing, key advantages and constraints, principal Project risks, and other essential information.

II. Strategic Context of the Project

- Country context

- Sectoral and institutional context

- Alignment with national strategies, programs, and development concepts

- Contribution and impact of the Project on the relevant sector, region, and subsector, and justification of the need for Project implementation

This section shall analyze the national, sectoral, and institutional context in which the Project will be implemented, assess its consistency with national development strategies and sector programs, evaluate the Project’s contribution and impact at sectoral, regional, and subsector levels, and present the rationale for Project preparation, including key stakeholders and institutional arrangements.

III. Project Objectives

- Project objectives and scope

- Project implementation strategy

- Project stakeholders

- Analysis of similar projects implemented previously

This section shall describe the Project’s main objectives and tasks, advantages and limitations, key constraints, implementation strategy, and stakeholder roles. It shall also include an analysis of lessons learned from previous investment projects in the sector and a review of comparable projects and their outcomes.

IV. Project Description

- Project components

- Project cost and financing sources

This section shall describe the Project location, scale, and components; provide a breakdown of Project costs, including cost composition, quantities, and pricing assumptions; identify financing institutions; and present the allocation of costs by financing source and expenditure category.

V. Project Implementation Arrangements

- Institutional arrangements and implementation measures

- Monitoring and evaluation mechanisms

- Project sustainability

- Readiness of Project facilities and availability of permits and approvals

This section shall describe the organization of Project implementation, including the roles and responsibilities of all stakeholders, the availability of human, technical, and financial resources, monitoring and evaluation arrangements, and the overall readiness of Project facilities, including permits and approvals required for implementation.

VI. Project Appraisal

- Technical feasibility assessment

- Procurement approach

- Climate change and natural disaster risks

- Financial management capacity of the executing agency and debt service assessment

- Economic and financial analysis

- Social aspects (including social protection)

- Environmental impacts and environmental protection

This section shall provide a comprehensive appraisal of the proposed Project, including assessment of the current state of the sector, demand analysis, justification of Project capacity, availability of required resources, and technical solutions. It shall describe selected technologies and equipment, justify marginal cost benchmarks, and assess master planning and engineering solutions, site conditions, and compliance with planning and construction norms. Cost estimates for construction and associated services shall be benchmarked against similar projects or unit costs and reflected in accordance with adopted design solutions, drawings, diagrams, and physical quantities (BOQ, where applicable).

The section shall also present the procurement plan and implementation schedule, as well as detailed economic and financial analyses, including investment and operating costs, economic benefits, efficiency indicators, and optimal allocation of Project and production capacities. In addition, social and environmental impacts, effects on stakeholders, and compliance with national policies and IFI safeguard requirements shall be assessed.

VII. Key Project Risks

- Overall risk assessment and mitigation measures

This section shall identify and analyze key Project risks, including operational, technical, financial, climate-related, and natural disaster risks, and propose appropriate risk mitigation strategies and measures.

VIII. Annexes

- Project Implementation Manual

- Procurement assessment and procurement planning documents

- Preliminary Terms of Reference for Project implementation consultants

- Decisions on allocation of Project sites (land, facilities, structures)

- Engineering and geological surveys (where required)

- Technical conditions for connection to utility networks

- State environmental expertise conclusion (where required)

- Other relevant supporting documents

Note

The Project Appraisal Document shall be prepared on the basis of the approved Project Concept. The Government Commission on Investment Attraction, Industrial Development, and Trade Regulation reserves the right to introduce amendments to the structure of the Project Appraisal Document, as necessary.

A specialized computer software used by electrical engineers to model, analyze, and simulate power systems — like electricity grids, generation plants, and transmission networks.