## Publication - PP
S000671 Obigarm-Nurobod Road Project – Long Bridge and Approaches
Project Country: | Tajikistan | Bank's Approval Date of the Initial Procurement Plan: | 02-17-2025
Project Sector: | Transport | Approved PP Update No.: | Version 3
AIIB Loan (USD Million): |  | Bank's Approval Date of the PP Update: | 09-21-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Activity Status
Ministry of Transport, Project Implementation Unit for Roads Rehabilitation | NCS-01/1 | Deputy Project Manager | 24,000.00 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Post |  |  | 09-01-2026 | Cleared
Ministry of Transport, Project Implementation Unit for Roads Rehabilitation | NiCS-03 | Gender Assistant | 26,400.00 | 100.00 | Consulting Services | LCSIC (Limited Competitive Selection of Individual Consultants) |  |  | Post |  | 06-24-2025 | 08-01-2025 | Cleared
Ministry of Transport, Project Implementation Unit for Roads Rehabilitation | CS-01 | International Consulting Company for the implementation of the Capacity building of road sector professionals component | 1,023,000.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Post |  | 09-18-2025 | 03-12-2026 | Cleared
Ministry of Transport, Project Implementation Unit for Roads Rehabilitation | NCS-02 | Training Specialist | 30,000.00 | 100.00 | Consulting Services | LCSIC (Limited Competitive Selection of Individual Consultants) |  |  | Post |  | 02-24-2025 | 04-03-2025 | Cleared
Ministry of Transport, Project Implementation Unit for Roads Rehabilitation | NCS-01 | Project Manager | 48,000.00 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Post |  |  | 03-22-2025 | Cleared
|  | Total: | 1,151,400.00