## Publication - PP
S000692 Nepal Project: Siddartha Highway (Butwal-Pokhara Section) Improvement Project
Project Country: | Nepal | Bank's Approval Date of the Initial Procurement Plan: | 08-17-2026
Project Sector: | Transport | Approved PP Update No.: | Version 1
AIIB Loan (USD Million): |  | Bank's Approval Date of the PP Update: | 08-17-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Months) | Activity Status
Development Cooperation Implementation Division, Department of Roads | AIIB-DOR-BP-QCBS-1 | Consultancy Services for Detailed Project Report (DPR) Preparation, Institutional Strengthening & Capacity Building, Tender & Contract Documentation, Environment and Social Impact Assessment (ESIA) and Resettlement Plan (RP) of the proposed Siddhartha Highway (Butwal-Pokhara Section) Improvement Project | 1,961,748.19 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 08-20-2026 | 04-18-2027 | 18 | Cleared
|  | Total: | 1,961,748.19