## Spreadsheet1
Project: GUAÍBA+RESILIENT
Project Number:
Date: 04/07/2025
Serial number | Contract number | Contract description | Acquisition Category | Cost estimate (US$ million) | Acquisition method | Bank Assessment | Expected date for publication of REOI / SPN | Contract duration | Retroactive Financing
1 |  | Execution of macro drainage work - Celupa conduit | Works | 734875.3468 | National Competitive Bidding (NCT) | Yes | 2026-01-30 | 11 months | No
2 |  | Study and executive projects for macro-drainage and dike in the Santa Rita sub-basin | Consulting service | 101102.9412 | Direct hiring (DC) | Yes | 2025-10-30 | 10 months | Yes
3 |  | Environmental and urban licensing of the macro-drainage works project for the Santa Rita sub-basin.Comprehensive study involving dike and macrodrainage | Consulting service | 88235.2941 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2026-10-30 | 10 months | No
4 |  | Execution of macrodrainage works in the Santa Rita sub-basin | Works |  | National Competitive Bidding (NCT) | Yes | 2027-10-30 | 22 months | No
5 | - | Execution of prior licensing, installation and operation of the project for the construction of a dike and drainage solutions | Consulting service | 88235.2941 | Direct hiring (DC) | Yes | 2028-04-30 | 37 months | No
6 | - | Execution of works on the city's protective dike | Works | 31686943.1023 | National Competitive Bidding (NCT) | Yes | 2029-04-30 | 16 months | No
7 | - | Acquisition of areas for the implementation of the logistics and industrial hub | Goods | 2939501.3871 | National Competitive Bidding (NCT) | Yes | 2025-08-31 | Single delivery | No
8 |  | Registration of the area in the name of the city hall in the Property Registry | Non-consulting services | 64338.2353 | Direct hiring (DC) | No | 2026-01-30 | Single delivery | No
9 |  | Execution of the traffic study of resilient roads and logistics and industrial hub | Consulting service | 45955.8824 |  | Yes | 2026-01-30 | 10 months | No
10 | - | Execution of a carbon footprint study of roads and logistics and industrial hubs | Consulting service | 18382.3529 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2026-01-30 | 10 months | No
11 |  | Execution of the preliminary licensing of the logistics hub and industrial district project | Consulting service | 47794.1176 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2026-07-30 | 10 months | No
12 | - | Execution of the urban planning project for the logistics and industrial hub | Consulting service | 388786.7647 | National Competitive Bidding (NCT) | Yes | 2026-12-30 | 10 months | No
13 | - | Execution of licensing for the installation of the logistics and industrial hub | Consulting service | 20220.5882 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2027-11-30 | 10 months | No
14 | - | Execution of executive, urban and complementary projects | Consulting service | 647977.9412 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2027-11-30 | 10 months | No
15 | - | Execution of infrastructure works for the implementation of the logistics hub and industrial city | Works | 12992596.1309 | National Competitive Bidding (NCT) | Yes | 2028-11-30 | 22 months | No
16 | - | Execution of licensing for the operation of the logistics and industrial hub | Consulting service | 20220.5882 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2030-07-30 | 3 months | No
17 | - | Execution of topography of the consolidated urban waterfront - in stages (drone image and curves + cadastral survey + infrastructure registration) | Consulting service | 18382.3529 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2025-09-30 | 10 months | Yes
18 |  | Graphics of the Review of conceptual studies for the implementation of the Revitalization Project of the Municipality of Guaíba area, including the entire consolidated coastline - Master Plan (Modules A, B and C) | Consulting service | 11580.8824 | Direct hiring (DC) |  | 2025-07-30 | 10 months | Yes
19 | - | Urban impact assessment study, historical and environmental heritage | Consulting service | 31250 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2026-01-30 | 10 months | No
20 | - | Preparation of executive projects for module A (Gomes Jardim Squares, 14 de Outubro Street and staircase and Gastão Leão Square) | Consulting service | 119485.2941 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2026-12-30 | 10 months | No
21 |  | Execution of works of module A | Works | 2388344.877 | National Competitive Bidding (NCT) | Yes | 2027-12-30 | 12 months | No
22 | - | Preparation of executive projects for module B (Waterfront and urban park) | Consulting service | 1102941.1765 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2026-12-30 | 10 months | No
23 |  | Execution of prior environmental licensing – LP – Module B | Consulting service | 47794.1176 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2028-01-30 | 10 months | No
24 |  | Execution of environmental licensing for installation – LI – Module B | Consulting service | 20220.5882 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2028-06-30 | 10 months | No
25 |  | Execution of works of module B | Works | 22046260.4031 | National Competitive Bidding (NCT) | Yes | 2029-01-30 | 22 months | No
26 | - | Execution of environmental licensing for module B operations | Consulting service | 20220.5882 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2030-06-30 | 10 months | No
27 | - | Preparation of the executive project for module C | Consulting service | 59742.6471 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2026-12-30 | 10 months | No
28 |  | Execution of prior and installation environmental licensing - Module C | Consulting service | 68014.7059 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2027-12-30 | 10 months | No
29 | - | Execution of works of module C | Works | 1194172.4385 | National Competitive Bidding (NCT) | Yes | 2028-01-30 | 12 months | No
30 | - | Layout study and executive project of resilient roads | Consulting service | 27573.5294 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2027-12-30 | 10 months | No
31 |  | Execution of prior environmental and installation licensing for the implementation of roads. | Consulting service | 68014.7059 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2028-01-30 | 10 months | No
32 |  | Execution of works on new resilient roads | Works | 4997152.358 | National Competitive Bidding (NCT) | Yes | 2029-01-31 | 19 months | No
33 |  | Environmental licensing operation for new resilient roads | Consulting service | 20220.5882 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2030-06-30 | 10 months | No
34 |  | ESMPF, RPF, SEP and GRM Report | Consulting service | 73590.4172 | Direct hiring (DC) | Yes | 2025-05-30 | 2 months | Yes
35 |  | Update of the Municipal Basic Sanitation Plan | Consulting service | 44974.3712 | National Competitive Bidding (NCT) or Direct Contracting (CD) |  |  |  | Yes
36 |  | In-person technical training on climate resilience for civil servants | Consulting service | 91859.4183 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2027-01-30 | 10 months | No
37 |  | Workshops with practical simulations and integrated training | Consulting service | 91859.4183 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2028-01-30 | 10 months | No
38 |  | Teaching material, certified support material | Goods | 16167.2576 | National Competitive Bidding (NCT) or Direct Contracting (CD) | No | 2027-01-30 | 28 months | No
39 |  | Environmental and climate monitoring system | Consulting service/goods | 499715.2358 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2026-01-30 | 60 months | No
40 |  | Program management and participatory evaluation - training vulnerable populations | Consulting service | 17269.5706 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2026-06-30 | 28 months | No
41 |  | Community risk management and first aid workshops | Consulting service | 18371.8837 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2027-03-30 | 10 months | No
42 |  | Training of 100 community multipliers | Consulting service | 18371.8837 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2028-01-30 | 10 months | No
43 |  | Itinerant lectures and discussion groups in communities | Consulting service | 18371.8837 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2028-01-30 | 10 months | No
44 |  | Financial education and basic productive inclusion | Consulting service | 18371.8837 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2029-01-30 | 10 months | No
45 |  | Support materials and basic kits (digital and printed) | Goods | 9185.9418 | National Competitive Bidding (NCT) or Direct Contracting (CD) | No | 2027-01-30 | 40 months | No
46 |  | Technical supervision consultancy for works | Consulting service | 793665.3745 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2027-06-30 | 40 months | No
47 |  | Environmental and Social Consulting | Consulting service | 826734.7651 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2027-06-30 | 40 months | No
48 |  | Project Management Consulting and Physical-Financial Monitoring | Consulting service | 440925.2081 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2027-06-30 | 40 months | No
49 |  | Support for the Management of the UGP (Program Management Unit) | Consulting service | 699601.3301 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2026-01-30 | 60 months | No
50 |  | Independent Financial Audit of the Program | Consulting service | 149914.5707 | National Competitive Bidding (NCT) or Direct Contracting (CD) | Yes | 2026-01-30 | 60 months | No

## Plan1 (hidden)
January | 0 | January2023 | 1
February | 1 | February2023 | 2
March | 2 | March2023 | 3
April | 3 | April2023 | 4
May | 4 | May2023 | 5
June | 5 | June2023 | 6
July | 6 | July2023 | 7
August | 7 | August2023 | 8
September | 8 | September 2023 | 9
October |  | October2023 | 10
November |  | November2023 | 11
December |  | December2023 | 12
|  | January2024 | 13
|  | February2024 | 14
|  | March2024 | 15
|  | April2024 | 16
|  | May2024 | 17
|  | June2024 | 18
|  | July2024 | 19
|  | August2024 | 20
|  | September2024 | 21
|  | October2024 | 22
|  | November2024 | 23
|  | December2024 | 24
|  | January2025 | 25
|  | February2025 | 26
|  | March2025 | 27
|  | April2025 | 28
|  | May2025 | 29
|  | June2025 | 30
|  | July2025 | 31
|  | August2025 | 32
|  | September2025 | 33
|  | October2025 | 34
|  | November2025 | 35
|  | December2025 | 36
|  | January2026 | 37
|  | February2026 | 38
|  | March2026 | 39
|  | April2026 | 40
|  | May2026 | 41
|  | June2026 | 42
|  | July2026 | 43
|  | August2026 | 44
|  | September2026 | 45
|  | October2026 | 46
|  | November2026 | 47
|  | December2026 | 48
|  | January2027 | 49
|  | February2027 | 50
|  | March2027 | 51
|  | April2027 | 52
|  | May2027 | 53
|  | June2027 | 54
|  | July2027 | 55
|  | August2027 | 56
|  | September2027 | 57
|  | October2027 | 58
|  | November2027 | 59
|  | December2027 | 60
|  | January2028 | 61
|  | February2028 | 62
|  | March2028 | 63
|  | April2028 | 64
|  | May2028 | 65
|  | June2028 | 66
|  | July2028 | 67
|  | August2028 | 68
|  | September2028 | 69
|  | October2028 | 70
|  | November2028 | 71
|  | December2028 | 72
|  | January2029 | 73
|  | February2029 | 74
|  | March2029 | 75
|  | April2029 | 76
|  | May2029 | 77
|  | June2029 | 78
|  | July2029 | 79
|  | August2029 | 80
|  | September2029 | 81
|  | October2029 | 82
|  | November2029 | 83
|  | December2029 | 84
|  | January2030 | 85
|  | February2030 | 86
|  | March2030 | 87
|  | April2030 | 88
|  | May2030 | 89
|  | June2030 | 90
|  | July2030 | 91
|  | August2030 | 92
|  | September2030 | 93
|  | October2030 | 94
|  | November2030 | 95
|  | December2030 | 96
|  | January2031 | 97
|  | February2031 | 98
|  | March2031 | 99
|  | April2031 | 100
|  | May2031 | 101
|  | June2031 | 102
|  | July2031 | 103
|  | August2031 | 104
|  | September2031 | 105
|  | October2031 | 106
|  | November2031 | 107
|  | December2031 | 108