## Sheet1
Cambodia: Climate Adaptive Irrigation and Sustainable Agriculture for Resilience Project
Loan Number L0452A
PP of April 2025
Serial No. | Contract Number | Contract Description | Procurement Category (G/W/NCS/CS) | Cost Estimate (US$ Million) | Procurement Method | Bank's Review (prior review/post review) | Sheduled Date of Publication of REOI / SPN | Contract Duration | Advance Procurement (Y/N) | Retroactive Financing (Y/N)
A. Consulting Services
CS-01 | AIIB-CAISAR-CS01* | Project Management and Implementation Consultant (PMIC) | CS | 6 | IOCS/QCBS | Prior | Q2-2025 | 6 years | Y | Y
CS-02 | AIIB-CAISAR-CS02 | International Individual Procurement Consultant (IIPC) | CS | 0.072 | OCSIC | Prior | Q2-2025 | 6 Months | Y | Y
CS-03 | AIIB-CAISAR-CS03 | International Individual Project Irrigation Design Specialist | CS | 0.072 | OCSIC | Post | Q2-2025 | 6 Months | Y | Y
CS-05 | AIIB-CAISAR-CS04 | National M&E Specialist | CS | 0.05 | LCSIC | Post | Q2-2025 | 12 months | Y | Y
CS-06 | AIIB-CAISAR-CS05 | Naitonal Project Management Specialist | CS | 0.05 | LCSIC | Prior | Q2-2025 | 12 months | Y | Y
CS-07 | AIIB-CAISAR-CS06 | Preparation of Initial Environmental Impact Assessment (IEIA) Firm | CS | 0.2 | IOCS/QCBS | Post | Q2 2025 | 4 Months | Y | Y
B. Works
W01 | AIIB-CAISAR-W01 | Modernization of main canal and distribution system of Krepeu Trom scheme | W | 4.8 | NCT | Prior | Q2-2025 | 24 months | N | N
W02 | AIIB-CAISAR-W02 | Modernization of main canal and distribution system of Ou Ta Poung Scheme 1) Feeder Canal 1 from DAMC (Option1), 2) Feeder Canal 2 from DAMC (Option 3), 3) Kabal Hong Main Canal (Option 5), 4) Distribution system and ponds 5) Command Area Development (Tertiary canals) | W | 79.22 | IOCT | Prior | Q2 2026 | 48 months | N | N
W03 | AIIB-CAISAR-W03 | Modernization of main canal and distribution system of Lum Harch scheme | W | 1.38 | NCT | Post | Q3 2026 | 12 months | N | N
W04 | AIIB-CAISAR-W04 | Modernization of main canal and distribution system of Yotasast Scheme | W | 2.77 | NCT | Post | Q3 2026 | 18 months | N | N
W05 | AIIB-CAISAR-W05 | Modernization of main canal and distribution system of Stoeung Krang Bat Scheme | W | 4.48 | NCT | Post | Q3 2026 | 24 months | N | N
W06 | AIIB-CAISAR-W06 | Modernization of main canal and distribution system of Brambei Mom Scheme | W | 5.25 | NCT | Post | Q3 2026 | 30 months | N | N
C. Goods and PMU equpment
G01 | AIIB-CAISAR-G01 | Vehicles | G | 0.36 | NCT | Prior | Q2 2025 |  | Y | Y
G02 | AIIB-CAISAR-G02 | Compuetrs and Office Equipment | G | 0.082 | RFQ | Post | Q2 2025 |  | Y | Y
G03 | AIIB-CAISAR-G03 | Motorcycles | G | 0.014 | RFQ | Prior | Q2 2025 |  | Y | Y
G04 | AIIB-CAISAR-G04 | Office furnitures | G | 0.016 | RFQ | Post | Q2 2025 |  | Y | Y
G05 | AIIB-CAISAR-G05**** | Supply and Installation and Commissioning of AWS equipment for Meteorology Station in Ou Ta Poung project area - Lot 1 | G | 4.5 | IOCT | Prior | Q4 2026 | 12 months | N | N
|  | Supply and Installation and Commissioning of AHS equipped for hydrology stations in Ou Ta Poung project area - Lot 2 | G |  | IOCT | Prior | Q4 2026 | 12 months | N | N
G06 | AIIB-CAISAR-G06 | Water Informatiuon and Management System (SCADA) in Pursat river basin | G | 0.49 | NCT | Prior | Q2 2026 | 12 months | N | N
Note on E14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The cost needs to be reconciled as it is mentioned as USD 3.16m in Annex 4B.
Note on H14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The projection was based on report that DED1 will be completed Q1 2025
Note on E15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No basis yet
Note on E25: Monichoth HP: included Software and Hardware network, downscalling model,NWP,climatology database,intergrated all data country wide and region ,capacity building to support flood proofting