## PP_1022-ENG
Attachment 1-China: Hubei Global Air Cargo Logistics Project----Procurement Plan (Updated Oct 2025)
$1 = CNY | AIIB Project Appraisal Mission Aide-Memoire | [11 empty] | Preparation Date |  |  | 2025.10.22
7.225 | 2024-10-22
Contract No. | Contract Name | Description of Contract Content | Estimated Contract Price |  | AIIB Loan | Type of Contract | Procurement Method | Contract Period (Months) | Review Method | Adopted Type of Bidding Documents | Advance Procurement | Estimated Announcement Date | Estimated Tender Opening Time | Estimated Contract Signing Time | Estimated Contract Completion Time | Notes
|  |  | CNY (in 10,000 RMB) | USD (in 10,000 USD) | Percentage (%)
Component 1: | Customs Operation and Bonded Facilities
HGAC-CW03 | Bonded Logistics Warehouse (3) | E01/E02 Standard Warehouses, with a total construction area of 44,150.04 m² | 14990.15 | 2074.7612 | 100% | CW | NCT | 6 | Prior | AIIB-MTD for China NCT Works | No | 2026.01 | 2026.02 | —— | —— | ——
HGAC-CW04 | Bonded Logistics Warehouse (4) | E03/E04 Standard Warehouses, with a total construction area of 44,150.04 m² | 14992.14 | 2075.0367 | 100% | CW | NCT | 6 | Prior |  | No | 2025.11 | 2025.12 | —— | —— | ——
HGAC-CW05 | Bonded Logistics Warehouse (5) and Auxiliary Works | H01/H04 Logistics Warehouses, H05 Equipment Room, H06 Truck Ramp, H09 Elevated Platform, with a total construction area of 60,362.735 m² | 22190.51 | 3071.3509 | 100% | CW | NCT | 6 | Prior |  | No | 2025.11 | 2025.12 | —— | —— | ——
HGAC-CW06 | Bonded Logistics Warehouse (6) and Auxiliary Works | H02/H03 Logistics Warehouses, H10 Elevated Platform, with a total construction area of 59,146.61 m² | 21353.59 | 2955.5142 | 100% | CW | NCT | 6 | Prior |  | No | 2025.12 | 2026.01 | —— | —— | ——
HGAC-CW07 | Bonded Logistics Warehouse (7) and Auxiliary Works | E05/L01 Logistics Warehouses, H07 Equipment Room, H08 Truck Ramp, H11 Elevated Platform, with a total construction area of 60,092.98 m² | 22112.58 | 3060.5647 | 100% | CW | NCT | 6 | Prior |  | No | 2025.12 | 2026.01 | —— | —— | ——
Subtotal |  |  | 95638.97 | 13237.2277 | 100%
Component 2: | Trade and Freight Service Facilities
HGAC-CW08 | Trade and Freight Service Facilities (3) | W01-C Comprehensive Office Building, with a construction area of 17,090 m² | 17209.5 | 2381.9377 | 100% | CW | NCT | 6 | Prior | AIIB-MTD for China NCT Works | No | 2025.12 | 2026.01 | —— | —— | ——
HGAC-CW13 | Other Works (Such as: Greening, Landscaping Works, etc.) | Other works, including landscape greenery, landscape water features, landscape electrical systems, outdoor signs and plaques, etc. | 6148.5726 | 851.0135 | 100% | CW | NCT | 6 | Prior |  | No | 2025.1 | 2025.11 | —— | —— | ——
Subtotal |  |  | 23358.0726 | 3232.9512 | 100%
Component 3: | Low-Carbon, Smart and Supporting Utilities
HGAC-GD01 | Rooftop Photovoltaic (1) | Procurement and Installation of Rooftop Photovoltaic Equipment for the Customs Inspection Center and Bonded Warehouses 1#-5# in Phase I (Starter Zone), with a total photovoltaic panel area of 26,163 m². | 2826 | 391.1419 | 100% | Goods | NCT | 12 | Prior | AIIB-MTD for China NCT Goods | No | 2025.1 | 2025.11 | —— | —— | ——
HGAC-GD02 | Rooftop Photovoltaic (2) | Procurement and Installation of Rooftop Photovoltaic Equipment for Self-Constructed Buildings in the Southern Area (Bonded Warehouses 1#/2#/3# and Bonded Processing Buildings 1#/2#), with a total photovoltaic panel area of 42,695 m². | 3072.5332 | 425.2641 | 100% | Goods | NCT | 12 | Prior |  | No | 2026.04 | 2026.05 | —— | —— | ——
HGAC-GD03 | Rooftop Photovoltaic (3) | Procurement and Installation of Rooftop Photovoltaic Equipment for All Buildings in the Northern Area (Funded by AIIB) North of Wuchu Avenue, including S01 Duty-Free Service Center, W01 Comprehensive Office Building, T01 Inspection Site, E01/E02/E03/E04 Standard Warehouses, and H01/H02/H03/H04/E05/J01/K01/L01/M01-A/M01-B Logistics Warehouses, with a total photovoltaic panel area of 95,717 m². | 6854.1126 | 948.6661 | 100% | Goods | NCT | 18 | Prior |  | No | 2026.12 | 2027.07 | —— | —— | ——
HGAC-GD04 | Smart Operation System (1) | South of Wuchu Avenue: Equipment and Software for the Smart Operation System of the Park, covering the Commercial Logistics Center, Warehouses 1-5, Customs Inspection Center, International Cargo Terminal 1#, International Cargo Terminal 2#, T01 Inspection Site, J01/K01/M01-A/M01-B, S01 Duty-Free Service Center, and W01 Comprehensive Office Building; Outdoor Works: Video Surveillance System, Parking Management System, and Public Address System; Exhibition Design and Setup for the Smart Operation Center. | 2983.69 | 412.9675 | 100% | Goods | NCT | 12 | Prior |  | No | 2025.12 | 2026.01 | —— | —— | ——
HGAC-GD05 | Smart Operation System (2) | North of Wuchu Avenue: Smart Operation System Equipment for E01/E02/E03/E04 Standard Warehouses and H01/H02/H03/H04/E05/L01 Logistics Warehouses; Outdoor Works: Video Surveillance System, Parking Management System, Public Address System, and Weak Current Pipeline Network Project, etc. | 1165.21 | 161.2747 | 100% | Goods | NCT | 12 | Post-review |  | No | 2026.04 | 2026.05 | —— | —— | ——
HGAC-GD06 | Integrated Digital Platform | Smart Customs Auxiliary Supervision Platform, Application Support Platform, Enterprise Customs Clearance Service Platform, Multimodal Transport Platform, Park Vehicle and Pedestrian Control Equipment, Park Video Equipment, Park Office Informatization Equipment, Park Safety/Energy Efficiency/Fire-Fighting Equipment, Digital Loading Docks, Digital Warehouses, One-Stop Security Inspection Area, and Quarantine Processing Area, etc. | 18142.15 | 2511.0242 | 100% | Goods | IOCT | 34 | Prior | AIIB SPD for Goods | No | 2026.12 | 2027.01 | —— | —— | ——
HGAC-GD07 | Others | Others | 24521.3716 | 3393.9615 | 100% | Goods | IOCT | 30 | Prior | —— | No | 2027.04 | 2027.05 | —— | —— | ——
Subtotal |  |  | 59565.0674 | 8244.3 | 100%
Component 4: | Capacity Building
HGAC-CS01 | Project Management | Technical Support for Project Management, Training, Study Tours, Development and Promotion of Knowledge Products, etc. | 1000 | 138.4083 | 100% | Consulting Services | IOCS/QCBS | 48 | Prior | AIIB SPD for Consulting Service | No | 2025.1 | 2025.11 | —— | —— | ——
HGAC-CS04 | International Green Building Certification | Certification for New Buildings Related to International Green Building | 761 | 105.3287 | 100% | Consulting Services | IOCS/QCBS | 46 | Prior | AIIB SPD for Consulting Service | No | 2025.12 | 2026.01 | —— | —— | ——
HGAC-CS05 | Consulting on Three-Star Green Building Certification | Three-Star Green Building Certification for New Domestic Buildings | 116 | 16.0554 | 100% | Consulting Services | NCS/CQS | 46 | Post-review | —— | No | 2025.12 | 2026.01 | —— | —— | ——
HGAC-CS06 | Research on Innovative Topics of Customs Supervision Model | Research on Innovative Topics of Customs Supervision Model | 180 | 24.9135 | 100% | Consulting Services | NCS/CQS | 36 | Post-review | —— | No | 2026.06 | 2026.07 | —— | —— | ——
HGAC-CS07 | Research on Innovative Topics of Integrated Multi-Inspection | Research on Innovative Topics of Integrated Multi-Inspection | 180 | 24.9135 | 100% | Consulting Services | NCS/CQS | 36 | Post-review | —— | No | 2026.06 | 2026.07 | —— | —— | ——
HGAC-CS08 | Research on Innovative Topics of Multimodal Transport | Research on Innovative Topics of Multimodal Transport | 180 | 24.9135 | 100% | Consulting Services | NCS/CQS | 36 | Post-review | —— | No | 2026.06 | 2026.07 | —— | —— | ——
Subtotal |  |  | 2417 | 334.5329 | 100%
Total |  |  | 180979.11 | 25049.0118 | 100%

## 采购计划1225_中文 (hidden)
附件1-亚投行贷款湖北航空货运产业园项目采购计划 (2024年12月更新)
1美元=人民币 | 亚投行项目评估考察备忘录
7.11 | 2024-04-12
合同编号 | 合同名称 | 合同内容描述 | 合同估算价 |  | 亚投行贷款 | 合同类型 | 采购方式 | 合同期 (月) | 审查 方式 | 采用招标文件类型 | 提前 采购 | 追溯贷款 | 预计 公告日期 | 预计 开标时间 | 预计合同 签订时间 | 预计合同 完成时间 | 备注
|  |  | 人民币 (万元) | 美元 (万元) | 占比 (%)
组成部分1: | 海关业务和保税设施
HGAC-CW01 | 海关运营设施 | (1) 海关查验仓库T01，面积10,911 m2 ; (2) 卡口与围网: #2海关卡口 949 m2、围网7,730 m | 6876.7533 | 967.1946 | 100% | 土建 | NCT | 18 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
1.1 | T01 | T01 海关查验仓库 | 5931.3338 |  | 100%
1.1.1 |  | 土建工程 | 4137.5599 |  | 100%
1.1.2 |  | 给排水工程 | 13.9661 |  | 100%
1.1.3 |  | 电气工程 | 125.6947 |  | 100%
1.1.4 |  | 暖通工程 | 97.7626 |  | 100%
1.1.5 |  | 消防工程 | 216.4742 |  | 100%
1.1.6 |  | 设备工程 | 59.6525 |  | 100%
1.1.7 |  | 场平工程 | 218.22 |  | 100%
1.1.8 |  | 室外工程 | 1024.0038 |  | 100%
1.1.8 |  | 绿建工程 | 38 |  | 100%
|  | 废弃物绿色处理 | 1 |  | 100%
|  | 雨洪管理设施 | 4 |  | 100%
|  | LEED认证增量措施 | 33 |  | 100%
1.2 |  | 2#海关卡口 | 481.6195 |  | 100%
1.2.1 |  | 地基处理 | 3.3215 |  | 100%
1.2.2 |  | 土建工程 | 455.52 |  | 100%
1.2.3 |  | 给排水工程 | 2.847 |  | 100%
1.2.4 |  | 暖通工程 | 3.796 |  | 100%
1.2.5 |  | 电气工程 | 8.541 |  | 100%
1.2.6 |  | 抗震支架 | 5.694 |  | 100%
1.2.7 |  | 标识标牌 | 1.9 |  | 100%
1.4 |  | 海关围网 | 463.8 |  | 100%
HGAC-CW02 | 保税物流仓库 (一) | 保税物流仓库M01，建筑面积总计20,396 m2 | 13277.6977 | 1867.468 | 100% | 土建 | NCT | 18 | 前审 | 是 |  |  | 2025.3 | 2025.4 | 2025.6 | 2026.12
2.8 | M01 物流仓库 |  | 13277.6977 | 1867.468 | 100% |  |  |  | 前审
2.8.1 | 土建工程 |  | 9630.4162 | 1354.4889 | 100% |  |  |  | 前审
2.8.2 | 给排水工程 |  | 32.5069 | 4.572 | 100% |  |  |  | 前审
2.8.3 | 电气工程 |  | 292.5619 | 41.1479 | 100% |  |  |  | 前审
2.8.4 | 暖通工程 |  | 227.5482 | 32.004 | 100% |  |  |  | 前审
2.8.5 | 消防工程 |  | 503.8566 | 70.8659 | 100% |  |  |  | 前审
2.8.6 | 设备工程 |  | 138.8447 | 19.5281 | 100% |  |  |  | 前审
2.8.7 | 场平工程 |  | 507.92 | 71.4374 | 100% |  |  |  | 前审
| 室外工程 |  | 1881.0431 | 264.563 | 100% |  |  |  | 前审
2.8.8 | 绿建工程 |  | 63 | 8.8608 | 100% |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 100% |  |  |  | 前审
| 雨洪管理设施 |  | 11 | 1.5471 | 100% |  |  |  | 前审
| LEED认证增量措施 |  | 51 | 7.173 | 100% |  |  |  | 前审
HGAC-CW03 | 保税物流仓库 (二) | 保税物流仓库J01 / K01、架空平台3，建筑面积总计42,780 m2 | 25772.9634 | 3624.8894 | 100% | 土建 | NCT | 18 | 前审 | 是 |  |  | 2025.3 | 2025.4 | 2025.6 | 2026.12
2.15 | J01 物流仓库 |  | 11277.3601 | 1586.1266 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.1 | 土建工程 |  | 8671.015 | 1219.552 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.2 | 给排水工程 |  | 29.2685 | 4.1165 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.3 | 电气工程 |  | 263.4163 | 37.0487 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.4 | 暖通工程 |  | 204.8794 | 28.8157 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.5 | 消防工程 |  | 453.6614 | 63.8061 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.6 | 设备工程 |  | 125.0127 | 17.5827 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.7 | 场平工程 |  | 457.32 | 64.3207 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| 室外工程 |  | 1015.7868 | 142.8673 | 100%
2.15.8 | 绿建工程 |  | 57 | 8.0169 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| 废弃物绿色处理 |  | 1 | 0.14065 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| 雨洪管理设施 |  | 9 | 1.2658 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| LEED认证增量措施 |  | 47 | 6.6104 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16 | K01 物流仓库 |  | 11277.3601 | 1586.1266 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.1 | 土建工程 |  | 8671.015 | 1219.552 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.2 | 给排水工程 |  | 29.2685 | 4.1165 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.3 | 电气工程 |  | 263.4163 | 37.0487 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.4 | 暖通工程 |  | 204.8794 | 28.8157 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.5 | 消防工程 |  | 453.6614 | 63.8061 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.6 | 设备工程 |  | 125.0127 | 17.5827 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.7 | 场平工程 |  | 457.32 | 64.3207 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| 室外工程 |  | 1015.7868 | 142.8673 | 100%
2.16.8 | 绿建工程 |  | 57 | 8.0169 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| 废弃物绿色处理 |  | 1 | 0.14065 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| 雨洪管理设施 |  | 9 | 1.2658 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| LEED认证增量措施 |  | 47 | 6.6104 | 100% | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.18 | 架空平台3 |  | 4178.7488 | 587.7284 | 100%
2.18.1 | 建筑工程 |  | 4053.3863 | 570.0965 | 100%
2.18.2 | 安装工程 |  | 125.3625 | 17.6319 | 100%
HGAC-CW04 | 保税物流仓库 (三) | 保税物流仓库H01 / H02 / E05,、架空平台2，建筑面积总计121,805 m2 | 54208.0131 | 7624.1931 | 100% | 土建 | IOCT | 18 | 前审 | 是 |  |  | 2027.3 | 2027.4 | 2027.6 | 2028.12
2.1 | H01 物流仓库 |  | 15502.4051 | 2180.3664 | 100%
2.10.1 | 土建工程 |  | 12124.8594 | 1705.3248 | 100%
2.10.2 | 给排水工程 |  | 40.9267 | 5.7562 | 100%
2.10.3 | 电气工程 |  | 368.3405 | 51.806 | 100%
2.10.4 | 暖通工程 |  | 286.487 | 40.2935 | 100%
2.10.5 | 消防工程 |  | 634.3642 | 89.2214 | 100%
2.10.6 | 设备工程 |  | 174.8079 | 24.5862 | 100%
2.10.7 | 场平工程 |  | 639.48 | 89.9409 | 100%
| 室外工程 |  | 1161.1395 | 163.3108 | 100%
2.10.8 | 绿建工程 |  | 72 | 10.1266 | 100%
| 废弃物绿色处理 |  | 1 | 0.14065 | 100%
| 雨洪管理设施 |  | 13 | 1.8284 | 100%
| LEED认证增量措施 |  | 58 | 8.1575 | 100%
2.11 | H02 物流仓库 |  | 15296.8552 | 2151.4564 | 100%
2.11.1 | 土建工程 |  | 12124.8594 | 1705.3248 | 100%
2.11.2 | 给排水工程 |  | 40.9267 | 5.7562 | 100%
2.11.3 | 电气工程 |  | 368.3405 | 51.806 | 100%
2.11.4 | 暖通工程 |  | 286.487 | 40.2935 | 100%
2.11.5 | 消防工程 |  | 634.3642 | 89.2214 | 100%
2.11.6 | 设备工程 |  | 174.8079 | 24.5862 | 100%
2.11.7 | 场平工程 |  | 639.48 | 89.9409 | 100%
| 室外工程 |  | 955.5896 | 134.4008 | 100%
2.11.8 | 绿建工程 |  | 72 | 10.1266 | 100%
| 废弃物绿色处理 |  | 1 | 0.14065 | 100%
| 雨洪管理设施 |  | 13 | 1.8284 | 100%
| LEED认证增量措施 |  | 58 | 8.1575 | 100%
2.9 | E05 物流仓库 |  | 13789.8727 | 1939.5039 | 100%
2.9.1 | 土建工程 |  | 10541.2786 | 1482.599 | 100%
2.9.2 | 给排水工程 |  | 35.5814 | 5.0044 | 100%
2.9.3 | 电气工程 |  | 320.233 | 45.0398 | 100%
2.9.4 | 暖通工程 |  | 249.0701 | 35.031 | 100%
2.9.5 | 消防工程 |  | 551.5123 | 77.5685 | 100%
2.9.6 | 设备工程 |  | 151.9769 | 21.3751 | 100%
2.9.7 | 场平工程 |  | 555.96 | 78.1941 | 100%
| 室外工程 |  | 1319.2604 | 185.55 | 100%
2.9.8 | 绿建工程 |  | 65 | 9.1421 | 100%
| 废弃物绿色处理 |  | 1 | 0.14065 | 100%
| 雨洪管理设施 |  | 11 | 1.5471 | 100%
| LEED认证增量措施 |  | 53 | 7.4543 | 100%
2.17 | 架空平台2 |  | 9618.88 | 1352.8664 | 100%
2.17.1 | 建筑工程 |  | 9330.3136 | 1312.2804 | 100%
2.17.2 | 安装工程 |  | 288.5664 | 40.586 | 100%
HGAC-CW05 | 保税物流仓库 (四) | 保税物流仓库H03 / H04 / L01，建筑面积总计100,098 m2 | 47558.926 | 6689.0191 | 100% | 土建 | IOCT | 18 | 前审 | 是 |  |  | 2027.3 | 2027.4 | 2027.6 | 2028.12
2.12 | H03 物流仓库 |  | 15098.9985 | 2123.6285 | 100% |  |  |  | 前审
2.12.1 | 土建工程 |  | 12124.8594 | 1705.3248 | 100% |  |  |  | 前审
2.12.2 | 给排水工程 |  | 40.9267 | 5.7562 | 100% |  |  |  | 前审
2.12.3 | 电气工程 |  | 368.3405 | 51.806 | 100% |  |  |  | 前审
2.12.4 | 暖通工程 |  | 286.487 | 40.2935 | 100% |  |  |  | 前审
2.12.5 | 消防工程 |  | 634.3642 | 89.2214 | 100% |  |  |  | 前审
2.12.6 | 设备工程 |  | 174.8079 | 24.5862 | 100% |  |  |  | 前审
2.12.7 | 场平工程 |  | 639.48 | 89.9409 | 100% |  |  |  | 前审
| 室外工程 |  | 757.7328 | 106.5728 | 100% |  |  |  | 前审
2.12.8 | 绿建工程 |  | 72 | 10.1266 | 100% |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 100% |  |  |  | 前审
| 雨洪管理设施 |  | 13 | 1.8284 | 100% |  |  |  | 前审
| LEED认证增量措施 |  | 58 | 8.1575 | 100% |  |  |  | 前审
2.13 | H04 物流仓库 |  | 15276.6249 | 2148.6111 | 100% |  |  |  | 前审
2.13.1 | 土建工程 |  | 12124.8594 | 1705.3248 | 100% |  |  |  | 前审
2.13.2 | 给排水工程 |  | 40.9267 | 5.7562 | 100% |  |  |  | 前审
2.13.3 | 电气工程 |  | 368.3405 | 51.806 | 100% |  |  |  | 前审
2.13.4 | 暖通工程 |  | 286.487 | 40.2935 | 100% |  |  |  | 前审
2.13.5 | 消防工程 |  | 634.3642 | 89.2214 | 100% |  |  |  | 前审
2.13.6 | 设备工程 |  | 174.8079 | 24.5862 | 100% |  |  |  | 前审
2.13.7 | 场平工程 |  | 639.48 | 89.9409 | 100% |  |  |  | 前审
| 室外工程 |  | 935.3592 | 131.5554 | 100% |  |  |  | 前审
2.13.8 | 绿建工程 |  | 72 | 10.1266 | 100% |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 100% |  |  |  | 前审
| 雨洪管理设施 |  | 13 | 1.8284 | 100% |  |  |  | 前审
| LEED认证增量措施 |  | 58 | 8.1575 | 100% |  |  |  | 前审
2.14 | L01 物流仓库 |  | 17183.3027 | 2416.7796 | 100% |  |  |  | 前审
2.14.1 | 土建工程 |  | 13708.4402 | 1928.0507 | 100% |  |  |  | 前审
2.14.2 | 给排水工程 |  | 46.272 | 6.508 | 100% |  |  |  | 前审
2.14.3 | 电气工程 |  | 416.448 | 58.5722 | 100% |  |  |  | 前审
2.14.4 | 暖通工程 |  | 323.904 | 45.5561 | 100% |  |  |  | 前审
2.14.5 | 消防工程 |  | 717.216 | 100.8743 | 100% |  |  |  | 前审
2.14.6 | 设备工程 |  | 197.6389 | 27.7973 | 100% |  |  |  | 前审
2.14.7 | 场平工程 |  | 723 | 101.6878 | 100% |  |  |  | 前审
| 室外工程 |  | 972.3836 | 136.7628 | 100% |  |  |  | 前审
2.14.8 | 绿建工程 |  | 78 | 10.9705 | 100% |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 100% |  |  |  | 前审
| 雨洪管理设施 |  | 14 | 1.9691 | 100% |  |  |  | 前审
| LEED认证增量措施 |  | 63 | 8.8608 | 100% |  |  |  | 前审
HGAC-CW06 | 保税加工仓库 | 保税加工仓库E01 / E02 / E03 / E04，建筑面积总计57,184 m2 | 23398.367 | 3290.9096 | 100% | 土建 | NCT | 18 | 前审 | 是 |  |  | 2026.3 | 2026.4 | 2026.6 | 2027.12
2.4 | E01 物流仓库 |  | 5921.3919 | 832.8259 | 100% |  |  |  | 前审
2.4.1 | 土建工程 |  | 3574 | 502.6723 | 100% |  |  |  | 前审
2.4.2 | 给排水工程 |  | 18.2989 | 2.5737 | 100% |  |  |  | 前审
2.4.3 | 电气工程 |  | 164.6899 | 23.1631 | 100% |  |  |  | 前审
2.4.4 | 暖通工程 |  | 128.0922 | 18.0158 | 100% |  |  |  | 前审
2.4.5 | 消防工程 |  | 283.6326 | 39.8921 | 100% |  |  |  | 前审
2.4.6 | 设备工程 |  | 78.1589 | 10.9928 | 100% |  |  |  | 前审
2.4.7 | 场平工程 |  | 571.84 | 80.4276 | 100% |  |  |  | 前审
| 室外工程 |  | 1036.6793 | 145.8058 | 100% |  |  |  | 前审
2.4.8 | 绿建工程 |  | 66 | 9.2827 | 100% |  |  |  | 前审
| 废弃物绿色处理 |  | 2 | 0.28129 | 100% |  |  |  | 前审
| 雨洪管理设施 |  | 11 | 1.5471 | 100% |  |  |  | 前审
| LEED认证增量措施 |  | 53 | 7.4543 | 100% |  |  |  | 前审
2.5 | E02 物流仓库 |  | 5952.1709 | 837.1548 | 100% |  |  |  | 前审
2.5.1 | 土建工程 |  | 3574 | 502.6723 | 100% |  |  |  | 前审
2.5.2 | 给排水工程 |  | 18.2989 | 2.5737 | 100% |  |  |  | 前审
2.5.3 | 电气工程 |  | 164.6899 | 23.1631 | 100% |  |  |  | 前审
2.5.4 | 暖通工程 |  | 128.0922 | 18.0158 | 100% |  |  |  | 前审
2.5.5 | 消防工程 |  | 283.6326 | 39.8921 | 100% |  |  |  | 前审
2.5.6 | 设备工程 |  | 78.1589 | 10.9928 | 100% |  |  |  | 前审
2.5.7 | 场平工程 |  | 571.84 | 80.4276 | 100% |  |  |  | 前审
| 室外工程 |  | 1068.4583 | 150.2754 | 100% |  |  |  | 前审
2.5.8 | 绿建工程 |  | 65 | 9.1421 | 100% |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 100% |  |  |  | 前审
| 雨洪管理设施 |  | 11 | 1.5471 | 100% |  |  |  | 前审
| LEED认证增量措施 |  | 53 | 7.4543 | 100% |  |  |  | 前审
2.6 | E03 物流仓库 |  | 5747.9617 | 808.4334 | 100% |  |  |  | 前审
2.6.1 | 土建工程 |  | 3574 | 502.6723 | 100% |  |  |  | 前审
2.6.2 | 给排水工程 |  | 18.2989 | 2.5737 | 100% |  |  |  | 前审
2.6.3 | 电气工程 |  | 164.6899 | 23.1631 | 100% |  |  |  | 前审
2.6.4 | 暖通工程 |  | 128.0922 | 18.0158 | 100% |  |  |  | 前审
2.6.5 | 消防工程 |  | 283.6326 | 39.8921 | 100% |  |  |  | 前审
2.6.6 | 设备工程 |  | 78.1589 | 10.9928 | 100% |  |  |  | 前审
2.6.7 | 场平工程 |  | 571.84 | 80.4276 | 100% |  |  |  | 前审
| 室外工程 |  | 864.2492 | 121.554 | 100% |  |  |  | 前审
2.6.8 | 绿建工程 |  | 65 | 9.1421 | 100% |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 100% |  |  |  | 前审
| 雨洪管理设施 |  | 11 | 1.5471 | 100% |  |  |  | 前审
| LEED认证增量措施 |  | 53 | 7.4543 | 100% |  |  |  | 前审
2.7 | E04 物流仓库 |  | 5776.8425 | 812.4954 | 100% |  |  |  | 前审
2.7.1 | 土建工程 |  | 3574 | 502.6723 | 100% |  |  |  | 前审
2.7.2 | 给排水工程 |  | 18.2989 | 2.5737 | 100% |  |  |  | 前审
2.7.3 | 电气工程 |  | 164.6899 | 23.1631 | 100% |  |  |  | 前审
2.7.4 | 暖通工程 |  | 128.0922 | 18.0158 | 100% |  |  |  | 前审
2.7.5 | 消防工程 |  | 283.6326 | 39.8921 | 100% |  |  |  | 前审
2.7.6 | 设备工程 |  | 78.1589 | 10.9928 | 100% |  |  |  | 前审
2.7.7 | 场平工程 |  | 571.84 | 80.4276 | 100% |  |  |  | 前审
| 室外工程 |  | 893.13 | 125.616 | 100% |  |  |  | 前审
2.7.8 | 绿建工程 |  | 65 | 9.1421 | 100% |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 100% |  |  |  | 前审
| 雨洪管理设施 |  | 11 | 1.5471 | 100% |  |  |  | 前审
| LEED认证增量措施 |  | 53 | 7.4543 | 100% |  |  |  | 前审
HGAC-CW07 | 附属工程 | 集卡坡道3、集卡坡道4、集卡坡道5、门卫室、设备用房 | 3292.1052 | 463.0246 | 100% | 土建 | NCT | 12 | 后审 |  |  |  | 2025.3 | 2025.4 | 2025.6 | 2026.5
小计 |  |  | 174384.8256 | 967.1946 | 100%
组成部分2: | 贸易和货运服务设施
HGAC-CW08 | 贸易和货运服务设施 | (1) 免税服务中心S01，建筑面积10,450 m2; (2) 综合办公楼W01，建筑面积39,432 m2 | 28051.0846 | 3945.3002 | 100% | 土建 | NCT | 18 | 前审 | 是 |  |  | 2025.3 | 2025.4 | 2025.6 | 2026.12
3.2 | S01 免税服务中心 |  | 8098.2373 | 1138.9926 | 100%
3.2.1 | 土建工程 |  | 4284.5 | 602.602 | 602.602
3.2.2 | 给排水工程 |  | 26.125 | 3.6744 | 3.6744
3.2.3 | 电气工程 |  | 151.525 | 21.3115 | 21.3115
3.2.4 | 暖通工程 |  | 120.175 | 16.9023 | 16.9023
3.2.5 | 消防工程 |  | 146.3 | 20.5767 | 20.5767
3.2.6 | 设备工程 |  | 41.8 | 5.879 | 5.879
3.2.7 | 场平工程 |  | 209 | 29.3952 | 29.3952
| 室外工程 |  | 2754.8123 | 387.456 | 387.456
3.2.8 | 绿建工程 |  | 364 | 51.1955 | 51.1955
| 其他可再生能源措施 |  | 289 | 40.647 | 40.647
| 废弃物绿色处理 |  | 4 | 0.56259 | 0.56259
| 雨洪管理设施 |  | 4 | 0.56259 | 0.56259
| LEED认证增量措施 |  | 32 | 4.5007 | 4.5007
| 绿建三星增量措施 |  | 35 | 4.9226 | 4.9226
3.1 | W01 综合办公楼 |  | 19952.8472 | 2806.3076 | 2806.3076
3.1.1 | 土建工程 |  | 14787.06 | 2079.7553 | 2079.7553
3.1.2 | 给排水工程 |  | 98.5804 | 13.865 | 13.865
3.1.3 | 电气工程 |  | 571.7663 | 80.4172 | 80.4172
3.1.4 | 暖通工程 |  | 453.4698 | 63.7792 | 63.7792
3.1.5 | 消防工程 |  | 552.0502 | 77.6442 | 77.6442
3.1.6 | 设备工程 |  | 157.7286 | 22.1841 | 22.1841
3.1.7 | 场平工程 |  | 788.6432 | 110.9203 | 110.9203
| 室外工程 |  | 2458.5486 | 345.7874 | 345.7874
3.1.8 | 绿建工程 |  | 85 | 11.955 | 11.955
| 废弃物绿色处理 |  | 4 | 0.56259 | 0.56259
| 雨洪管理设施 |  | 15 | 2.1097 | 2.1097
| LEED认证增量措施 |  | 66 | 9.2827 | 9.2827
小计 |  |  | 28051.0846 | 3945.3002 | 100%
组成部分3: | 低碳、智慧和配套设施
HGAC-CW09 | 园区市政道路施工总承包 | (1) 高架联络道#1 (路基面积2,667 m2)、高架联络道#2 (路基面积2,375 m2); (2) 4条北区道路(规划二路581.6 m、规划三路990 m、规划四路1,075 m、规划五路354 m), 以及相关基础设施 | 20312.85 | 2856.9409 | 100% | 土建 | NCT | 12 | 前审 | 是 |  |  | 2025.1 | 2025.3 | 2025.3 | 2026.3
6 | 配套设施 |  | 2688.05 | 378.0661 | 37807% |  |  |  | 前审
6.1 | 1#高架联络道 |  | 399.45 | 56.1814 | 5618% |  |  |  | 前审
6.1.1 | 路基 |  | 2145.6 | 301.7722 | 30177% |  |  |  | 前审
6.1.2 | 钢箱梁 |  | 143 | 20.1125 | 2011% |  |  |  | 前审
6.1.3 | 装饰棚 |  | 6521.05 | 917.166 | 91717% |  |  |  | 前审
6.2 | 2#高架联络道 |  | 6521.05 | 917.166 | 91717% |  |  |  | 前审
6.2.1 | 路基 |  | 356.25 | 50.1055 | 5011% |  |  |  | 前审
6.2.3 | 钢箱梁 |  | 5956.8 | 837.8059 | 83781% |  |  |  | 前审
6.2.4 | 装饰棚 |  | 208 | 29.2546 | 2925% |  |  |  | 前审
6.3 | 规划二路 |  | 1959.93 | 275.6582 | 27566% |  |  |  | 前审
6.3.1 | 路基 |  | 1959.93 | 275.6582 | 27566% |  |  |  | 前审
6.4 | 规划三路 |  | 3742.2 | 526.3291 | 52633% |  |  |  | 前审
6.4.1 | 路基 |  | 3742.2 | 526.3291 | 52633% |  |  |  | 前审
6.5 | 规划四路 |  | 4063.5 | 571.519 | 57152% |  |  |  | 前审
6.5.1 | 路基 |  | 4063.5 | 571.519 | 57152% |  |  |  | 前审
6.6 | 规划五路 |  | 1338.12 | 188.2025 | 18820% |  |  |  | 前审
6.6.1 | 路基 |  | 1338.12 | 188.2025 | 18820% |  |  |  | 前审
HGAC-CW10 | 土方工程 | 二期北区土方工程 | 20000 | 2812.9395 | 100% | 土建 | NCT | 12 | 前审 |  |  |  | 2025.1 | 2025.2 | 2025.3 | 2026.2 | 土建类别第一个
HGAC-GD01 | 屋顶光伏(一) | (1) 一期(先行启动区)海关查验中心、国际快件中心#1 /#2、保税物流中心(B类)#1 / #2 / #3、国际货站顶部光伏设备采购与安装，共计76,134 m2；(2)自建南区建筑(·P01 / R01 / R02保税物流仓库、Q01 / Q02保税加工仓库)顶部光伏设备采购与安装，共计87,936 m2。总计(1) + (2) = 164,070 m2 | 5413.5455 | 761.3988 | 100% | 货物 | NCT | 12 | 前审 | 是 |  |  | 2025.1 | 2025.3 | 2025.3 | 2026.3 | 货物类别第一个
4.1.22 | 海关查验中心 | 11022 | 363.6765 | 51.15 | 36368%
4.1.23 | 保税仓库1 | 11707 | 386.1825 | 54.3154 | 38618%
4.1.24 | 保税仓库2 | 11707 | 386.1825 | 54.3154 | 38618%
4.1.25 | 保税仓库3 | 11707 | 386.1825 | 54.3154 | 38618%
4.1.26 | 国际快件中心 | 18327 | 604.7635 | 85.0582 | 60476%
4.1.27 | 快件中心 | 11664 | 384.8185 | 54.1236 | 38482%
4.1.16 | P001 | 16128 | 532.1305 | 74.8425 | 53213%
4.1.17 | Q001 | 18768 | 619.256 | 87.0965 | 61926%
4.1.18 | Q002 | 18768 | 619.256 | 87.0965 | 61926%
4.1.19 | R001 | 17136 | 565.5485 | 79.5427 | 56555%
4.1.20 | R002 | 17136 | 565.5485 | 79.5427 | 56555%
HGAC-GD02 | 屋顶光伏(二) | 亚投行资金建设北区所有建筑，包括免税服务中心S01、综合业务楼W01，海关查验仓库T01、保税物流仓库E01~E04 / H01~H04 / J01 / K01 / L01 / M01，总计196,714 m2 | 6823.41 | 959.692 | 100% | 货物 | NCT | 42 | 前审 |  |  |  | 2025.6 | 2025.7 | 2025.9 | 2028.12
4.1 | 光伏 | 370864.11m2 | 12236.96 | 1721.0914 | 172109%
| 亚投行资金建设北区 | 196714.11 | 6823.4145 | 959.6926 | 95969%
4.1.1 | 免税服务中心S01 | 5226.66 | 172.3755 | 24.2441 | 2424%
4.1.2 | 综合业务楼W01 | 4929.02 | 162.657 | 22.8772 | 2288%
4.1.3 | E001 | 13104 | 432.388 | 60.8141 | 6081%
4.1.4 | E002 | 13104 | 432.388 | 60.8141 | 6081%
4.1.5 | E003 | 13104 | 432.388 | 60.8141 | 6081%
4.1.6 | E004 | 13104 | 432.388 | 60.8141 | 6081%
4.1.7 | E005 | 13104 | 432.388 | 60.8141 | 6081%
4.1.8 | H001 | 15120 | 498.883 | 70.1664 | 7017%
4.1.9 | H002 | 15120 | 498.883 | 70.1664 | 7017%
4.1.10 | H003 | 15120 | 498.883 | 70.1664 | 7017%
4.1.11 | H004 | 15120 | 498.883 | 70.1664 | 7017%
4.1.12 | J001 | 10800 | 356.345 | 50.1188 | 5012%
4.1.13 | K001 | 9360 | 308.7755 | 43.4283 | 4343%
4.1.14 | L001 | 17136 | 565.5485 | 79.5427 | 7954%
4.1.15 | M001 | 23262.43 | 767.591 | 107.9594 | 10796%
4.1.21 | T001(海关查验仓库) | 10080 | 332.65 | 46.7862 | 4679%
| 自建南区 | 87936 | 2901.75 | 408.1224 | 40812%
4.1.16 | P001(自建南区) | 16128 | 532.13 | 74.8425 | 7484%
4.1.17 | Q001(自建南区) | 18768 | 619.26 | 87.097 | 8710%
4.1.18 | Q002(自建南区) | 18768 | 619.26 | 87.097 | 8710%
4.1.19 | R001(自建南区) | 17136 | 565.55 | 79.5429 | 7954%
4.1.20 | R002(自建南区) | 17136 | 565.55 | 79.5429 | 7954%
| 先行启动区 | 86214 | 2844.45 | 961.4906 | 96149%
4.1.22 | 海关查验中心(先行启动区) | 11022 | 363.68 | 51.1505 | 5115%
4.1.23 | 保税仓库1 | 11707 | 386.18 | 54.315 | 5432%
4.1.24 | 保税仓库2 | 11707 | 386.18 | 54.315 | 5432%
4.1.25 | 保税仓库3 | 11707 | 386.18 | 54.315 | 5432%
4.1.26 | 国际快件中心 | 18327 | 604.76 | 85.0577 | 8506%
4.1.27 | 国际快件中心 | 11664 | 384.82 | 54.1238 | 5412%
HGAC-GD03 | 新能源利用 | 商贸物流中心(一期先行启动区)空气源热泵空调系统工程 | 3364 | 473.1364 | 100% | 货物 | NCT | 48 | 前审 |  |  |  | 2025.1 | 2025.3 | 2025.3 | 2028.7
HGAC-GD04 | 智慧运营系统 | 园区智慧运营系统设备与软件，含综保税区IOC平台、园区能源能耗管理、碳管理、ESG可视、资产管理、交通出入园管理、智慧安防、智慧消防、园区企业管理等 | 4000 | 562.5879 | 100% | 货物 | NCT | 48 | 前审 |  |  |  | 2025.1 | 2025.3 | 2025.3 | 2028.7
| 4.2 | 智慧运营平台 | 4000
HGAC-GD05 | 综合信息化平台 | 智慧海关辅助监管平台、应用支撑平台、企业通关服务平台、多式联运平台、园区车辆行人管控设备、园区视频设备、园区办公信息化设备、园区安全 / 能效 /消防设备、数字化月台、数字化仓库、一站式安检区、检疫处理区等 | 18818.98 | 2646.8326 | 100% | 货物 | IOCT | 42 | 前审 | 是 |  |  | 2025.6 | 2025.7 | 2025.9 | 2028.12
4.3 | 综合信息化平台 |  | 18818.98 | 2646.8326 | 264683%
4.3.1 | 智慧海关辅助监管平台 |  | 3355 | 471.8706 | 47187%
4.3.2 | 应用支撑平台 |  | 920 | 129.3952 | 12940%
4.3.3 | 企业通关服务平台 |  | 3160 | 444.4444 | 44444%
4.3.4 | 多式联运平台 |  | 2100 | 295.3586 | 29536%
4.3.5 | 园区车辆行人管控设备 |  | 341.9 | 48.0872 | 4809%
4.3.6 | 园区视频设备 |  | 656.15 | 92.2855 | 9229%
4.3.7 | 园区办公信息化设备 |  | 355.67 | 50.0239 | 5002%
4.3.8 | 园区安全、能效、消防设备 |  | 211.46 | 29.7412 | 2974%
4.3.9 | 数字化月台 |  | 33.6 | 4.7257 | 472.6%
4.3.10 | 数字化仓库 |  | 333.3 | 46.8776 | 4688%
4.3.11 | 一站式安检区 |  | 7000 | 984.5288 | 98453%
4.3.12 | 检疫处理区 |  | 351.9 | 49.4937 | 4949%
小计 |  |  | 78732.7855 | 11073.5282 | 100%
组成部分4: | 能力建设
HGAC-CS01 | 项目管理 | 项目管理技术支持、培训、考察、知识产品开发推广等 | 1000 | 140.647 | 100% | 咨询服务 | IOCS/QCBS | 48 | 前审 |  |  |  | 2025.1 | 2025.3 | 2025.4 | 2028.12
HGAC-CS02 | 项目监测评价 | 外部环境监测、外部移民监测、外部社会和性别监测、项目绩效评估等 | 1000 | 140.647 | 100% | 咨询服务 | IOCS/QCBS | 48 | 前审 |  |  |  | 2025.1 | 2025.3 | 2025.4 | 2028.12
HGAC-CS03 | 国际或国内绿建认证 | 园区建筑国际或国内绿建认证咨询服务 | 761 | 107.0323 | 100% | 咨询服务 | IOCS/QCBS | 42 | 前审 |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
HGAC-CS04 | 绿建三星认证咨询 | 园区建筑绿色建筑认证咨询服务 | 116 | 16.315 | 100% | 咨询服务 | NCS/CQS | 42 | 后审 |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
HGAC-CS05 | 海关监管模式创新课题研究 | 海关监管模式创新课题研究 | 350 | 49.2264 | 100% | 咨询服务 | NCS/CQS | 24 | 后审 |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
HGAC-CS06 | 多检合一创新课题研究 | 多检合一创新课题研究 | 350 | 49.2264 | 100% | 咨询服务 | NCS/CQS | 24 | 后审 |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
HGAC-CS07 | 多式联运创新课题研究 | 多式联运创新课题研究 | 300 | 42.1941 | 100% | 咨询服务 | NCS/CQS | 24 | 后审 |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
小计 |  |  | 3877 | 545.2883 | 100%
总计 |  |  | 285045.6957 | 40090.8152 | 100%
|  | CW土建 | 242748.7602 | 34141.8791
|  | Goods货物 | 38419.9355 | 5403.6477
|  | Consulting Services咨询服务 | 3877 | 545.2883
|  |  | 285045.6957 | 40090.8152

## PP_1225-ENG (hidden)
Attachment 1-China: Hubei Global Air Cargo Logistics Hub Project----Procurement Plan (Updated December 2024)
$1 = CNY | AIIB Loan Appraisal Mission MoM
7.11 | 2024-04-12
Contract No. | Contract Name | Description | Cost Estimate |  | % of AIIB Financing |  | Procurement Category | Procurement Method | Contract Duration (Months) | Bank Review (Prior / Post) | Date of SPN | Bid Openning | Contract Signing | Contract Closing | Notes
|  |  | CNY million | $ million
Component 1: | Customs Operation and Bonded Facilities
HGAC-CW01 | Customs Operation Facilities | (1) Customs Inspection Center T01 (10,911 m2) ; (2) Customs Kiosk & Fence: #2 Customs Kiosk (949 m2), Fence (7,730 m) | 6876.7533 | 967.1946 | 100% | 6876.7533 | Works | NCT | 18 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
1.1 | Bonded Logistics Warehouse (1) | T01 海关查验仓库 | 5931.3338 |  | 0 | 5931.3338 | Works |  |  | Post
1.1.1 | Bonded Logistics Warehouse (2) | 土建工程 | 4137.5599 |  | 0 | 4137.5599 | Works |  |  | Post
1.1.2 | Bonded Logistics Warehouse (3) | 给排水工程 | 13.9661 |  | 0 | 13.9661 | Works |  |  | Post
1.1.3 | Bonded Logistics Warehouse (4) | 电气工程 | 125.6947 |  | 0 | 125.6947 | Works |  |  | Post
1.1.4 | Bonded and Processing Warehouses | 暖通工程 | 97.7626 |  | 0 | 97.7626 | Works |  |  | Post
1.1.5 | Auxiliary Facilities | 消防工程 | 216.4742 |  | 0 | 216.4742 | Works |  |  | Post
1.1.6 |  | 设备工程 | 59.6525 |  | 0 | 59.6525 | Works |  |  | Post
1.1.7 |  | 场平工程 | 218.22 |  | 0 | 218.22 | Works |  |  | Post
1.1.8 |  | 室外工程 | 1024.0038 |  | 0 | 1024.0038 | Works |  |  | Post
1.1.8 |  | 绿建工程 | 38 |  | 0 | 38 | Works |  |  | Post
|  | 废弃物绿色处理 | 1 |  | 0 | 1 | Works |  |  | Post
|  | 雨洪管理设施 | 4 |  | 0 | 4 | Works |  |  | Post
|  | LEED认证增量措施 | 33 |  | 0 | 33 | Works |  |  | Post
1.2 |  | 2#海关卡口 | 481.6195 |  | 0 | 481.6195 | Works |  |  | Post
1.2.1 |  | 地基处理 | 3.3215 |  | 0 | 3.3215 | Works |  |  | Post
1.2.2 |  | 土建工程 | 455.52 |  | 0 | 455.52 | Works |  |  | Post
1.2.3 |  | 给排水工程 | 2.847 |  | 0 | 2.847 | Works |  |  | Post
1.2.4 |  | 暖通工程 | 3.796 |  | 0 | 3.796 | Works |  |  | Post
1.2.5 |  | 电气工程 | 8.541 |  | 0 | 8.541 | Works |  |  | Post
1.2.6 |  | 抗震支架 | 5.694 |  | 0 | 5.694 | Works |  |  | Post
1.2.7 |  | 标识标牌 | 1.9 |  | 0 | 1.9 | Works |  |  | Post
1.4 |  | 海关围网 | 463.8 |  | 0 | 463.8 | Works |  |  | Post
HGAC-CW02 | Bonded Logistics Warehouses (1) | Bonded Logistics Warehoue M01 (20,396 m2) | 13277.6977 | 1867.468 | 100% | 13277.6977 | Works | NCT | 18 | Prior | 2025.3 | 2025.4 | 2025.6 | 2026.12
2.8 | Bonded Logistics Warehouse (2) |  | 13277.6977 | 1867.468 | 100% | 13277.6977 | Works |  |  | Post
2.8.1 | Bonded Logistics Warehouse (3) |  | 9630.4162 | 1354.4889 | 100% | 9630.4162 | Works |  |  | Post
2.8.2 | Bonded Logistics Warehouse (4) |  | 32.5069 | 4.572 | 100% | 32.5069 | Works |  |  | Post
2.8.3 | Bonded Logistics Warehouse (5) |  | 292.5619 | 41.1479 | 100% | 292.5619 | Works |  |  | Post
2.8.4 | Bonded Logistics Warehouse (6) |  | 227.5482 | 32.004 | 100% | 227.5482 | Works |  |  | Post
2.8.5 | Bonded Logistics Warehouse (7) |  | 503.8566 | 70.8659 | 100% | 503.8566 | Works |  |  | Post
2.8.6 | Bonded Logistics Warehouse (8) |  | 138.8447 | 19.5281 | 100% | 138.8447 | Works |  |  | Post
2.8.7 | Bonded Logistics Warehouse (9) |  | 507.92 | 71.4374 | 100% | 507.92 | Works |  |  | Post
| Bonded Logistics Warehouse (10) |  | 1881.0431 | 264.563 | 100% | 1881.0431 | Works |  |  | Post
2.8.8 | Bonded Logistics Warehouse (11) |  | 63 | 8.8608 | 100% | 63 | Works |  |  | Post
| Bonded Logistics Warehouse (12) |  | 1 | 0.14065 | 100% | 1 | Works |  |  | Post
| Bonded Logistics Warehouse (13) |  | 11 | 1.5471 | 100% | 11 | Works |  |  | Post
| Bonded Logistics Warehouse (14) |  | 51 | 7.173 | 100% | 51 | Works |  |  | Post
HGAC-CW03 | Bonded Logistics Warehouses (2) | Bonded Logistics Warehouse J01 / K010, Elevated Platform #3 (42,780 m2) | 25772.9634 | 3624.8894 | 100% | 25772.9634 | Works | NCT | 18 | Prior | 2025.3 | 2025.4 | 2025.6 | 2026.12
2.15 | Bonded Logistics Warehouse (16) |  | 11277.3601 | 1586.1266 | 100% | 11277.3601 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.1 | Bonded Logistics Warehouse (17) |  | 8671.015 | 1219.552 | 100% | 8671.015 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.2 | Bonded Logistics Warehouse (18) |  | 29.2685 | 4.1165 | 100% | 29.2685 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.3 | Bonded Logistics Warehouse (19) |  | 263.4163 | 37.0487 | 100% | 263.4163 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.4 | Bonded Logistics Warehouse (20) |  | 204.8794 | 28.8157 | 100% | 204.8794 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.5 | Bonded Logistics Warehouse (21) |  | 453.6614 | 63.8061 | 100% | 453.6614 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.6 | Bonded Logistics Warehouse (22) |  | 125.0127 | 17.5827 | 100% | 125.0127 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.7 | Bonded Logistics Warehouse (23) |  | 457.32 | 64.3207 | 100% | 457.32 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (24) |  | 1015.7868 | 142.8673 | 100% | 1015.7868 | Works |  |  | Post
2.15.8 | Bonded Logistics Warehouse (25) |  | 57 | 8.0169 | 100% | 57 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (26) |  | 1 | 0.14065 | 100% | 1 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (27) |  | 9 | 1.2658 | 100% | 9 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (28) |  | 47 | 6.6104 | 100% | 47 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16 | Bonded Logistics Warehouse (29) |  | 11277.3601 | 1586.1266 | 100% | 11277.3601 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.1 | Bonded Logistics Warehouse (30) |  | 8671.015 | 1219.552 | 100% | 8671.015 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.2 | Bonded Logistics Warehouse (31) |  | 29.2685 | 4.1165 | 100% | 29.2685 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.3 | Bonded Logistics Warehouse (32) |  | 263.4163 | 37.0487 | 100% | 263.4163 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.4 | Bonded Logistics Warehouse (33) |  | 204.8794 | 28.8157 | 100% | 204.8794 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.5 | Bonded Logistics Warehouse (34) |  | 453.6614 | 63.8061 | 100% | 453.6614 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.6 | Bonded Logistics Warehouse (35) |  | 125.0127 | 17.5827 | 100% | 125.0127 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.7 | Bonded Logistics Warehouse (36) |  | 457.32 | 64.3207 | 100% | 457.32 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (37) |  | 1015.7868 | 142.8673 | 100% | 1015.7868 | Works |  |  | Post
2.16.8 | Bonded Logistics Warehouse (38) |  | 57 | 8.0169 | 100% | 57 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (39) |  | 1 | 0.14065 | 100% | 1 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (40) |  | 9 | 1.2658 | 100% | 9 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (41) |  | 47 | 6.6104 | 100% | 47 | Works | NCT | 18个月 | Post | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.18 | Bonded Logistics Warehouse (42) |  | 4178.7488 | 587.7284 | 100% | 4178.7488 | Works |  |  | Post
2.18.1 | Bonded Logistics Warehouse (43) |  | 4053.3863 | 570.0965 | 100% | 4053.3863 | Works |  |  | Post
2.18.2 | Bonded Logistics Warehouse (44) |  | 125.3625 | 17.6319 | 100% | 125.3625 | Works |  |  | Post
HGAC-CW04 | Bonded Logistics Warehouses (3) | Bonded Logistics Warehouse H01 / H02 / E05 and Elevated Platform #2 (121,805 m2) | 54208.0131 | 7624.1931 | 100% | 54208.0131 | Works | IOCT | 18 | Prior | 2027.3 | 2027.4 | 2027.6 | 2028.12
2.1 | Bonded Logistics Warehouse (46) |  | 15502.4051 | 2180.3664 | 100% | 15502.4051 | Works |  |  | Post
2.10.1 | Bonded Logistics Warehouse (47) |  | 12124.8594 | 1705.3248 | 100% | 12124.8594 | Works |  |  | Post
2.10.2 | Bonded Logistics Warehouse (48) |  | 40.9267 | 5.7562 | 100% | 40.9267 | Works |  |  | Post
2.10.3 | Bonded Logistics Warehouse (49) |  | 368.3405 | 51.806 | 100% | 368.3405 | Works |  |  | Post
2.10.4 | Bonded Logistics Warehouse (50) |  | 286.487 | 40.2935 | 100% | 286.487 | Works |  |  | Post
2.10.5 | Bonded Logistics Warehouse (51) |  | 634.3642 | 89.2214 | 100% | 634.3642 | Works |  |  | Post
2.10.6 | Bonded Logistics Warehouse (52) |  | 174.8079 | 24.5862 | 100% | 174.8079 | Works |  |  | Post
2.10.7 | Bonded Logistics Warehouse (53) |  | 639.48 | 89.9409 | 100% | 639.48 | Works |  |  | Post
| Bonded Logistics Warehouse (54) |  | 1161.1395 | 163.3108 | 100% | 1161.1395 | Works |  |  | Post
2.10.8 | Bonded Logistics Warehouse (55) |  | 72 | 10.1266 | 100% | 72 | Works |  |  | Post
| Bonded Logistics Warehouse (56) |  | 1 | 0.14065 | 100% | 1 | Works |  |  | Post
| Bonded Logistics Warehouse (57) |  | 13 | 1.8284 | 100% | 13 | Works |  |  | Post
| Bonded Logistics Warehouse (58) |  | 58 | 8.1575 | 100% | 58 | Works |  |  | Post
2.11 | Bonded Logistics Warehouse (59) |  | 15296.8552 | 2151.4564 | 100% | 15296.8552 | Works |  |  | Post
2.11.1 | Bonded Logistics Warehouse (60) |  | 12124.8594 | 1705.3248 | 100% | 12124.8594 | Works |  |  | Post
2.11.2 | Bonded Logistics Warehouse (61) |  | 40.9267 | 5.7562 | 100% | 40.9267 | Works |  |  | Post
2.11.3 | Bonded Logistics Warehouse (62) |  | 368.3405 | 51.806 | 100% | 368.3405 | Works |  |  | Post
2.11.4 | Bonded Logistics Warehouse (63) |  | 286.487 | 40.2935 | 100% | 286.487 | Works |  |  | Post
2.11.5 | Bonded Logistics Warehouse (64) |  | 634.3642 | 89.2214 | 100% | 634.3642 | Works |  |  | Post
2.11.6 | Bonded Logistics Warehouse (65) |  | 174.8079 | 24.5862 | 100% | 174.8079 | Works |  |  | Post
2.11.7 | Bonded Logistics Warehouse (66) |  | 639.48 | 89.9409 | 100% | 639.48 | Works |  |  | Post
| Bonded Logistics Warehouse (67) |  | 955.5896 | 134.4008 | 100% | 955.5896 | Works |  |  | Post
2.11.8 | Bonded Logistics Warehouse (68) |  | 72 | 10.1266 | 100% | 72 | Works |  |  | Post
| Bonded Logistics Warehouse (69) |  | 1 | 0.14065 | 100% | 1 | Works |  |  | Post
| Bonded Logistics Warehouse (70) |  | 13 | 1.8284 | 100% | 13 | Works |  |  | Post
| Bonded Logistics Warehouse (71) |  | 58 | 8.1575 | 100% | 58 | Works |  |  | Post
2.9 | Bonded Logistics Warehouse (72) |  | 13789.8727 | 1939.5039 | 100% | 13789.8727 | Works |  |  | Post
2.9.1 | Bonded Logistics Warehouse (73) |  | 10541.2786 | 1482.599 | 100% | 10541.2786 | Works |  |  | Post
2.9.2 | Bonded Logistics Warehouse (74) |  | 35.5814 | 5.0044 | 100% | 35.5814 | Works |  |  | Post
2.9.3 | Bonded Logistics Warehouse (75) |  | 320.233 | 45.0398 | 100% | 320.233 | Works |  |  | Post
2.9.4 | Bonded Logistics Warehouse (76) |  | 249.0701 | 35.031 | 100% | 249.0701 | Works |  |  | Post
2.9.5 | Bonded Logistics Warehouse (77) |  | 551.5123 | 77.5685 | 100% | 551.5123 | Works |  |  | Post
2.9.6 | Bonded Logistics Warehouse (78) |  | 151.9769 | 21.3751 | 100% | 151.9769 | Works |  |  | Post
2.9.7 | Bonded Logistics Warehouse (79) |  | 555.96 | 78.1941 | 100% | 555.96 | Works |  |  | Post
| Bonded Logistics Warehouse (80) |  | 1319.2604 | 185.55 | 100% | 1319.2604 | Works |  |  | Post
2.9.8 | Bonded Logistics Warehouse (81) |  | 65 | 9.1421 | 100% | 65 | Works |  |  | Post
| Bonded Logistics Warehouse (82) |  | 1 | 0.14065 | 100% | 1 | Works |  |  | Post
| Bonded Logistics Warehouse (83) |  | 11 | 1.5471 | 100% | 11 | Works |  |  | Post
| Bonded Logistics Warehouse (84) |  | 53 | 7.4543 | 100% | 53 | Works |  |  | Post
2.17 | Bonded Logistics Warehouse (85) |  | 9618.88 | 1352.8664 | 100% | 9618.88 | Works |  |  | Post
2.17.1 | Bonded Logistics Warehouse (86) |  | 9330.3136 | 1312.2804 | 100% | 9330.3136 | Works |  |  | Post
2.17.2 | Bonded Logistics Warehouse (87) |  | 288.5664 | 40.586 | 100% | 288.5664 | Works |  |  | Post
HGAC-CW05 | Bonded Logistics Warehouses (4) | Bonded Logistics Warehouse H03 / H04 / L01 (100,098 m2) | 47558.926 | 6689.0191 | 100% | 47558.926 | Works | IOCT | 18 | Prior | 2027.3 | 2027.4 | 2027.6 | 2028.12
2.12 | H03 物流仓库 |  | 15098.9985 | 2123.6285 | 100% | 15098.9985 | Works |  |  | Post
2.12.1 | 土建工程 |  | 12124.8594 | 1705.3248 | 100% | 12124.8594 | Works |  |  | Post
2.12.2 | 给排水工程 |  | 40.9267 | 5.7562 | 100% | 40.9267 | Works |  |  | Post
2.12.3 | 电气工程 |  | 368.3405 | 51.806 | 100% | 368.3405 | Works |  |  | Post
2.12.4 | 暖通工程 |  | 286.487 | 40.2935 | 100% | 286.487 | Works |  |  | Post
2.12.5 | 消防工程 |  | 634.3642 | 89.2214 | 100% | 634.3642 | Works |  |  | Post
2.12.6 | 设备工程 |  | 174.8079 | 24.5862 | 100% | 174.8079 | Works |  |  | Post
2.12.7 | 场平工程 |  | 639.48 | 89.9409 | 100% | 639.48 | Works |  |  | Post
| 室外工程 |  | 757.7328 | 106.5728 | 100% | 757.7328 | Works |  |  | Post
2.12.8 | 绿建工程 |  | 72 | 10.1266 | 100% | 72 | Works |  |  | Post
| 废弃物绿色处理 |  | 1 | 0.14065 | 100% | 1 | Works |  |  | Post
| 雨洪管理设施 |  | 13 | 1.8284 | 100% | 13 | Works |  |  | Post
| LEED认证增量措施 |  | 58 | 8.1575 | 100% | 58 | Works |  |  | Post
2.13 | H04 物流仓库 |  | 15276.6249 | 2148.6111 | 100% | 15276.6249 | Works |  |  | Post
2.13.1 | 土建工程 |  | 12124.8594 | 1705.3248 | 100% | 12124.8594 | Works |  |  | Post
2.13.2 | 给排水工程 |  | 40.9267 | 5.7562 | 100% | 40.9267 | Works |  |  | Post
2.13.3 | 电气工程 |  | 368.3405 | 51.806 | 100% | 368.3405 | Works |  |  | Post
2.13.4 | 暖通工程 |  | 286.487 | 40.2935 | 100% | 286.487 | Works |  |  | Post
2.13.5 | 消防工程 |  | 634.3642 | 89.2214 | 100% | 634.3642 | Works |  |  | Post
2.13.6 | 设备工程 |  | 174.8079 | 24.5862 | 100% | 174.8079 | Works |  |  | Post
2.13.7 | 场平工程 |  | 639.48 | 89.9409 | 100% | 639.48 | Works |  |  | Post
| 室外工程 |  | 935.3592 | 131.5554 | 100% | 935.3592 | Works |  |  | Post
2.13.8 | 绿建工程 |  | 72 | 10.1266 | 100% | 72 | Works |  |  | Post
| 废弃物绿色处理 |  | 1 | 0.14065 | 100% | 1 | Works |  |  | Post
| 雨洪管理设施 |  | 13 | 1.8284 | 100% | 13 | Works |  |  | Post
| LEED认证增量措施 |  | 58 | 8.1575 | 100% | 58 | Works |  |  | Post
2.14 | L01 物流仓库 |  | 17183.3027 | 2416.7796 | 100% | 17183.3027 | Works |  |  | Post
2.14.1 | 土建工程 |  | 13708.4402 | 1928.0507 | 100% | 13708.4402 | Works |  |  | Post
2.14.2 | 给排水工程 |  | 46.272 | 6.508 | 100% | 46.272 | Works |  |  | Post
2.14.3 | 电气工程 |  | 416.448 | 58.5722 | 100% | 416.448 | Works |  |  | Post
2.14.4 | 暖通工程 |  | 323.904 | 45.5561 | 100% | 323.904 | Works |  |  | Post
2.14.5 | 消防工程 |  | 717.216 | 100.8743 | 100% | 717.216 | Works |  |  | Post
2.14.6 | 设备工程 |  | 197.6389 | 27.7973 | 100% | 197.6389 | Works |  |  | Post
2.14.7 | 场平工程 |  | 723 | 101.6878 | 100% | 723 | Works |  |  | Post
| 室外工程 |  | 972.3836 | 136.7628 | 100% | 972.3836 | Works |  |  | Post
2.14.8 | 绿建工程 |  | 78 | 10.9705 | 100% | 78 | Works |  |  | Post
| 废弃物绿色处理 |  | 1 | 0.14065 | 100% | 1 | Works |  |  | Post
| 雨洪管理设施 |  | 14 | 1.9691 | 100% | 14 | Works |  |  | Post
| LEED认证增量措施 |  | 63 | 8.8608 | 100% | 63 | Works |  |  | Post
HGAC-CW06 | Bonded Processing Warehouses | Bonded Processing Warehouse E01 / E02 / E03 / E04 (57,184 m2) | 23398.367 | 3290.9096 | 100% | 23398.367 | Works | NCT | 18 | Prior | 2026.3 | 2026.4 | 2026.6 | 2027.12
2.4 | E01 物流仓库 |  | 5921.3919 | 832.8259 | 100% | 5921.3919 | Works |  |  | Post
2.4.1 | 土建工程 |  | 3574 | 502.6723 | 100% | 3574 | Works |  |  | Post
2.4.2 | 给排水工程 |  | 18.2989 | 2.5737 | 100% | 18.2989 | Works |  |  | Post
2.4.3 | 电气工程 |  | 164.6899 | 23.1631 | 100% | 164.6899 | Works |  |  | Post
2.4.4 | 暖通工程 |  | 128.0922 | 18.0158 | 100% | 128.0922 | Works |  |  | Post
2.4.5 | 消防工程 |  | 283.6326 | 39.8921 | 100% | 283.6326 | Works |  |  | Post
2.4.6 | 设备工程 |  | 78.1589 | 10.9928 | 100% | 78.1589 | Works |  |  | Post
2.4.7 | 场平工程 |  | 571.84 | 80.4276 | 100% | 571.84 | Works |  |  | Post
| 室外工程 |  | 1036.6793 | 145.8058 | 100% | 1036.6793 | Works |  |  | Post
2.4.8 | 绿建工程 |  | 66 | 9.2827 | 100% | 66 | Works |  |  | Post
| 废弃物绿色处理 |  | 2 | 0.28129 | 100% | 2 | Works |  |  | Post
| 雨洪管理设施 |  | 11 | 1.5471 | 100% | 11 | Works |  |  | Post
| LEED认证增量措施 |  | 53 | 7.4543 | 100% | 53 | Works |  |  | Post
2.5 | E02 物流仓库 |  | 5952.1709 | 837.1548 | 100% | 5952.1709 | Works |  |  | Post
2.5.1 | 土建工程 |  | 3574 | 502.6723 | 100% | 3574 | Works |  |  | Post
2.5.2 | 给排水工程 |  | 18.2989 | 2.5737 | 100% | 18.2989 | Works |  |  | Post
2.5.3 | 电气工程 |  | 164.6899 | 23.1631 | 100% | 164.6899 | Works |  |  | Post
2.5.4 | 暖通工程 |  | 128.0922 | 18.0158 | 100% | 128.0922 | Works |  |  | Post
2.5.5 | 消防工程 |  | 283.6326 | 39.8921 | 100% | 283.6326 | Works |  |  | Post
2.5.6 | 设备工程 |  | 78.1589 | 10.9928 | 100% | 78.1589 | Works |  |  | Post
2.5.7 | 场平工程 |  | 571.84 | 80.4276 | 100% | 571.84 | Works |  |  | Post
| 室外工程 |  | 1068.4583 | 150.2754 | 100% | 1068.4583 | Works |  |  | Post
2.5.8 | 绿建工程 |  | 65 | 9.1421 | 100% | 65 | Works |  |  | Post
| 废弃物绿色处理 |  | 1 | 0.14065 | 100% | 1 | Works |  |  | Post
| 雨洪管理设施 |  | 11 | 1.5471 | 100% | 11 | Works |  |  | Post
| LEED认证增量措施 |  | 53 | 7.4543 | 100% | 53 | Works |  |  | Post
2.6 | E03 物流仓库 |  | 5747.9617 | 808.4334 | 100% | 5747.9617 | Works |  |  | Post
2.6.1 | 土建工程 |  | 3574 | 502.6723 | 100% | 3574 | Works |  |  | Post
2.6.2 | 给排水工程 |  | 18.2989 | 2.5737 | 100% | 18.2989 | Works |  |  | Post
2.6.3 | 电气工程 |  | 164.6899 | 23.1631 | 100% | 164.6899 | Works |  |  | Post
2.6.4 | 暖通工程 |  | 128.0922 | 18.0158 | 100% | 128.0922 | Works |  |  | Post
2.6.5 | 消防工程 |  | 283.6326 | 39.8921 | 100% | 283.6326 | Works |  |  | Post
2.6.6 | 设备工程 |  | 78.1589 | 10.9928 | 100% | 78.1589 | Works |  |  | Post
2.6.7 | 场平工程 |  | 571.84 | 80.4276 | 100% | 571.84 | Works |  |  | Post
| 室外工程 |  | 864.2492 | 121.554 | 100% | 864.2492 | Works |  |  | Post
2.6.8 | 绿建工程 |  | 65 | 9.1421 | 100% | 65 | Works |  |  | Post
| 废弃物绿色处理 |  | 1 | 0.14065 | 100% | 1 | Works |  |  | Post
| 雨洪管理设施 |  | 11 | 1.5471 | 100% | 11 | Works |  |  | Post
| LEED认证增量措施 |  | 53 | 7.4543 | 100% | 53 | Works |  |  | Post
2.7 | E04 物流仓库 |  | 5776.8425 | 812.4954 | 100% | 5776.8425 | Works |  |  | Post
2.7.1 | 土建工程 |  | 3574 | 502.6723 | 100% | 3574 | Works |  |  | Post
2.7.2 | 给排水工程 |  | 18.2989 | 2.5737 | 100% | 18.2989 | Works |  |  | Post
2.7.3 | 电气工程 |  | 164.6899 | 23.1631 | 100% | 164.6899 | Works |  |  | Post
2.7.4 | 暖通工程 |  | 128.0922 | 18.0158 | 100% | 128.0922 | Works |  |  | Post
2.7.5 | 消防工程 |  | 283.6326 | 39.8921 | 100% | 283.6326 | Works |  |  | Post
2.7.6 | 设备工程 |  | 78.1589 | 10.9928 | 100% | 78.1589 | Works |  |  | Post
2.7.7 | 场平工程 |  | 571.84 | 80.4276 | 100% | 571.84 | Works |  |  | Post
| 室外工程 |  | 893.13 | 125.616 | 100% | 893.13 | Works |  |  | Post
2.7.8 | 绿建工程 |  | 65 | 9.1421 | 100% | 65 | Works |  |  | Post
| 废弃物绿色处理 |  | 1 | 0.14065 | 100% | 1 | Works |  |  | Post
| 雨洪管理设施 |  | 11 | 1.5471 | 100% | 11 | Works |  |  | Post
| LEED认证增量措施 |  | 53 | 7.4543 | 100% | 53 | Works |  |  | Post
HGAC-CW07 | Auxiliary Facilities | Contrainer Truck Ramp #3 / #4 / #5, Guard Station, Equipment Room | 3292.1052 | 463.0246 | 100% | 3292.1052 | Works | NCT | 12 | Post | 2025.3 | 2025.4 | 2025.6 | 2026.12
Total |  |  | 174384.8256 | 967.1946 | 100% | 174384.8256
Component 2: | Trade and Freight Service Facilities
HGAC-CW08 | Trade and Freight Service Facilities | (1) Duty-Free Service Center S01 (10,450 m2); (2) Comprehensive Office Building W01 (39,432 m2) | 28051.0846 | 3945.3002 | 100% | 28051.0846 | Works | NCT | 18 | Prior | 2025.3 | 2025.4 | 2025.6 | 2026.12
3.2 | S01 免税服务中心 |  | 8098.2373 | 1138.9926 | 100% | 8098.2373
3.2.1 | 土建工程 |  | 4284.5 | 602.602 | 100% | 4284.5
3.2.2 | 给排水工程 |  | 26.125 | 3.6744 | 100% | 26.125
3.2.3 | 电气工程 |  | 151.525 | 21.3115 | 100% | 151.525
3.2.4 | 暖通工程 |  | 120.175 | 16.9023 | 100% | 120.175
3.2.5 | 消防工程 |  | 146.3 | 20.5767 | 100% | 146.3
3.2.6 | 设备工程 |  | 41.8 | 5.879 | 100% | 41.8
3.2.7 | 场平工程 |  | 209 | 29.3952 | 100% | 209
| 室外工程 |  | 2754.8123 | 387.456 | 100% | 2754.8123
3.2.8 | 绿建工程 |  | 364 | 51.1955 | 100% | 364
| 其他可再生能源措施 |  | 289 | 40.647 | 100% | 289
| 废弃物绿色处理 |  | 4 | 0.56259 | 100% | 4
| 雨洪管理设施 |  | 4 | 0.56259 | 100% | 4
| LEED认证增量措施 |  | 32 | 4.5007 | 100% | 32
| 绿建三星增量措施 |  | 35 | 4.9226 | 100% | 35
3.1 | W01 综合办公楼 |  | 19952.8472 | 2806.3076 | 100% | 19952.8472
3.1.1 | 土建工程 |  | 14787.06 | 2079.7553 | 100% | 14787.06
3.1.2 | 给排水工程 |  | 98.5804 | 13.865 | 100% | 98.5804
3.1.3 | 电气工程 |  | 571.7663 | 80.4172 | 100% | 571.7663
3.1.4 | 暖通工程 |  | 453.4698 | 63.7792 | 100% | 453.4698
3.1.5 | 消防工程 |  | 552.0502 | 77.6442 | 100% | 552.0502
3.1.6 | 设备工程 |  | 157.7286 | 22.1841 | 100% | 157.7286
3.1.7 | 场平工程 |  | 788.6432 | 110.9203 | 100% | 788.6432
| 室外工程 |  | 2458.5486 | 345.7874 | 100% | 2458.5486
3.1.8 | 绿建工程 |  | 85 | 11.955 | 100% | 85
| 废弃物绿色处理 |  | 4 | 0.56259 | 100% | 4
| 雨洪管理设施 |  | 15 | 2.1097 | 100% | 15
| LEED认证增量措施 |  | 66 | 9.2827 | 100% | 66
Total |  |  | 28051.0846 | 3945.3002 | 100% | 28051.0846
Component 3: | Low-Carbon, Smart and Supporting Utilities
HGAC-CW09 | Roads (EPC Contract) | (1) Elevated Connecting Bridge #1 (Roadbed Area = 2,667 m2) / #2 (Roadbed Area = 2,375 m2); (2) 4 Roads in Phase II Area (Guihua Road No. 2 = 581.6 m / Guihua Road No. 3 = 990 m / Guihua Road No. 4 = 1,075 m / Guihua Road No. 5 = 354 m), and associated infrastructures | 20312.85 | 2856.9409 | 100% | 20312.85 | Works | NCT | 12 | Prior | 2025.1 | 2025.3 | 2025.3 | 2026.3
6 | 配套设施 |  | 2688.05 | 378.0661 | 100% | 2688.05 |  |  |  | 前审
6.1 | 1#高架联络道 |  | 399.45 | 56.1814 | 100% | 399.45 |  |  |  | 前审
6.1.1 | 路基 |  | 2145.6 | 301.7722 | 100% | 2145.6 |  |  |  | 前审
6.1.2 | 钢箱梁 |  | 143 | 20.1125 | 100% | 143 |  |  |  | 前审
6.1.3 | 装饰棚 |  | 6521.05 | 917.166 | 100% | 6521.05 |  |  |  | 前审
6.2 | 2#高架联络道 |  | 6521.05 | 917.166 | 100% | 6521.05 |  |  |  | 前审
6.2.1 | 路基 |  | 356.25 | 50.1055 | 100% | 356.25 |  |  |  | 前审
6.2.3 | 钢箱梁 |  | 5956.8 | 837.8059 | 100% | 5956.8 |  |  |  | 前审
6.2.4 | 装饰棚 |  | 208 | 29.2546 | 100% | 208 |  |  |  | 前审
6.3 | 规划二路 |  | 1959.93 | 275.6582 | 100% | 1959.93 |  |  |  | 前审
6.3.1 | 路基 |  | 1959.93 | 275.6582 | 100% | 1959.93 |  |  |  | 前审
6.4 | 规划三路 |  | 3742.2 | 526.3291 | 100% | 3742.2 |  |  |  | 前审
6.4.1 | 路基 |  | 3742.2 | 526.3291 | 100% | 3742.2 |  |  |  | 前审
6.5 | 规划四路 |  | 4063.5 | 571.519 | 100% | 4063.5 |  |  |  | 前审
6.5.1 | 路基 |  | 4063.5 | 571.519 | 100% | 4063.5 |  |  |  | 前审
6.6 | 规划五路 |  | 1338.12 | 188.2025 | 100% | 1338.12 |  |  |  | 前审
6.6.1 | 路基 |  | 1338.12 | 188.2025 | 100% | 1338.12 |  |  |  | 前审
HGAC-CW10 | Earth Works | Earth Works for Phase II | 20000 | 2812.9395 | 100% | 20000 | Works | NCT | 12 | Prior | 2025.1 | 2025.2 | 2025.3 | 2026.2 | 1st Works Contract
HGAC-GD01 | Roof-Top Photovolviac (1) | (1) Roof-Top Volvtaic for Phase II buildings including Customs Inspection Center (Phase I), International Express Center #1 / #2, Bonded Logistics Center (Type B) #1 / #2 / #3 and International Cargo Terminal, totalling 76,134 m2；(2) Phase II buildings including Bonded Logistics Warehouse P01 / R01 / R02 and Bonded Processing Warehouse Q01 / Q02, totalling 87,936 m2. (1) + (2) = 164,070 m2 | 5413.5455 | 761.3988 | 100% | 5413.5455 | Goods | NCT | 12 | Prior | 2025.1 | 2025.3 | 2025.3 | 2026.3 | 1st Goods Contract
4.1.22 | 海关查验中心 | 11022 | 363.6765 | 51.15 | 363.6765 | 51.15
4.1.23 | 保税仓库1 | 11707 | 386.1825 | 54.3154 | 386.1825 | 54.3154
4.1.24 | 保税仓库2 | 11707 | 386.1825 | 54.3154 | 386.1825 | 54.3154
4.1.25 | 保税仓库3 | 11707 | 386.1825 | 54.3154 | 386.1825 | 54.3154
4.1.26 | 国际快件中心 | 18327 | 604.7635 | 85.0582 | 604.7635 | 85.0582
4.1.27 | 快件中心 | 11664 | 384.8185 | 54.1236 | 384.8185 | 54.1236
4.1.16 | P001 | 16128 | 532.1305 | 74.8425 | 532.1305 | 74.8425
4.1.17 | Q001 | 18768 | 619.256 | 87.0965 | 619.256 | 87.0965
4.1.18 | Q002 | 18768 | 619.256 | 87.0965 | 619.256 | 87.0965
4.1.19 | R001 | 17136 | 565.5485 | 79.5427 | 565.5485 | 79.5427
4.1.20 | R002 | 17136 | 565.5485 | 79.5427 | 565.5485 | 79.5427
HGAC-GD02 | Roof-Top Photovolviac (2) | All buildings in Phase II including Duty-Free Service Center S01, Comprehensive Office Building W01, Customs Inspection Warehouse T01, Bonded Logistics Warehouse E01~E04 / H01~H04 / J01 / K01 / L01 / M01, totalling 196,714 m2 | 6823.41 | 959.692 | 100% | 6823.41 | Goods | NCT | 42 | Prior | 2025.6 | 2025.7 | 2025.9 | 2028.12
4.1 | 光伏 | 370864.11m2 | 12236.96 | 1721.0914 | 100% | 12236.96 | Goods |  |  | Post
| 亚投行资金建设北区 | 196714.11 | 6823.4145 | 959.6926 | 100% | 6823.4145 | Goods |  |  | Post
4.1.1 | 免税服务中心S01 | 5226.66 | 172.3755 | 24.2441 | 100% | 172.3755 | Goods |  |  | Post
4.1.2 | 综合业务楼W01 | 4929.02 | 162.657 | 22.8772 | 100% | 162.657 | Goods |  |  | Post
4.1.3 | E001 | 13104 | 432.388 | 60.8141 | 100% | 432.388 | Goods |  |  | Post
4.1.4 | E002 | 13104 | 432.388 | 60.8141 | 100% | 432.388 | Goods |  |  | Post
4.1.5 | E003 | 13104 | 432.388 | 60.8141 | 100% | 432.388 | Goods |  |  | Post
4.1.6 | E004 | 13104 | 432.388 | 60.8141 | 100% | 432.388 | Goods |  |  | Post
4.1.7 | E005 | 13104 | 432.388 | 60.8141 | 100% | 432.388 | Goods |  |  | Post
4.1.8 | H001 | 15120 | 498.883 | 70.1664 | 100% | 498.883 | Goods |  |  | Post
4.1.9 | H002 | 15120 | 498.883 | 70.1664 | 100% | 498.883 | Goods |  |  | Post
4.1.10 | H003 | 15120 | 498.883 | 70.1664 | 100% | 498.883 | Goods |  |  | Post
4.1.11 | H004 | 15120 | 498.883 | 70.1664 | 100% | 498.883 | Goods |  |  | Post
4.1.12 | J001 | 10800 | 356.345 | 50.1188 | 100% | 356.345 | Goods |  |  | Post
4.1.13 | K001 | 9360 | 308.7755 | 43.4283 | 100% | 308.7755 | Goods |  |  | Post
4.1.14 | L001 | 17136 | 565.5485 | 79.5427 | 100% | 565.5485 | Goods |  |  | Post
4.1.15 | M001 | 23262.43 | 767.591 | 107.9594 | 100% | 767.591 | Goods |  |  | Post
4.1.21 | T001(海关查验仓库) | 10080 | 332.65 | 46.7862 | 100% | 332.65 | Goods |  |  | Post
| 自建南区 | 87936 | 2901.75 | 408.1224 | 100% | 2901.75 | Goods |  |  | Post
4.1.16 | P001(自建南区) | 16128 | 532.13 | 74.8425 | 100% | 532.13 | Goods |  |  | Post
4.1.17 | Q001(自建南区) | 18768 | 619.26 | 87.097 | 100% | 619.26 | Goods |  |  | Post
4.1.18 | Q002(自建南区) | 18768 | 619.26 | 87.097 | 100% | 619.26 | Goods |  |  | Post
4.1.19 | R001(自建南区) | 17136 | 565.55 | 79.5429 | 100% | 565.55 | Goods |  |  | Post
4.1.20 | R002(自建南区) | 17136 | 565.55 | 79.5429 | 100% | 565.55 | Goods |  |  | Post
| 先行启动区 | 86214 | 2844.45 | 961.4906 | 100% | 6823.41 | Goods |  |  | Post
4.1.22 | 海关查验中心(先行启动区) | 11022 | 363.68 | 51.1505 | 100% | 363.68 | Goods |  |  | Post
4.1.23 | 保税仓库1 | 11707 | 386.18 | 54.315 | 100% | 386.18 | Goods |  |  | Post
4.1.24 | 保税仓库2 | 11707 | 386.18 | 54.315 | 100% | 386.18 | Goods |  |  | Post
4.1.25 | 保税仓库3 | 11707 | 386.18 | 54.315 | 100% | 386.18 | Goods |  |  | Post
4.1.26 | 国际快件中心 | 18327 | 604.76 | 85.0577 | 100% | 604.76 | Goods |  |  | Post
4.1.27 | 国际快件中心 | 11664 | 384.82 | 54.1238 | 100% | 384.82 | Goods |  |  | Post
HGAC-GD03 | Use of New Energy | Air heat pump energy for air conditioning system for Business Logistics Center (Phase I) | 3364 | 473.1364 | 100% | 3364 | Goods | NCT | 48 | Prior | 2025.1 | 2025.3 | 2025.3 | 2028.7
HGAC-GD04 | Smart Operations System | Intelligent operation system equipment and software for the park, including the IOC platform of the bonded zone, energy consumption management, carbon management, ESG visualization, asset management, transportation access management, smart security, smart fire protection, park enterprise management, etc | 4000 | 562.5879 | 100% | 4000 | Goods | NCT | 48 | Prior | 2025.1 | 2025.3 | 2025.3 | 2028.7
| 4.2 | 智慧运营平台 | 4000 |  | 100% | 4000 | Goods |  |  | Post
HGAC-GD05 | Integrated Information System | Smart customs auxiliary supervision platform, application support platform, enterprise customs clearance service platform, multimodal transport platform, park vehicle and dedestrian control equipment, park video equipment, park office informatization equipment, park safety/energy efficiency/firefighting equipment, digital platform, digital warehouse, one-stop security inspection area, quarantine processing area, etc. | 18818.98 | 2646.8326 | 100% | 18818.98 | Goods | ICOT | 42 | Prior | 2025.6 | 2025.7 | 2025.9 | 2028.12
4.3 | 综合信息化平台 |  | 18818.98 | 2646.8326 | 100% | 18818.98
4.3.1 | 智慧海关辅助监管平台 |  | 3355 | 471.8706 | 100% | 3355
4.3.2 | 应用支撑平台 |  | 920 | 129.3952 | 100% | 920
4.3.3 | 企业通关服务平台 |  | 3160 | 444.4444 | 100% | 3160
4.3.4 | 多式联运平台 |  | 2100 | 295.3586 | 100% | 2100
4.3.5 | 园区车辆行人管控设备 |  | 341.9 | 48.0872 | 100% | 341.9
4.3.6 | 园区视频设备 |  | 656.15 | 92.2855 | 100% | 656.15
4.3.7 | 园区办公信息化设备 |  | 355.67 | 50.0239 | 100% | 355.67
4.3.8 | 园区安全、能效、消防设备 |  | 211.46 | 29.7412 | 100% | 211.46
4.3.9 | 数字化月台 |  | 33.6 | 4.7257 | 100% | 33.6
4.3.10 | 数字化仓库 |  | 333.3 | 46.8776 | 100% | 333.3
4.3.11 | 一站式安检区 |  | 7000 | 984.5288 | 100% | 7000
4.3.12 | 检疫处理区 |  | 351.9 | 49.4937 | 100% | 351.9
Total |  |  | 78732.7855 | 11073.5282 | 100% | 75368.7855
Component 4: | Capacity Building
HGAC-CS01 | Project Management | Project management technical support, training, study tours, knowledge product development and dissemination | 1000 | 140.647 | 100% | 1000 | Consulting Services | IOCS/QCBS | 48 | Prior | 2025.1 | 2025.3 | 2025.4 | 2028.12
HGAC-CS02 | Project M&E | External environmental monitoring, external resettlement monitoring, external social / gender monitoring, project performance monitoring, etc. | 1000 | 140.647 | 100% | 1000 | Consulting Services | IOCS/QCBS | 48 | Prior | 2025.1 | 2025.3 | 2025.4 | 2028.12
HGAC-CS03 | Green Building Certification | Consulting services for certifying building to international or domestic standards | 761 | 107.0323 | 100% | 761 | Consulting Services | IOCS/QCBS | 42 | Prior | 2025.6 | 2025.7 | 2025.8 | 2028.12
HGAC-CS04 | 3-Star Green Building Certification | Consulting services for 3-star certification of buildings | 116 | 16.315 | 100% | 116 | Consulting Services | NCS/CQS | 42 | Post | 2025.6 | 2025.7 | 2025.8 | 2028.12
HGAC-CS05 | Research on Innovative Models for Customs Control & Supervision | Research on Innovative Models for Customs Control & Supervision | 350 | 49.2264 | 100% | 350 | Consulting Services | NCS/QCBS | 24 | Post | 2025.6 | 2025.7 | 2025.8 | 2028.12
HGAC-CS06 | Research on Innovative Models for Integrated Multi-Quarantine Service | Research on Innovative Models for Integrated Multi-Quanrantine Service | 350 | 49.2264 | 100% |  | Consulting Services | NCS/QCBS | 24 | Post | 2025.6 | 2025.7 | 2025.8 | 2028.12
HGAC-CS07 | Research on Innovative Models for Multi-Modal Transport | Research on Innovative Models for Multi-Modal Transport | 300 | 42.1941 | 100% |  | Consulting Services | NCS/QCBS | 24 | Post | 2025.6 | 2025.7 | 2025.8 | 2028.12
Total |  |  | 3877 | 545.2883 | 100% | 3877
GRAND TOTAL |  |  | 285045.6957 | 40090.8152 | 100% | 285045.6957
|  | CW土建 | 242748.7602 | 34141.8791
|  | Goods货物 | 38419.9355 | 5403.6477
|  | Consulting Services咨询服务 | 3877 | 545.2883
|  |  | 285045.6957 | 40090.8152

## 采购计划0530_中文 (hidden)
附件1-亚投行贷款湖北航空货运产业园项目采购计划 (2024年4月)
1美元=人民币 | 亚投行项目评估考察备忘录
7.11 | 2024-04-12
合同编号 | 合同名称 | 合同内容描述 | 合同估算价 |  | 亚投行贷款额 |  | 合同类型 | 采购方式 | 合同期 (月) | 审查 方式 | 采用招标文件类型 | 提前 采购 | 追溯贷款 | 预计 公告日期 | 预计 开标时间 | 预计合同 签订时间 | 预计合同 完成时间 | 备注
|  |  | 人民币 (万元) | 美元 (万元) | 美元 (万元) | 人民币 (万元)
组成部分1: | 海关业务和保税设施
HGAC-CW01 | 海关运营设施 | (1) 海关查验仓库T01，面积10,911 m2 ; (2) 卡口与围网: #2海关卡口 949 m2、围网7,730 m | 6876.7533 | 967.1946 | 967.1946 | 6876.7533 | 土建 | NCT | 18 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
1.1 | T01 | T01 海关查验仓库 | 5931.3338 |  | 0 | 5931.3338
1.1.1 |  | 土建工程 | 4137.5599 |  | 0 | 4137.5599
1.1.2 |  | 给排水工程 | 13.9661 |  | 0 | 13.9661
1.1.3 |  | 电气工程 | 125.6947 |  | 0 | 125.6947
1.1.4 |  | 暖通工程 | 97.7626 |  | 0 | 97.7626
1.1.5 |  | 消防工程 | 216.4742 |  | 0 | 216.4742
1.1.6 |  | 设备工程 | 59.6525 |  | 0 | 59.6525
1.1.7 |  | 场平工程 | 218.22 |  | 0 | 218.22
1.1.8 |  | 室外工程 | 1024.0038 |  | 0 | 1024.0038
1.1.8 |  | 绿建工程 | 38 |  | 0 | 38
|  | 废弃物绿色处理 | 1 |  | 0 | 1
|  | 雨洪管理设施 | 4 |  | 0 | 4
|  | LEED认证增量措施 | 33 |  | 0 | 33
1.2 |  | 2#海关卡口 | 481.6195 |  | 0 | 481.6195
1.2.1 |  | 地基处理 | 3.3215 |  | 0 | 3.3215
1.2.2 |  | 土建工程 | 455.52 |  | 0 | 455.52
1.2.3 |  | 给排水工程 | 2.847 |  | 0 | 2.847
1.2.4 |  | 暖通工程 | 3.796 |  | 0 | 3.796
1.2.5 |  | 电气工程 | 8.541 |  | 0 | 8.541
1.2.6 |  | 抗震支架 | 5.694 |  | 0 | 5.694
1.2.7 |  | 标识标牌 | 1.9 |  | 0 | 1.9
1.4 |  | 海关围网 | 463.8 |  | 0 | 463.8
HGAC-CW02 | 保税物流仓库 (一) | 保税物流仓库M01，建筑面积总计20,396 m2 | 13277.6977 | 1867.468 | 1867.468 | 13277.6977 | 土建 | NCT | 18 | 前审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.8 | M01 物流仓库 |  | 13277.6977 | 1867.468 | 1867.468 | 13277.6977 |  |  |  | 前审
2.8.1 | 土建工程 |  | 9630.4162 | 1354.4889 | 1354.4889 | 9630.4162 |  |  |  | 前审
2.8.2 | 给排水工程 |  | 32.5069 | 4.572 | 4.572 | 32.5069 |  |  |  | 前审
2.8.3 | 电气工程 |  | 292.5619 | 41.1479 | 41.1479 | 292.5619 |  |  |  | 前审
2.8.4 | 暖通工程 |  | 227.5482 | 32.004 | 32.004 | 227.5482 |  |  |  | 前审
2.8.5 | 消防工程 |  | 503.8566 | 70.8659 | 70.8659 | 503.8566 |  |  |  | 前审
2.8.6 | 设备工程 |  | 138.8447 | 19.5281 | 19.5281 | 138.8447 |  |  |  | 前审
2.8.7 | 场平工程 |  | 507.92 | 71.4374 | 71.4374 | 507.92 |  |  |  | 前审
| 室外工程 |  | 1881.0431 | 264.563 | 264.563 | 1881.0431 |  |  |  | 前审
2.8.8 | 绿建工程 |  | 63 | 8.8608 | 8.8608 | 63 |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 |  |  |  | 前审
| 雨洪管理设施 |  | 11 | 1.5471 | 1.5471 | 11 |  |  |  | 前审
| LEED认证增量措施 |  | 51 | 7.173 | 7.173 | 51 |  |  |  | 前审
HGAC-CW03 | 保税物流仓库 (二) | 保税物流仓库J01 / K01、架空平台3，建筑面积总计42,780 m2 | 25772.9634 | 3624.8894 | 3624.8894 | 25772.9634 | 土建 | NCT | 18 | 前审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15 | J01 物流仓库 |  | 11277.3601 | 1586.1266 | 1586.1266 | 11277.3601 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.1 | 土建工程 |  | 8671.015 | 1219.552 | 1219.552 | 8671.015 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.2 | 给排水工程 |  | 29.2685 | 4.1165 | 4.1165 | 29.2685 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.3 | 电气工程 |  | 263.4163 | 37.0487 | 37.0487 | 263.4163 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.4 | 暖通工程 |  | 204.8794 | 28.8157 | 28.8157 | 204.8794 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.5 | 消防工程 |  | 453.6614 | 63.8061 | 63.8061 | 453.6614 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.6 | 设备工程 |  | 125.0127 | 17.5827 | 17.5827 | 125.0127 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.7 | 场平工程 |  | 457.32 | 64.3207 | 64.3207 | 457.32 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| 室外工程 |  | 1015.7868 | 142.8673 | 142.8673 | 1015.7868
2.15.8 | 绿建工程 |  | 57 | 8.0169 | 8.0169 | 57 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| 雨洪管理设施 |  | 9 | 1.2658 | 1.2658 | 9 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| LEED认证增量措施 |  | 47 | 6.6104 | 6.6104 | 47 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16 | K01 物流仓库 |  | 11277.3601 | 1586.1266 | 1586.1266 | 11277.3601 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.1 | 土建工程 |  | 8671.015 | 1219.552 | 1219.552 | 8671.015 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.2 | 给排水工程 |  | 29.2685 | 4.1165 | 4.1165 | 29.2685 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.3 | 电气工程 |  | 263.4163 | 37.0487 | 37.0487 | 263.4163 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.4 | 暖通工程 |  | 204.8794 | 28.8157 | 28.8157 | 204.8794 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.5 | 消防工程 |  | 453.6614 | 63.8061 | 63.8061 | 453.6614 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.6 | 设备工程 |  | 125.0127 | 17.5827 | 17.5827 | 125.0127 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.7 | 场平工程 |  | 457.32 | 64.3207 | 64.3207 | 457.32 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| 室外工程 |  | 1015.7868 | 142.8673 | 142.8673 | 1015.7868
2.16.8 | 绿建工程 |  | 57 | 8.0169 | 8.0169 | 57 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| 雨洪管理设施 |  | 9 | 1.2658 | 1.2658 | 9 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| LEED认证增量措施 |  | 47 | 6.6104 | 6.6104 | 47 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.18 | 架空平台3 |  | 4178.7488 | 587.7284 | 587.7284 | 4178.7488
2.18.1 | 建筑工程 |  | 4053.3863 | 570.0965 | 570.0965 | 4053.3863
2.18.2 | 安装工程 |  | 125.3625 | 17.6319 | 17.6319 | 125.3625
HGAC-CW04 | 保税物流仓库 (三) | 保税物流仓库H01 / H02 / E05,、架空平台2，建筑面积总计121,805 m2 | 54208.0131 | 7624.1931 | 7624.1931 | 54208.0131 | 土建 | IOCT | 18 | 前审 | 是 |  |  | 2027.3 | 2027.4 | 2027.5 | 2028.12
2.1 | H01 物流仓库 |  | 15502.4051 | 2180.3664 | 2180.3664 | 15502.4051
2.10.1 | 土建工程 |  | 12124.8594 | 1705.3248 | 1705.3248 | 12124.8594
2.10.2 | 给排水工程 |  | 40.9267 | 5.7562 | 5.7562 | 40.9267
2.10.3 | 电气工程 |  | 368.3405 | 51.806 | 51.806 | 368.3405
2.10.4 | 暖通工程 |  | 286.487 | 40.2935 | 40.2935 | 286.487
2.10.5 | 消防工程 |  | 634.3642 | 89.2214 | 89.2214 | 634.3642
2.10.6 | 设备工程 |  | 174.8079 | 24.5862 | 24.5862 | 174.8079
2.10.7 | 场平工程 |  | 639.48 | 89.9409 | 89.9409 | 639.48
| 室外工程 |  | 1161.1395 | 163.3108 | 163.3108 | 1161.1395
2.10.8 | 绿建工程 |  | 72 | 10.1266 | 10.1266 | 72
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1
| 雨洪管理设施 |  | 13 | 1.8284 | 1.8284 | 13
| LEED认证增量措施 |  | 58 | 8.1575 | 8.1575 | 58
2.11 | H02 物流仓库 |  | 15296.8552 | 2151.4564 | 2151.4564 | 15296.8552
2.11.1 | 土建工程 |  | 12124.8594 | 1705.3248 | 1705.3248 | 12124.8594
2.11.2 | 给排水工程 |  | 40.9267 | 5.7562 | 5.7562 | 40.9267
2.11.3 | 电气工程 |  | 368.3405 | 51.806 | 51.806 | 368.3405
2.11.4 | 暖通工程 |  | 286.487 | 40.2935 | 40.2935 | 286.487
2.11.5 | 消防工程 |  | 634.3642 | 89.2214 | 89.2214 | 634.3642
2.11.6 | 设备工程 |  | 174.8079 | 24.5862 | 24.5862 | 174.8079
2.11.7 | 场平工程 |  | 639.48 | 89.9409 | 89.9409 | 639.48
| 室外工程 |  | 955.5896 | 134.4008 | 134.4008 | 955.5896
2.11.8 | 绿建工程 |  | 72 | 10.1266 | 10.1266 | 72
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1
| 雨洪管理设施 |  | 13 | 1.8284 | 1.8284 | 13
| LEED认证增量措施 |  | 58 | 8.1575 | 8.1575 | 58
2.9 | E05 物流仓库 |  | 13789.8727 | 1939.5039 | 1939.5039 | 13789.8727
2.9.1 | 土建工程 |  | 10541.2786 | 1482.599 | 1482.599 | 10541.2786
2.9.2 | 给排水工程 |  | 35.5814 | 5.0044 | 5.0044 | 35.5814
2.9.3 | 电气工程 |  | 320.233 | 45.0398 | 45.0398 | 320.233
2.9.4 | 暖通工程 |  | 249.0701 | 35.031 | 35.031 | 249.0701
2.9.5 | 消防工程 |  | 551.5123 | 77.5685 | 77.5685 | 551.5123
2.9.6 | 设备工程 |  | 151.9769 | 21.3751 | 21.3751 | 151.9769
2.9.7 | 场平工程 |  | 555.96 | 78.1941 | 78.1941 | 555.96
| 室外工程 |  | 1319.2604 | 185.55 | 185.55 | 1319.2604
2.9.8 | 绿建工程 |  | 65 | 9.1421 | 9.1421 | 65
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1
| 雨洪管理设施 |  | 11 | 1.5471 | 1.5471 | 11
| LEED认证增量措施 |  | 53 | 7.4543 | 7.4543 | 53
2.17 | 架空平台2 |  | 9618.88 | 1352.8664 | 1352.8664 | 9618.88
2.17.1 | 建筑工程 |  | 9330.3136 | 1312.2804 | 1312.2804 | 9330.3136
2.17.2 | 安装工程 |  | 288.5664 | 40.586 | 40.586 | 288.5664
HGAC-CW05 | 保税物流仓库 (四) | 保税物流仓库H03 / H04 / L01，建筑面积总计100,098 m2 | 47558.926 | 6689.0191 | 6689.0191 | 47558.926 | 土建 | IOCT | 18 | 前审 | 是 |  |  | 2027.3 | 2027.4 | 2027.5 | 2028.12
2.12 | H03 物流仓库 |  | 15098.9985 | 2123.6285 | 2123.6285 | 15098.9985 |  |  |  | 前审
2.12.1 | 土建工程 |  | 12124.8594 | 1705.3248 | 1705.3248 | 12124.8594 |  |  |  | 前审
2.12.2 | 给排水工程 |  | 40.9267 | 5.7562 | 5.7562 | 40.9267 |  |  |  | 前审
2.12.3 | 电气工程 |  | 368.3405 | 51.806 | 51.806 | 368.3405 |  |  |  | 前审
2.12.4 | 暖通工程 |  | 286.487 | 40.2935 | 40.2935 | 286.487 |  |  |  | 前审
2.12.5 | 消防工程 |  | 634.3642 | 89.2214 | 89.2214 | 634.3642 |  |  |  | 前审
2.12.6 | 设备工程 |  | 174.8079 | 24.5862 | 24.5862 | 174.8079 |  |  |  | 前审
2.12.7 | 场平工程 |  | 639.48 | 89.9409 | 89.9409 | 639.48 |  |  |  | 前审
| 室外工程 |  | 757.7328 | 106.5728 | 106.5728 | 757.7328 |  |  |  | 前审
2.12.8 | 绿建工程 |  | 72 | 10.1266 | 10.1266 | 72 |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 |  |  |  | 前审
| 雨洪管理设施 |  | 13 | 1.8284 | 1.8284 | 13 |  |  |  | 前审
| LEED认证增量措施 |  | 58 | 8.1575 | 8.1575 | 58 |  |  |  | 前审
2.13 | H04 物流仓库 |  | 15276.6249 | 2148.6111 | 2148.6111 | 15276.6249 |  |  |  | 前审
2.13.1 | 土建工程 |  | 12124.8594 | 1705.3248 | 1705.3248 | 12124.8594 |  |  |  | 前审
2.13.2 | 给排水工程 |  | 40.9267 | 5.7562 | 5.7562 | 40.9267 |  |  |  | 前审
2.13.3 | 电气工程 |  | 368.3405 | 51.806 | 51.806 | 368.3405 |  |  |  | 前审
2.13.4 | 暖通工程 |  | 286.487 | 40.2935 | 40.2935 | 286.487 |  |  |  | 前审
2.13.5 | 消防工程 |  | 634.3642 | 89.2214 | 89.2214 | 634.3642 |  |  |  | 前审
2.13.6 | 设备工程 |  | 174.8079 | 24.5862 | 24.5862 | 174.8079 |  |  |  | 前审
2.13.7 | 场平工程 |  | 639.48 | 89.9409 | 89.9409 | 639.48 |  |  |  | 前审
| 室外工程 |  | 935.3592 | 131.5554 | 131.5554 | 935.3592 |  |  |  | 前审
2.13.8 | 绿建工程 |  | 72 | 10.1266 | 10.1266 | 72 |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 |  |  |  | 前审
| 雨洪管理设施 |  | 13 | 1.8284 | 1.8284 | 13 |  |  |  | 前审
| LEED认证增量措施 |  | 58 | 8.1575 | 8.1575 | 58 |  |  |  | 前审
2.14 | L01 物流仓库 |  | 17183.3027 | 2416.7796 | 2416.7796 | 17183.3027 |  |  |  | 前审
2.14.1 | 土建工程 |  | 13708.4402 | 1928.0507 | 1928.0507 | 13708.4402 |  |  |  | 前审
2.14.2 | 给排水工程 |  | 46.272 | 6.508 | 6.508 | 46.272 |  |  |  | 前审
2.14.3 | 电气工程 |  | 416.448 | 58.5722 | 58.5722 | 416.448 |  |  |  | 前审
2.14.4 | 暖通工程 |  | 323.904 | 45.5561 | 45.5561 | 323.904 |  |  |  | 前审
2.14.5 | 消防工程 |  | 717.216 | 100.8743 | 100.8743 | 717.216 |  |  |  | 前审
2.14.6 | 设备工程 |  | 197.6389 | 27.7973 | 27.7973 | 197.6389 |  |  |  | 前审
2.14.7 | 场平工程 |  | 723 | 101.6878 | 101.6878 | 723 |  |  |  | 前审
| 室外工程 |  | 972.3836 | 136.7628 | 136.7628 | 972.3836 |  |  |  | 前审
2.14.8 | 绿建工程 |  | 78 | 10.9705 | 10.9705 | 78 |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 |  |  |  | 前审
| 雨洪管理设施 |  | 14 | 1.9691 | 1.9691 | 14 |  |  |  | 前审
| LEED认证增量措施 |  | 63 | 8.8608 | 8.8608 | 63 |  |  |  | 前审
HGAC-CW06 | 保税加工仓库 | 保税加工仓库E01 / E02 / E03 / E04，建筑面积总计57,184 m2 | 23398.367 | 3290.9096 | 3290.9096 | 23398.367 | 土建 | NCT | 18 | 前审 | 是 |  |  | 2026.3 | 2026.4 | 2026.5 | 2027.12
2.4 | E01 物流仓库 |  | 5921.3919 | 832.8259 | 832.8259 | 5921.3919 |  |  |  | 前审
2.4.1 | 土建工程 |  | 3574 | 502.6723 | 502.6723 | 3574 |  |  |  | 前审
2.4.2 | 给排水工程 |  | 18.2989 | 2.5737 | 2.5737 | 18.2989 |  |  |  | 前审
2.4.3 | 电气工程 |  | 164.6899 | 23.1631 | 23.1631 | 164.6899 |  |  |  | 前审
2.4.4 | 暖通工程 |  | 128.0922 | 18.0158 | 18.0158 | 128.0922 |  |  |  | 前审
2.4.5 | 消防工程 |  | 283.6326 | 39.8921 | 39.8921 | 283.6326 |  |  |  | 前审
2.4.6 | 设备工程 |  | 78.1589 | 10.9928 | 10.9928 | 78.1589 |  |  |  | 前审
2.4.7 | 场平工程 |  | 571.84 | 80.4276 | 80.4276 | 571.84 |  |  |  | 前审
| 室外工程 |  | 1036.6793 | 145.8058 | 145.8058 | 1036.6793 |  |  |  | 前审
2.4.8 | 绿建工程 |  | 66 | 9.2827 | 9.2827 | 66 |  |  |  | 前审
| 废弃物绿色处理 |  | 2 | 0.28129 | 0.28129 | 2 |  |  |  | 前审
| 雨洪管理设施 |  | 11 | 1.5471 | 1.5471 | 11 |  |  |  | 前审
| LEED认证增量措施 |  | 53 | 7.4543 | 7.4543 | 53 |  |  |  | 前审
2.5 | E02 物流仓库 |  | 5952.1709 | 837.1548 | 837.1548 | 5952.1709 |  |  |  | 前审
2.5.1 | 土建工程 |  | 3574 | 502.6723 | 502.6723 | 3574 |  |  |  | 前审
2.5.2 | 给排水工程 |  | 18.2989 | 2.5737 | 2.5737 | 18.2989 |  |  |  | 前审
2.5.3 | 电气工程 |  | 164.6899 | 23.1631 | 23.1631 | 164.6899 |  |  |  | 前审
2.5.4 | 暖通工程 |  | 128.0922 | 18.0158 | 18.0158 | 128.0922 |  |  |  | 前审
2.5.5 | 消防工程 |  | 283.6326 | 39.8921 | 39.8921 | 283.6326 |  |  |  | 前审
2.5.6 | 设备工程 |  | 78.1589 | 10.9928 | 10.9928 | 78.1589 |  |  |  | 前审
2.5.7 | 场平工程 |  | 571.84 | 80.4276 | 80.4276 | 571.84 |  |  |  | 前审
| 室外工程 |  | 1068.4583 | 150.2754 | 150.2754 | 1068.4583 |  |  |  | 前审
2.5.8 | 绿建工程 |  | 65 | 9.1421 | 9.1421 | 65 |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 |  |  |  | 前审
| 雨洪管理设施 |  | 11 | 1.5471 | 1.5471 | 11 |  |  |  | 前审
| LEED认证增量措施 |  | 53 | 7.4543 | 7.4543 | 53 |  |  |  | 前审
2.6 | E03 物流仓库 |  | 5747.9617 | 808.4334 | 808.4334 | 5747.9617 |  |  |  | 前审
2.6.1 | 土建工程 |  | 3574 | 502.6723 | 502.6723 | 3574 |  |  |  | 前审
2.6.2 | 给排水工程 |  | 18.2989 | 2.5737 | 2.5737 | 18.2989 |  |  |  | 前审
2.6.3 | 电气工程 |  | 164.6899 | 23.1631 | 23.1631 | 164.6899 |  |  |  | 前审
2.6.4 | 暖通工程 |  | 128.0922 | 18.0158 | 18.0158 | 128.0922 |  |  |  | 前审
2.6.5 | 消防工程 |  | 283.6326 | 39.8921 | 39.8921 | 283.6326 |  |  |  | 前审
2.6.6 | 设备工程 |  | 78.1589 | 10.9928 | 10.9928 | 78.1589 |  |  |  | 前审
2.6.7 | 场平工程 |  | 571.84 | 80.4276 | 80.4276 | 571.84 |  |  |  | 前审
| 室外工程 |  | 864.2492 | 121.554 | 121.554 | 864.2492 |  |  |  | 前审
2.6.8 | 绿建工程 |  | 65 | 9.1421 | 9.1421 | 65 |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 |  |  |  | 前审
| 雨洪管理设施 |  | 11 | 1.5471 | 1.5471 | 11 |  |  |  | 前审
| LEED认证增量措施 |  | 53 | 7.4543 | 7.4543 | 53 |  |  |  | 前审
2.7 | E04 物流仓库 |  | 5776.8425 | 812.4954 | 812.4954 | 5776.8425 |  |  |  | 前审
2.7.1 | 土建工程 |  | 3574 | 502.6723 | 502.6723 | 3574 |  |  |  | 前审
2.7.2 | 给排水工程 |  | 18.2989 | 2.5737 | 2.5737 | 18.2989 |  |  |  | 前审
2.7.3 | 电气工程 |  | 164.6899 | 23.1631 | 23.1631 | 164.6899 |  |  |  | 前审
2.7.4 | 暖通工程 |  | 128.0922 | 18.0158 | 18.0158 | 128.0922 |  |  |  | 前审
2.7.5 | 消防工程 |  | 283.6326 | 39.8921 | 39.8921 | 283.6326 |  |  |  | 前审
2.7.6 | 设备工程 |  | 78.1589 | 10.9928 | 10.9928 | 78.1589 |  |  |  | 前审
2.7.7 | 场平工程 |  | 571.84 | 80.4276 | 80.4276 | 571.84 |  |  |  | 前审
| 室外工程 |  | 893.13 | 125.616 | 125.616 | 893.13 |  |  |  | 前审
2.7.8 | 绿建工程 |  | 65 | 9.1421 | 9.1421 | 65 |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 |  |  |  | 前审
| 雨洪管理设施 |  | 11 | 1.5471 | 1.5471 | 11 |  |  |  | 前审
| LEED认证增量措施 |  | 53 | 7.4543 | 7.4543 | 53 |  |  |  | 前审
HGAC-CW07 | 附属工程 | 集卡坡道3、集卡坡道4、集卡坡道5、门卫室、设备用房 | 3292.1052 | 463.0246 | 463.0246 | 3292.1052 | 土建 | NCT | 12 | 前审 |  |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.5
小计 |  |  | 174384.8256 | 967.1946 | 967.1946 | 174384.8256
组成部分2: | 贸易和货运服务设施
HGAC-CW08 | 贸易和货运服务设施 | (1) 免税服务中心S01，建筑面积10,450 m2; (2) 综合办公楼W01，建筑面积39,432 m2 | 28051.0846 | 3945.3002 | 3945.3002 | 28051.0846 | 土建 | NCT | 18 | 前审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
3.2 | S01 免税服务中心 |  | 8098.2373 | 1138.9926 | 1138.9926 | 8098.2373
3.2.1 | 土建工程 |  | 4284.5 | 602.602 | 602.602 | 4284.5
3.2.2 | 给排水工程 |  | 26.125 | 3.6744 | 3.6744 | 26.125
3.2.3 | 电气工程 |  | 151.525 | 21.3115 | 21.3115 | 151.525
3.2.4 | 暖通工程 |  | 120.175 | 16.9023 | 16.9023 | 120.175
3.2.5 | 消防工程 |  | 146.3 | 20.5767 | 20.5767 | 146.3
3.2.6 | 设备工程 |  | 41.8 | 5.879 | 5.879 | 41.8
3.2.7 | 场平工程 |  | 209 | 29.3952 | 29.3952 | 209
| 室外工程 |  | 2754.8123 | 387.456 | 387.456 | 2754.8123
3.2.8 | 绿建工程 |  | 364 | 51.1955 | 51.1955 | 364
| 其他可再生能源措施 |  | 289 | 40.647 | 40.647 | 289
| 废弃物绿色处理 |  | 4 | 0.56259 | 0.56259 | 4
| 雨洪管理设施 |  | 4 | 0.56259 | 0.56259 | 4
| LEED认证增量措施 |  | 32 | 4.5007 | 4.5007 | 32
| 绿建三星增量措施 |  | 35 | 4.9226 | 4.9226 | 35
3.1 | W01 综合办公楼 |  | 19952.8472 | 2806.3076 | 2806.3076 | 19952.8472
3.1.1 | 土建工程 |  | 14787.06 | 2079.7553 | 2079.7553 | 14787.06
3.1.2 | 给排水工程 |  | 98.5804 | 13.865 | 13.865 | 98.5804
3.1.3 | 电气工程 |  | 571.7663 | 80.4172 | 80.4172 | 571.7663
3.1.4 | 暖通工程 |  | 453.4698 | 63.7792 | 63.7792 | 453.4698
3.1.5 | 消防工程 |  | 552.0502 | 77.6442 | 77.6442 | 552.0502
3.1.6 | 设备工程 |  | 157.7286 | 22.1841 | 22.1841 | 157.7286
3.1.7 | 场平工程 |  | 788.6432 | 110.9203 | 110.9203 | 788.6432
| 室外工程 |  | 2458.5486 | 345.7874 | 345.7874 | 2458.5486
3.1.8 | 绿建工程 |  | 85 | 11.955 | 11.955 | 85
| 废弃物绿色处理 |  | 4 | 0.56259 | 0.56259 | 4
| 雨洪管理设施 |  | 15 | 2.1097 | 2.1097 | 15
| LEED认证增量措施 |  | 66 | 9.2827 | 9.2827 | 66
小计 |  |  | 28051.0846 | 3945.3002 | 3945.3002 | 28051.0846
组成部分3: | 低碳、智慧和配套设施
HGAC-CW09 | 园区道路 | (1) 高架联络道#1 (路基面积2,667 m2)、高架联络道#2 (路基面积2,375 m2); (2) 4条北区道路(规划二路581.6 m、规划三路990 m、规划四路1,075 m、规划五路354 m), 以及相关基础设施 | 20312.85 | 2856.9409 | 2856.9409 | 20312.85 | 土建 | NCT | 12 | 前审 | 是 | 是 |  | 2024.9 | 2024.10 | 2024.11 | 2025.11 | 土建类别第一个
6 | 配套设施 |  | 2688.05 | 378.0661 | 378.0661 | 2688.05 |  |  |  | 前审
6.1 | 1#高架联络道 |  | 399.45 | 56.1814 | 56.1814 | 399.45 |  |  |  | 前审
6.1.1 | 路基 |  | 2145.6 | 301.7722 | 301.7722 | 2145.6 |  |  |  | 前审
6.1.2 | 钢箱梁 |  | 143 | 20.1125 | 20.1125 | 143 |  |  |  | 前审
6.1.3 | 装饰棚 |  | 6521.05 | 917.166 | 917.166 | 6521.05 |  |  |  | 前审
6.2 | 2#高架联络道 |  | 6521.05 | 917.166 | 917.166 | 6521.05 |  |  |  | 前审
6.2.1 | 路基 |  | 356.25 | 50.1055 | 50.1055 | 356.25 |  |  |  | 前审
6.2.3 | 钢箱梁 |  | 5956.8 | 837.8059 | 837.8059 | 5956.8 |  |  |  | 前审
6.2.4 | 装饰棚 |  | 208 | 29.2546 | 29.2546 | 208 |  |  |  | 前审
6.3 | 规划二路 |  | 1959.93 | 275.6582 | 275.6582 | 1959.93 |  |  |  | 前审
6.3.1 | 路基 |  | 1959.93 | 275.6582 | 275.6582 | 1959.93 |  |  |  | 前审
6.4 | 规划三路 |  | 3742.2 | 526.3291 | 526.3291 | 3742.2 |  |  |  | 前审
6.4.1 | 路基 |  | 3742.2 | 526.3291 | 526.3291 | 3742.2 |  |  |  | 前审
6.5 | 规划四路 |  | 4063.5 | 571.519 | 571.519 | 4063.5 |  |  |  | 前审
6.5.1 | 路基 |  | 4063.5 | 571.519 | 571.519 | 4063.5 |  |  |  | 前审
6.6 | 规划五路 |  | 1338.12 | 188.2025 | 188.2025 | 1338.12 |  |  |  | 前审
6.6.1 | 路基 |  | 1338.12 | 188.2025 | 188.2025 | 1338.12 |  |  |  | 前审
HGAC-CW10 | 土方工程 | 二期北区土方工程 | 20000 | 2812.9395 | 2812.9395 | 20000 | 土建 | NCT | 12 | 前审 |  | 是 |  | 2024.9 | 2024.10 | 2024.11 | 2025.11
HGAC-GD01 | 屋顶光伏(一) | (1) 一期(先行启动区)海关查验中心、国际快件中心#1 /#2、保税物流中心(B类)#1 / #2 / #3、国际货站顶部光伏设备采购与安装，共计76,134 m2；(2)自建南区建筑(·P01 / R01 / R02保税物流仓库、Q01 / Q02保税加工仓库)顶部光伏设备采购与安装，共计87,936 m2。总计(1) + (2) = 164,070 m2 | 5413.5455 | 761.3988 | 761.3988 | 5413.5455 | 货物 | NCT | 12 | 前审 | 是 | 是 |  | 2024.9 | 2024.10 | 2024.11 | 2025.11 | 货物类别第一个
4.1.22 | 海关查验中心 | 11022 | 363.6765 | 51.15 | 363.6765 | 51.15
4.1.23 | 保税仓库1 | 11707 | 386.1825 | 54.3154 | 386.1825 | 54.3154
4.1.24 | 保税仓库2 | 11707 | 386.1825 | 54.3154 | 386.1825 | 54.3154
4.1.25 | 保税仓库3 | 11707 | 386.1825 | 54.3154 | 386.1825 | 54.3154
4.1.26 | 国际快件中心 | 18327 | 604.7635 | 85.0582 | 604.7635 | 85.0582
4.1.27 | 快件中心 | 11664 | 384.8185 | 54.1236 | 384.8185 | 54.1236
4.1.16 | P001 | 16128 | 532.1305 | 74.8425 | 532.1305 | 74.8425
4.1.17 | Q001 | 18768 | 619.256 | 87.0965 | 619.256 | 87.0965
4.1.18 | Q002 | 18768 | 619.256 | 87.0965 | 619.256 | 87.0965
4.1.19 | R001 | 17136 | 565.5485 | 79.5427 | 565.5485 | 79.5427
4.1.20 | R002 | 17136 | 565.5485 | 79.5427 | 565.5485 | 79.5427
HGAC-GD02 | 屋顶光伏(二) | 亚投行资金建设北区所有建筑，包括免税服务中心S01、综合业务楼W01，海关查验仓库T01、保税物流仓库E01~E04 / H01~H04 / J01 / K01 / L01 / M01，总计196,714 m2 | 6823.41 | 959.692 | 959.692 | 6823.41 | 货物 | NCT | 40 | 后审 |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
4.1 | 光伏 | 370864.11m2 | 12236.96 | 1721.0914 | 1721.0914 | 12236.96
| 亚投行资金建设北区 | 196714.11 | 6823.4145 | 959.6926 | 959.6926 | 6823.4145
4.1.1 | 免税服务中心S01 | 5226.66 | 172.3755 | 24.2441 | 24.2441 | 172.3755
4.1.2 | 综合业务楼W01 | 4929.02 | 162.657 | 22.8772 | 22.8772 | 162.657
4.1.3 | E001 | 13104 | 432.388 | 60.8141 | 60.8141 | 432.388
4.1.4 | E002 | 13104 | 432.388 | 60.8141 | 60.8141 | 432.388
4.1.5 | E003 | 13104 | 432.388 | 60.8141 | 60.8141 | 432.388
4.1.6 | E004 | 13104 | 432.388 | 60.8141 | 60.8141 | 432.388
4.1.7 | E005 | 13104 | 432.388 | 60.8141 | 60.8141 | 432.388
4.1.8 | H001 | 15120 | 498.883 | 70.1664 | 70.1664 | 498.883
4.1.9 | H002 | 15120 | 498.883 | 70.1664 | 70.1664 | 498.883
4.1.10 | H003 | 15120 | 498.883 | 70.1664 | 70.1664 | 498.883
4.1.11 | H004 | 15120 | 498.883 | 70.1664 | 70.1664 | 498.883
4.1.12 | J001 | 10800 | 356.345 | 50.1188 | 50.1188 | 356.345
4.1.13 | K001 | 9360 | 308.7755 | 43.4283 | 43.4283 | 308.7755
4.1.14 | L001 | 17136 | 565.5485 | 79.5427 | 79.5427 | 565.5485
4.1.15 | M001 | 23262.43 | 767.591 | 107.9594 | 107.9594 | 767.591
4.1.21 | T001(海关查验仓库) | 10080 | 332.65 | 46.7862 | 46.7862 | 332.65
| 自建南区 | 87936 | 2901.75 | 408.1224 | 408.1224 | 2901.75
4.1.16 | P001(自建南区) | 16128 | 532.13 | 74.8425 | 74.8425 | 532.13
4.1.17 | Q001(自建南区) | 18768 | 619.26 | 87.097 | 87.097 | 619.26
4.1.18 | Q002(自建南区) | 18768 | 619.26 | 87.097 | 87.097 | 619.26
4.1.19 | R001(自建南区) | 17136 | 565.55 | 79.5429 | 79.5429 | 565.55
4.1.20 | R002(自建南区) | 17136 | 565.55 | 79.5429 | 79.5429 | 565.55
| 先行启动区 | 86214 | 2844.45 | 961.4906 | 961.4906 | 6823.41
4.1.22 | 海关查验中心(先行启动区) | 11022 | 363.68 | 51.1505 | 51.1505 | 363.68
4.1.23 | 保税仓库1 | 11707 | 386.18 | 54.315 | 54.315 | 386.18
4.1.24 | 保税仓库2 | 11707 | 386.18 | 54.315 | 54.315 | 386.18
4.1.25 | 保税仓库3 | 11707 | 386.18 | 54.315 | 54.315 | 386.18
4.1.26 | 国际快件中心 | 18327 | 604.76 | 85.0577 | 85.0577 | 604.76
4.1.27 | 国际快件中心 | 11664 | 384.82 | 54.1238 | 54.1238 | 384.82
HGAC-GD03 | 新能源利用 | 商贸物流中心(一期先行启动区)地热泵工程 | 3364 | 473.1364 | 473.1364 | 3364 | 货物 | NCT | 40 | 后审 |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
HGAC-GD04 | 智慧运营系统 | 园区智慧运营系统设备与软件 | 4000 | 562.5879 | 562.5879 | 4000 | 货物 | NCT | 40 | 后审 |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
| 4.2 | 智慧运营平台 | 4000 |  |  | 4000
HGAC-GD05 | 综合信息化平台 | 智慧海关辅助监管平台、应用支撑平台、企业通关服务平台、多式联运平台、园区车辆行人管控设备、园区视频设备、园区办公信息化设备、园区安全 / 能效 /消防设备、数字化月台、数字化仓库、一站式安检区、检疫处理区 | 18818.98 | 2646.8326 | 2646.8326 | 18818.98 | 货物 | ICOT | 40 | 前审 | 是 |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
4.3 | 综合信息化平台 |  | 18818.98 | 2646.8326 | 2646.8326 | 18818.98
4.3.1 | 智慧海关辅助监管平台 |  | 3355 | 471.8706 | 471.8706 | 3355
4.3.2 | 应用支撑平台 |  | 920 | 129.3952 | 129.3952 | 920
4.3.3 | 企业通关服务平台 |  | 3160 | 444.4444 | 444.4444 | 3160
4.3.4 | 多式联运平台 |  | 2100 | 295.3586 | 295.3586 | 2100
4.3.5 | 园区车辆行人管控设备 |  | 341.9 | 48.0872 | 48.0872 | 341.9
4.3.6 | 园区视频设备 |  | 656.15 | 92.2855 | 92.2855 | 656.15
4.3.7 | 园区办公信息化设备 |  | 355.67 | 50.0239 | 50.0239 | 355.67
4.3.8 | 园区安全、能效、消防设备 |  | 211.46 | 29.7412 | 29.7412 | 211.46
4.3.9 | 数字化月台 |  | 33.6 | 4.7257 | 4.7257 | 33.6
4.3.10 | 数字化仓库 |  | 333.3 | 46.8776 | 46.8776 | 333.3
4.3.11 | 一站式安检区 |  | 7000 | 984.5288 | 984.5288 | 7000
4.3.12 | 检疫处理区 |  | 351.9 | 49.4937 | 49.4937 | 351.9
小计 |  |  | 78732.7855 | 11073.5282 | 10600.3918 | 75368.7855
组成部分4: | 能力建设
HGAC-CS01 | 项目管理 | 项目管理技术支持、培训、考察、知识产品开发推广等 | 1000 | 140.647 | 140.647 | 1000 | 咨询服务 | IOCS/QCBS | 51 | 前审 |  | 是 |  | 2024.9 | 2024.10 | 2024.11 | 2028.12
HGAC-CS02 | 项目监测评价 | 外部环境监测、外部移民监测、外部社会和性别监测、项目绩效评估等 | 1000 | 140.647 | 140.647 | 1000 | 咨询服务 | IOCS/QCBS | 51 | 前审 |  | 是 |  | 2024.9 | 2024.10 | 2024.11 | 2028.12
HGAC-CS03 | LEED认证咨询 | 园区建筑LEED认证咨询服务 | 761 | 107.0323 | 107.0323 | 761 | 咨询服务 | IOCS/QCBS | 42 | 前审 |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
HGAC-CS04 | 绿建三星认证咨询 | 园区建筑绿色建筑认证咨询服务 | 116 | 16.315 | 16.315 | 116 | 咨询服务 | NCS/CQS | 42 | 后审 |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
HGAC-CS05 | 其它能力建设服务 | 其它能力建设服务 | 1000 | 140.647 | 140.647 | 1000 | 咨询服务 | IOCS/QCBS | 42 | 前审 |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
小计 |  |  | 3877 | 545.2883 | 545.2883 | 3877
总计 |  |  | 285045.6957 | 40090.8152 | 40090.8152 | 285045.6957
|  | CW土建 | 242748.7602 | 34141.8791
|  | Goods货物 | 38419.9355 | 5403.6477
|  | Consulting Services咨询服务 | 3877 | 545.2883
|  |  | 285045.6957 | 40090.8152
提前采购
|  | CW-09 | 2856.9409
|  | CW-10 | 2812.9395
|  | GD-01 | 761.3988
|  | CS-01 | 140.647
|  | CS-02 | 140.647
6712.5732

## PP_0530-ENG (hidden)
Attachment 1-China: Hubei Global Air Cargo Logistics Hub Project----Procurement Plan (April 2024)
$1 = CNY | AIIB Loan Appraisal Mission MoM
7.11 | 2024-04-12
Contract No. | Contract Name | Description | Cost Estimate |  | % of AIIB Financing |  | Procurement Category | Procurement Method | Contract Duration (Months) | Bank Review (Prior / Post) | 采用招标文件类型 | Advance Contracting | 追溯贷款 | Date of SPN | Bid Openning | Contract Signing | Contract Closing | Notes
|  |  | CNY million | $ million
Component 1: | Customs Operation and Bonded Facilities
HGAC-CW01 | Customs Operation Facilities | (1) Customs Inspection Center T01 (10,911 m2) ; (2) Customs Kiosk & Fence: #2 Customs Kiosk (949 m2), Fence (7,730 m) | 6876.7533 | 967.1946 | 967.1946 | 6876.7533 | Works | NCT | 18 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
1.1 | Bonded Logistics Warehouse (1) | T01 海关查验仓库 | 5931.3338 |  | 0 | 5931.3338 | Works |  |  | Post
1.1.1 | Bonded Logistics Warehouse (2) | 土建工程 | 4137.5599 |  | 0 | 4137.5599 | Works |  |  | Post
1.1.2 | Bonded Logistics Warehouse (3) | 给排水工程 | 13.9661 |  | 0 | 13.9661 | Works |  |  | Post
1.1.3 | Bonded Logistics Warehouse (4) | 电气工程 | 125.6947 |  | 0 | 125.6947 | Works |  |  | Post
1.1.4 | Bonded and Processing Warehouses | 暖通工程 | 97.7626 |  | 0 | 97.7626 | Works |  |  | Post
1.1.5 | Auxiliary Facilities | 消防工程 | 216.4742 |  | 0 | 216.4742 | Works |  |  | Post
1.1.6 |  | 设备工程 | 59.6525 |  | 0 | 59.6525 | Works |  |  | Post
1.1.7 |  | 场平工程 | 218.22 |  | 0 | 218.22 | Works |  |  | Post
1.1.8 |  | 室外工程 | 1024.0038 |  | 0 | 1024.0038 | Works |  |  | Post
1.1.8 |  | 绿建工程 | 38 |  | 0 | 38 | Works |  |  | Post
|  | 废弃物绿色处理 | 1 |  | 0 | 1 | Works |  |  | Post
|  | 雨洪管理设施 | 4 |  | 0 | 4 | Works |  |  | Post
|  | LEED认证增量措施 | 33 |  | 0 | 33 | Works |  |  | Post
1.2 |  | 2#海关卡口 | 481.6195 |  | 0 | 481.6195 | Works |  |  | Post
1.2.1 |  | 地基处理 | 3.3215 |  | 0 | 3.3215 | Works |  |  | Post
1.2.2 |  | 土建工程 | 455.52 |  | 0 | 455.52 | Works |  |  | Post
1.2.3 |  | 给排水工程 | 2.847 |  | 0 | 2.847 | Works |  |  | Post
1.2.4 |  | 暖通工程 | 3.796 |  | 0 | 3.796 | Works |  |  | Post
1.2.5 |  | 电气工程 | 8.541 |  | 0 | 8.541 | Works |  |  | Post
1.2.6 |  | 抗震支架 | 5.694 |  | 0 | 5.694 | Works |  |  | Post
1.2.7 |  | 标识标牌 | 1.9 |  | 0 | 1.9 | Works |  |  | Post
1.4 |  | 海关围网 | 463.8 |  | 0 | 463.8 | Works |  |  | Post
HGAC-CW02 | Bonded Logistics Warehouses (1) | Bonded Logistics Warehoue M01 (20,396 m2) | 13277.6977 | 1867.468 | 1867.468 | 13277.6977 | Works | NCT | 18 | Prior | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.8 | Bonded Logistics Warehouse (2) |  | 13277.6977 | 1867.468 | 1867.468 | 13277.6977 | Works |  |  | Post
2.8.1 | Bonded Logistics Warehouse (3) |  | 9630.4162 | 1354.4889 | 1354.4889 | 9630.4162 | Works |  |  | Post
2.8.2 | Bonded Logistics Warehouse (4) |  | 32.5069 | 4.572 | 4.572 | 32.5069 | Works |  |  | Post
2.8.3 | Bonded Logistics Warehouse (5) |  | 292.5619 | 41.1479 | 41.1479 | 292.5619 | Works |  |  | Post
2.8.4 | Bonded Logistics Warehouse (6) |  | 227.5482 | 32.004 | 32.004 | 227.5482 | Works |  |  | Post
2.8.5 | Bonded Logistics Warehouse (7) |  | 503.8566 | 70.8659 | 70.8659 | 503.8566 | Works |  |  | Post
2.8.6 | Bonded Logistics Warehouse (8) |  | 138.8447 | 19.5281 | 19.5281 | 138.8447 | Works |  |  | Post
2.8.7 | Bonded Logistics Warehouse (9) |  | 507.92 | 71.4374 | 71.4374 | 507.92 | Works |  |  | Post
| Bonded Logistics Warehouse (10) |  | 1881.0431 | 264.563 | 264.563 | 1881.0431 | Works |  |  | Post
2.8.8 | Bonded Logistics Warehouse (11) |  | 63 | 8.8608 | 8.8608 | 63 | Works |  |  | Post
| Bonded Logistics Warehouse (12) |  | 1 | 0.14065 | 0.14065 | 1 | Works |  |  | Post
| Bonded Logistics Warehouse (13) |  | 11 | 1.5471 | 1.5471 | 11 | Works |  |  | Post
| Bonded Logistics Warehouse (14) |  | 51 | 7.173 | 7.173 | 51 | Works |  |  | Post
HGAC-CW03 | Bonded Logistics Warehouses (2) | Bonded Logistics Warehouse J01 / K010, Elevated Platform #3 (42,780 m2) | 25772.9634 | 3624.8894 | 3624.8894 | 25772.9634 | Works | NCT | 18 | Prior | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15 | Bonded Logistics Warehouse (16) |  | 11277.3601 | 1586.1266 | 1586.1266 | 11277.3601 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.1 | Bonded Logistics Warehouse (17) |  | 8671.015 | 1219.552 | 1219.552 | 8671.015 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.2 | Bonded Logistics Warehouse (18) |  | 29.2685 | 4.1165 | 4.1165 | 29.2685 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.3 | Bonded Logistics Warehouse (19) |  | 263.4163 | 37.0487 | 37.0487 | 263.4163 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.4 | Bonded Logistics Warehouse (20) |  | 204.8794 | 28.8157 | 28.8157 | 204.8794 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.5 | Bonded Logistics Warehouse (21) |  | 453.6614 | 63.8061 | 63.8061 | 453.6614 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.6 | Bonded Logistics Warehouse (22) |  | 125.0127 | 17.5827 | 17.5827 | 125.0127 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.7 | Bonded Logistics Warehouse (23) |  | 457.32 | 64.3207 | 64.3207 | 457.32 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (24) |  | 1015.7868 | 142.8673 | 142.8673 | 1015.7868 | Works |  |  | Post
2.15.8 | Bonded Logistics Warehouse (25) |  | 57 | 8.0169 | 8.0169 | 57 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (26) |  | 1 | 0.14065 | 0.14065 | 1 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (27) |  | 9 | 1.2658 | 1.2658 | 9 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (28) |  | 47 | 6.6104 | 6.6104 | 47 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16 | Bonded Logistics Warehouse (29) |  | 11277.3601 | 1586.1266 | 1586.1266 | 11277.3601 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.1 | Bonded Logistics Warehouse (30) |  | 8671.015 | 1219.552 | 1219.552 | 8671.015 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.2 | Bonded Logistics Warehouse (31) |  | 29.2685 | 4.1165 | 4.1165 | 29.2685 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.3 | Bonded Logistics Warehouse (32) |  | 263.4163 | 37.0487 | 37.0487 | 263.4163 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.4 | Bonded Logistics Warehouse (33) |  | 204.8794 | 28.8157 | 28.8157 | 204.8794 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.5 | Bonded Logistics Warehouse (34) |  | 453.6614 | 63.8061 | 63.8061 | 453.6614 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.6 | Bonded Logistics Warehouse (35) |  | 125.0127 | 17.5827 | 17.5827 | 125.0127 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.7 | Bonded Logistics Warehouse (36) |  | 457.32 | 64.3207 | 64.3207 | 457.32 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (37) |  | 1015.7868 | 142.8673 | 142.8673 | 1015.7868 | Works |  |  | Post
2.16.8 | Bonded Logistics Warehouse (38) |  | 57 | 8.0169 | 8.0169 | 57 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (39) |  | 1 | 0.14065 | 0.14065 | 1 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (40) |  | 9 | 1.2658 | 1.2658 | 9 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (41) |  | 47 | 6.6104 | 6.6104 | 47 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.18 | Bonded Logistics Warehouse (42) |  | 4178.7488 | 587.7284 | 587.7284 | 4178.7488 | Works |  |  | Post
2.18.1 | Bonded Logistics Warehouse (43) |  | 4053.3863 | 570.0965 | 570.0965 | 4053.3863 | Works |  |  | Post
2.18.2 | Bonded Logistics Warehouse (44) |  | 125.3625 | 17.6319 | 17.6319 | 125.3625 | Works |  |  | Post
HGAC-CW04 | Bonded Logistics Warehouses (3) | Bonded Logistics Warehouse H01 / H02 / E05 and Elevated Platform #2 (121,805 m2) | 54208.0131 | 7624.1931 | 7624.1931 | 54208.0131 | Works | IOCT | 18 | Prior | 是 |  |  | 2027.3 | 2027.4 | 2027.5 | 2028.12
2.1 | Bonded Logistics Warehouse (46) |  | 15502.4051 | 2180.3664 | 2180.3664 | 15502.4051 | Works |  |  | Post
2.10.1 | Bonded Logistics Warehouse (47) |  | 12124.8594 | 1705.3248 | 1705.3248 | 12124.8594 | Works |  |  | Post
2.10.2 | Bonded Logistics Warehouse (48) |  | 40.9267 | 5.7562 | 5.7562 | 40.9267 | Works |  |  | Post
2.10.3 | Bonded Logistics Warehouse (49) |  | 368.3405 | 51.806 | 51.806 | 368.3405 | Works |  |  | Post
2.10.4 | Bonded Logistics Warehouse (50) |  | 286.487 | 40.2935 | 40.2935 | 286.487 | Works |  |  | Post
2.10.5 | Bonded Logistics Warehouse (51) |  | 634.3642 | 89.2214 | 89.2214 | 634.3642 | Works |  |  | Post
2.10.6 | Bonded Logistics Warehouse (52) |  | 174.8079 | 24.5862 | 24.5862 | 174.8079 | Works |  |  | Post
2.10.7 | Bonded Logistics Warehouse (53) |  | 639.48 | 89.9409 | 89.9409 | 639.48 | Works |  |  | Post
| Bonded Logistics Warehouse (54) |  | 1161.1395 | 163.3108 | 163.3108 | 1161.1395 | Works |  |  | Post
2.10.8 | Bonded Logistics Warehouse (55) |  | 72 | 10.1266 | 10.1266 | 72 | Works |  |  | Post
| Bonded Logistics Warehouse (56) |  | 1 | 0.14065 | 0.14065 | 1 | Works |  |  | Post
| Bonded Logistics Warehouse (57) |  | 13 | 1.8284 | 1.8284 | 13 | Works |  |  | Post
| Bonded Logistics Warehouse (58) |  | 58 | 8.1575 | 8.1575 | 58 | Works |  |  | Post
2.11 | Bonded Logistics Warehouse (59) |  | 15296.8552 | 2151.4564 | 2151.4564 | 15296.8552 | Works |  |  | Post
2.11.1 | Bonded Logistics Warehouse (60) |  | 12124.8594 | 1705.3248 | 1705.3248 | 12124.8594 | Works |  |  | Post
2.11.2 | Bonded Logistics Warehouse (61) |  | 40.9267 | 5.7562 | 5.7562 | 40.9267 | Works |  |  | Post
2.11.3 | Bonded Logistics Warehouse (62) |  | 368.3405 | 51.806 | 51.806 | 368.3405 | Works |  |  | Post
2.11.4 | Bonded Logistics Warehouse (63) |  | 286.487 | 40.2935 | 40.2935 | 286.487 | Works |  |  | Post
2.11.5 | Bonded Logistics Warehouse (64) |  | 634.3642 | 89.2214 | 89.2214 | 634.3642 | Works |  |  | Post
2.11.6 | Bonded Logistics Warehouse (65) |  | 174.8079 | 24.5862 | 24.5862 | 174.8079 | Works |  |  | Post
2.11.7 | Bonded Logistics Warehouse (66) |  | 639.48 | 89.9409 | 89.9409 | 639.48 | Works |  |  | Post
| Bonded Logistics Warehouse (67) |  | 955.5896 | 134.4008 | 134.4008 | 955.5896 | Works |  |  | Post
2.11.8 | Bonded Logistics Warehouse (68) |  | 72 | 10.1266 | 10.1266 | 72 | Works |  |  | Post
| Bonded Logistics Warehouse (69) |  | 1 | 0.14065 | 0.14065 | 1 | Works |  |  | Post
| Bonded Logistics Warehouse (70) |  | 13 | 1.8284 | 1.8284 | 13 | Works |  |  | Post
| Bonded Logistics Warehouse (71) |  | 58 | 8.1575 | 8.1575 | 58 | Works |  |  | Post
2.9 | Bonded Logistics Warehouse (72) |  | 13789.8727 | 1939.5039 | 1939.5039 | 13789.8727 | Works |  |  | Post
2.9.1 | Bonded Logistics Warehouse (73) |  | 10541.2786 | 1482.599 | 1482.599 | 10541.2786 | Works |  |  | Post
2.9.2 | Bonded Logistics Warehouse (74) |  | 35.5814 | 5.0044 | 5.0044 | 35.5814 | Works |  |  | Post
2.9.3 | Bonded Logistics Warehouse (75) |  | 320.233 | 45.0398 | 45.0398 | 320.233 | Works |  |  | Post
2.9.4 | Bonded Logistics Warehouse (76) |  | 249.0701 | 35.031 | 35.031 | 249.0701 | Works |  |  | Post
2.9.5 | Bonded Logistics Warehouse (77) |  | 551.5123 | 77.5685 | 77.5685 | 551.5123 | Works |  |  | Post
2.9.6 | Bonded Logistics Warehouse (78) |  | 151.9769 | 21.3751 | 21.3751 | 151.9769 | Works |  |  | Post
2.9.7 | Bonded Logistics Warehouse (79) |  | 555.96 | 78.1941 | 78.1941 | 555.96 | Works |  |  | Post
| Bonded Logistics Warehouse (80) |  | 1319.2604 | 185.55 | 185.55 | 1319.2604 | Works |  |  | Post
2.9.8 | Bonded Logistics Warehouse (81) |  | 65 | 9.1421 | 9.1421 | 65 | Works |  |  | Post
| Bonded Logistics Warehouse (82) |  | 1 | 0.14065 | 0.14065 | 1 | Works |  |  | Post
| Bonded Logistics Warehouse (83) |  | 11 | 1.5471 | 1.5471 | 11 | Works |  |  | Post
| Bonded Logistics Warehouse (84) |  | 53 | 7.4543 | 7.4543 | 53 | Works |  |  | Post
2.17 | Bonded Logistics Warehouse (85) |  | 9618.88 | 1352.8664 | 1352.8664 | 9618.88 | Works |  |  | Post
2.17.1 | Bonded Logistics Warehouse (86) |  | 9330.3136 | 1312.2804 | 1312.2804 | 9330.3136 | Works |  |  | Post
2.17.2 | Bonded Logistics Warehouse (87) |  | 288.5664 | 40.586 | 40.586 | 288.5664 | Works |  |  | Post
HGAC-CW05 | Bonded Logistics Warehouses (4) | Bonded Logistics Warehouse H03 / H04 / L01 (100,098 m2) | 47558.926 | 6689.0191 | 6689.0191 | 47558.926 | Works | IOCT | 18 | Prior | 是 |  |  | 2027.3 | 2027.4 | 2027.5 | 2028.12
2.12 | H03 物流仓库 |  | 15098.9985 | 2123.6285 | 2123.6285 | 15098.9985 | Works |  |  | Post
2.12.1 | 土建工程 |  | 12124.8594 | 1705.3248 | 1705.3248 | 12124.8594 | Works |  |  | Post
2.12.2 | 给排水工程 |  | 40.9267 | 5.7562 | 5.7562 | 40.9267 | Works |  |  | Post
2.12.3 | 电气工程 |  | 368.3405 | 51.806 | 51.806 | 368.3405 | Works |  |  | Post
2.12.4 | 暖通工程 |  | 286.487 | 40.2935 | 40.2935 | 286.487 | Works |  |  | Post
2.12.5 | 消防工程 |  | 634.3642 | 89.2214 | 89.2214 | 634.3642 | Works |  |  | Post
2.12.6 | 设备工程 |  | 174.8079 | 24.5862 | 24.5862 | 174.8079 | Works |  |  | Post
2.12.7 | 场平工程 |  | 639.48 | 89.9409 | 89.9409 | 639.48 | Works |  |  | Post
| 室外工程 |  | 757.7328 | 106.5728 | 106.5728 | 757.7328 | Works |  |  | Post
2.12.8 | 绿建工程 |  | 72 | 10.1266 | 10.1266 | 72 | Works |  |  | Post
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 | Works |  |  | Post
| 雨洪管理设施 |  | 13 | 1.8284 | 1.8284 | 13 | Works |  |  | Post
| LEED认证增量措施 |  | 58 | 8.1575 | 8.1575 | 58 | Works |  |  | Post
2.13 | H04 物流仓库 |  | 15276.6249 | 2148.6111 | 2148.6111 | 15276.6249 | Works |  |  | Post
2.13.1 | 土建工程 |  | 12124.8594 | 1705.3248 | 1705.3248 | 12124.8594 | Works |  |  | Post
2.13.2 | 给排水工程 |  | 40.9267 | 5.7562 | 5.7562 | 40.9267 | Works |  |  | Post
2.13.3 | 电气工程 |  | 368.3405 | 51.806 | 51.806 | 368.3405 | Works |  |  | Post
2.13.4 | 暖通工程 |  | 286.487 | 40.2935 | 40.2935 | 286.487 | Works |  |  | Post
2.13.5 | 消防工程 |  | 634.3642 | 89.2214 | 89.2214 | 634.3642 | Works |  |  | Post
2.13.6 | 设备工程 |  | 174.8079 | 24.5862 | 24.5862 | 174.8079 | Works |  |  | Post
2.13.7 | 场平工程 |  | 639.48 | 89.9409 | 89.9409 | 639.48 | Works |  |  | Post
| 室外工程 |  | 935.3592 | 131.5554 | 131.5554 | 935.3592 | Works |  |  | Post
2.13.8 | 绿建工程 |  | 72 | 10.1266 | 10.1266 | 72 | Works |  |  | Post
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 | Works |  |  | Post
| 雨洪管理设施 |  | 13 | 1.8284 | 1.8284 | 13 | Works |  |  | Post
| LEED认证增量措施 |  | 58 | 8.1575 | 8.1575 | 58 | Works |  |  | Post
2.14 | L01 物流仓库 |  | 17183.3027 | 2416.7796 | 2416.7796 | 17183.3027 | Works |  |  | Post
2.14.1 | 土建工程 |  | 13708.4402 | 1928.0507 | 1928.0507 | 13708.4402 | Works |  |  | Post
2.14.2 | 给排水工程 |  | 46.272 | 6.508 | 6.508 | 46.272 | Works |  |  | Post
2.14.3 | 电气工程 |  | 416.448 | 58.5722 | 58.5722 | 416.448 | Works |  |  | Post
2.14.4 | 暖通工程 |  | 323.904 | 45.5561 | 45.5561 | 323.904 | Works |  |  | Post
2.14.5 | 消防工程 |  | 717.216 | 100.8743 | 100.8743 | 717.216 | Works |  |  | Post
2.14.6 | 设备工程 |  | 197.6389 | 27.7973 | 27.7973 | 197.6389 | Works |  |  | Post
2.14.7 | 场平工程 |  | 723 | 101.6878 | 101.6878 | 723 | Works |  |  | Post
| 室外工程 |  | 972.3836 | 136.7628 | 136.7628 | 972.3836 | Works |  |  | Post
2.14.8 | 绿建工程 |  | 78 | 10.9705 | 10.9705 | 78 | Works |  |  | Post
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 | Works |  |  | Post
| 雨洪管理设施 |  | 14 | 1.9691 | 1.9691 | 14 | Works |  |  | Post
| LEED认证增量措施 |  | 63 | 8.8608 | 8.8608 | 63 | Works |  |  | Post
HGAC-CW06 | Bonded Processing Warehouses | Bonded Processing Warehouse E01 / E02 / E03 / E04 (57,184 m2) | 23398.367 | 3290.9096 | 3290.9096 | 23398.367 | Works | NCT | 18 | Prior | 是 |  |  | 2026.3 | 2026.4 | 2026.5 | 2027.12
2.4 | E01 物流仓库 |  | 5921.3919 | 832.8259 | 832.8259 | 5921.3919 | Works |  |  | Post
2.4.1 | 土建工程 |  | 3574 | 502.6723 | 502.6723 | 3574 | Works |  |  | Post
2.4.2 | 给排水工程 |  | 18.2989 | 2.5737 | 2.5737 | 18.2989 | Works |  |  | Post
2.4.3 | 电气工程 |  | 164.6899 | 23.1631 | 23.1631 | 164.6899 | Works |  |  | Post
2.4.4 | 暖通工程 |  | 128.0922 | 18.0158 | 18.0158 | 128.0922 | Works |  |  | Post
2.4.5 | 消防工程 |  | 283.6326 | 39.8921 | 39.8921 | 283.6326 | Works |  |  | Post
2.4.6 | 设备工程 |  | 78.1589 | 10.9928 | 10.9928 | 78.1589 | Works |  |  | Post
2.4.7 | 场平工程 |  | 571.84 | 80.4276 | 80.4276 | 571.84 | Works |  |  | Post
| 室外工程 |  | 1036.6793 | 145.8058 | 145.8058 | 1036.6793 | Works |  |  | Post
2.4.8 | 绿建工程 |  | 66 | 9.2827 | 9.2827 | 66 | Works |  |  | Post
| 废弃物绿色处理 |  | 2 | 0.28129 | 0.28129 | 2 | Works |  |  | Post
| 雨洪管理设施 |  | 11 | 1.5471 | 1.5471 | 11 | Works |  |  | Post
| LEED认证增量措施 |  | 53 | 7.4543 | 7.4543 | 53 | Works |  |  | Post
2.5 | E02 物流仓库 |  | 5952.1709 | 837.1548 | 837.1548 | 5952.1709 | Works |  |  | Post
2.5.1 | 土建工程 |  | 3574 | 502.6723 | 502.6723 | 3574 | Works |  |  | Post
2.5.2 | 给排水工程 |  | 18.2989 | 2.5737 | 2.5737 | 18.2989 | Works |  |  | Post
2.5.3 | 电气工程 |  | 164.6899 | 23.1631 | 23.1631 | 164.6899 | Works |  |  | Post
2.5.4 | 暖通工程 |  | 128.0922 | 18.0158 | 18.0158 | 128.0922 | Works |  |  | Post
2.5.5 | 消防工程 |  | 283.6326 | 39.8921 | 39.8921 | 283.6326 | Works |  |  | Post
2.5.6 | 设备工程 |  | 78.1589 | 10.9928 | 10.9928 | 78.1589 | Works |  |  | Post
2.5.7 | 场平工程 |  | 571.84 | 80.4276 | 80.4276 | 571.84 | Works |  |  | Post
| 室外工程 |  | 1068.4583 | 150.2754 | 150.2754 | 1068.4583 | Works |  |  | Post
2.5.8 | 绿建工程 |  | 65 | 9.1421 | 9.1421 | 65 | Works |  |  | Post
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 | Works |  |  | Post
| 雨洪管理设施 |  | 11 | 1.5471 | 1.5471 | 11 | Works |  |  | Post
| LEED认证增量措施 |  | 53 | 7.4543 | 7.4543 | 53 | Works |  |  | Post
2.6 | E03 物流仓库 |  | 5747.9617 | 808.4334 | 808.4334 | 5747.9617 | Works |  |  | Post
2.6.1 | 土建工程 |  | 3574 | 502.6723 | 502.6723 | 3574 | Works |  |  | Post
2.6.2 | 给排水工程 |  | 18.2989 | 2.5737 | 2.5737 | 18.2989 | Works |  |  | Post
2.6.3 | 电气工程 |  | 164.6899 | 23.1631 | 23.1631 | 164.6899 | Works |  |  | Post
2.6.4 | 暖通工程 |  | 128.0922 | 18.0158 | 18.0158 | 128.0922 | Works |  |  | Post
2.6.5 | 消防工程 |  | 283.6326 | 39.8921 | 39.8921 | 283.6326 | Works |  |  | Post
2.6.6 | 设备工程 |  | 78.1589 | 10.9928 | 10.9928 | 78.1589 | Works |  |  | Post
2.6.7 | 场平工程 |  | 571.84 | 80.4276 | 80.4276 | 571.84 | Works |  |  | Post
| 室外工程 |  | 864.2492 | 121.554 | 121.554 | 864.2492 | Works |  |  | Post
2.6.8 | 绿建工程 |  | 65 | 9.1421 | 9.1421 | 65 | Works |  |  | Post
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 | Works |  |  | Post
| 雨洪管理设施 |  | 11 | 1.5471 | 1.5471 | 11 | Works |  |  | Post
| LEED认证增量措施 |  | 53 | 7.4543 | 7.4543 | 53 | Works |  |  | Post
2.7 | E04 物流仓库 |  | 5776.8425 | 812.4954 | 812.4954 | 5776.8425 | Works |  |  | Post
2.7.1 | 土建工程 |  | 3574 | 502.6723 | 502.6723 | 3574 | Works |  |  | Post
2.7.2 | 给排水工程 |  | 18.2989 | 2.5737 | 2.5737 | 18.2989 | Works |  |  | Post
2.7.3 | 电气工程 |  | 164.6899 | 23.1631 | 23.1631 | 164.6899 | Works |  |  | Post
2.7.4 | 暖通工程 |  | 128.0922 | 18.0158 | 18.0158 | 128.0922 | Works |  |  | Post
2.7.5 | 消防工程 |  | 283.6326 | 39.8921 | 39.8921 | 283.6326 | Works |  |  | Post
2.7.6 | 设备工程 |  | 78.1589 | 10.9928 | 10.9928 | 78.1589 | Works |  |  | Post
2.7.7 | 场平工程 |  | 571.84 | 80.4276 | 80.4276 | 571.84 | Works |  |  | Post
| 室外工程 |  | 893.13 | 125.616 | 125.616 | 893.13 | Works |  |  | Post
2.7.8 | 绿建工程 |  | 65 | 9.1421 | 9.1421 | 65 | Works |  |  | Post
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 | Works |  |  | Post
| 雨洪管理设施 |  | 11 | 1.5471 | 1.5471 | 11 | Works |  |  | Post
| LEED认证增量措施 |  | 53 | 7.4543 | 7.4543 | 53 | Works |  |  | Post
HGAC-CW07 | Auxiliary Facilities | Contrainer Truck Ramp #3 / #4 / #5, Guard Station, Equipment Room | 3292.1052 | 463.0246 | 463.0246 | 3292.1052 | Works | NCT | 12 | Prior |  |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.5
Total |  |  | 174384.8256 | 967.1946 | 967.1946 | 174384.8256
Component 2: | Trade and Freight Service Facilities
HGAC-CW08 | Trade and Freight Service Facilities | (1) Duty-Free Service Center S01 (10,450 m2); (2) Comprehensive Office Building W01 (39,432 m2) | 28051.0846 | 3945.3002 | 3945.3002 | 28051.0846 | Works | NCT | 18 | Prior | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
3.2 | S01 免税服务中心 |  | 8098.2373 | 1138.9926 | 1138.9926 | 8098.2373
3.2.1 | 土建工程 |  | 4284.5 | 602.602 | 602.602 | 4284.5
3.2.2 | 给排水工程 |  | 26.125 | 3.6744 | 3.6744 | 26.125
3.2.3 | 电气工程 |  | 151.525 | 21.3115 | 21.3115 | 151.525
3.2.4 | 暖通工程 |  | 120.175 | 16.9023 | 16.9023 | 120.175
3.2.5 | 消防工程 |  | 146.3 | 20.5767 | 20.5767 | 146.3
3.2.6 | 设备工程 |  | 41.8 | 5.879 | 5.879 | 41.8
3.2.7 | 场平工程 |  | 209 | 29.3952 | 29.3952 | 209
| 室外工程 |  | 2754.8123 | 387.456 | 387.456 | 2754.8123
3.2.8 | 绿建工程 |  | 364 | 51.1955 | 51.1955 | 364
| 其他可再生能源措施 |  | 289 | 40.647 | 40.647 | 289
| 废弃物绿色处理 |  | 4 | 0.56259 | 0.56259 | 4
| 雨洪管理设施 |  | 4 | 0.56259 | 0.56259 | 4
| LEED认证增量措施 |  | 32 | 4.5007 | 4.5007 | 32
| 绿建三星增量措施 |  | 35 | 4.9226 | 4.9226 | 35
3.1 | W01 综合办公楼 |  | 19952.8472 | 2806.3076 | 2806.3076 | 19952.8472
3.1.1 | 土建工程 |  | 14787.06 | 2079.7553 | 2079.7553 | 14787.06
3.1.2 | 给排水工程 |  | 98.5804 | 13.865 | 13.865 | 98.5804
3.1.3 | 电气工程 |  | 571.7663 | 80.4172 | 80.4172 | 571.7663
3.1.4 | 暖通工程 |  | 453.4698 | 63.7792 | 63.7792 | 453.4698
3.1.5 | 消防工程 |  | 552.0502 | 77.6442 | 77.6442 | 552.0502
3.1.6 | 设备工程 |  | 157.7286 | 22.1841 | 22.1841 | 157.7286
3.1.7 | 场平工程 |  | 788.6432 | 110.9203 | 110.9203 | 788.6432
| 室外工程 |  | 2458.5486 | 345.7874 | 345.7874 | 2458.5486
3.1.8 | 绿建工程 |  | 85 | 11.955 | 11.955 | 85
| 废弃物绿色处理 |  | 4 | 0.56259 | 0.56259 | 4
| 雨洪管理设施 |  | 15 | 2.1097 | 2.1097 | 15
| LEED认证增量措施 |  | 66 | 9.2827 | 9.2827 | 66
Total |  |  | 28051.0846 | 3945.3002 | 3945.3002 | 28051.0846
Component 3: | Low-Carbon, Smart and Supporting Utilities
HGAC-CW09 | Roads | (1) Elevated Connecting Bridge #1 (Roadbed Area = 2,667 m2) / #2 (Roadbed Area = 2,375 m2); (2) 4 Roads in Phase II Area (Guihua Road No. 2 = 581.6 m / Guihua Road No. 3 = 990 m / Guihua Road No. 4 = 1,075 m / Guihua Road No. 5 = 354 m), and associated infrastructures | 20312.85 | 2856.9409 | 2856.9409 | 20312.85 | Works | NCT | 12 | Prior | 是 | Yes |  | 2024.9 | 2024.10 | 2024.11 | 2025.11 | 1st Works Contract
6 | 配套设施 |  | 2688.05 | 378.0661 | 378.0661 | 2688.05 |  |  |  | 前审 |  | Yes
6.1 | 1#高架联络道 |  | 399.45 | 56.1814 | 56.1814 | 399.45 |  |  |  | 前审 |  | Yes
6.1.1 | 路基 |  | 2145.6 | 301.7722 | 301.7722 | 2145.6 |  |  |  | 前审 |  | Yes
6.1.2 | 钢箱梁 |  | 143 | 20.1125 | 20.1125 | 143 |  |  |  | 前审 |  | Yes
6.1.3 | 装饰棚 |  | 6521.05 | 917.166 | 917.166 | 6521.05 |  |  |  | 前审 |  | Yes
6.2 | 2#高架联络道 |  | 6521.05 | 917.166 | 917.166 | 6521.05 |  |  |  | 前审 |  | Yes
6.2.1 | 路基 |  | 356.25 | 50.1055 | 50.1055 | 356.25 |  |  |  | 前审 |  | Yes
6.2.3 | 钢箱梁 |  | 5956.8 | 837.8059 | 837.8059 | 5956.8 |  |  |  | 前审 |  | Yes
6.2.4 | 装饰棚 |  | 208 | 29.2546 | 29.2546 | 208 |  |  |  | 前审 |  | Yes
6.3 | 规划二路 |  | 1959.93 | 275.6582 | 275.6582 | 1959.93 |  |  |  | 前审 |  | Yes
6.3.1 | 路基 |  | 1959.93 | 275.6582 | 275.6582 | 1959.93 |  |  |  | 前审 |  | Yes
6.4 | 规划三路 |  | 3742.2 | 526.3291 | 526.3291 | 3742.2 |  |  |  | 前审 |  | Yes
6.4.1 | 路基 |  | 3742.2 | 526.3291 | 526.3291 | 3742.2 |  |  |  | 前审 |  | Yes
6.5 | 规划四路 |  | 4063.5 | 571.519 | 571.519 | 4063.5 |  |  |  | 前审 |  | Yes
6.5.1 | 路基 |  | 4063.5 | 571.519 | 571.519 | 4063.5 |  |  |  | 前审 |  | Yes
6.6 | 规划五路 |  | 1338.12 | 188.2025 | 188.2025 | 1338.12 |  |  |  | 前审 |  | Yes
6.6.1 | 路基 |  | 1338.12 | 188.2025 | 188.2025 | 1338.12 |  |  |  | 前审 |  | Yes
HGAC-CW10 | Earth Works | Earth Works for Phase II | 20000 | 2812.9395 | 2812.9395 | 20000 | Works | NCT | 12 | Prior |  | Yes |  | 2024.9 | 2024.10 | 2024.11 | 2025.11
HGAC-GD01 | Roof-Top Photovolviac (1) | (1) Roof-Top Volvtaic for Phase II buildings including Customs Inspection Center (Phase I), International Express Center #1 / #2, Bonded Logistics Center (Type B) #1 / #2 / #3 and International Cargo Terminal, totalling 76,134 m2；(2) Phase II buildings including Bonded Logistics Warehouse P01 / R01 / R02 and Bonded Processing Warehouse Q01 / Q02, totalling 87,936 m2. (1) + (2) = 164,070 m2 | 5413.5455 | 761.3988 | 761.3988 | 5413.5455 | Goods | NCT | 12 | Prior | 是 | Yes |  | 2024.9 | 2024.10 | 2024.11 | 2025.11 | 1st Goods Contract
4.1.22 | 海关查验中心 | 11022 | 363.6765 | 51.15 | 363.6765 | 51.15
4.1.23 | 保税仓库1 | 11707 | 386.1825 | 54.3154 | 386.1825 | 54.3154
4.1.24 | 保税仓库2 | 11707 | 386.1825 | 54.3154 | 386.1825 | 54.3154
4.1.25 | 保税仓库3 | 11707 | 386.1825 | 54.3154 | 386.1825 | 54.3154
4.1.26 | 国际快件中心 | 18327 | 604.7635 | 85.0582 | 604.7635 | 85.0582
4.1.27 | 快件中心 | 11664 | 384.8185 | 54.1236 | 384.8185 | 54.1236
4.1.16 | P001 | 16128 | 532.1305 | 74.8425 | 532.1305 | 74.8425
4.1.17 | Q001 | 18768 | 619.256 | 87.0965 | 619.256 | 87.0965
4.1.18 | Q002 | 18768 | 619.256 | 87.0965 | 619.256 | 87.0965
4.1.19 | R001 | 17136 | 565.5485 | 79.5427 | 565.5485 | 79.5427
4.1.20 | R002 | 17136 | 565.5485 | 79.5427 | 565.5485 | 79.5427
HGAC-GD02 | Roof-Top Photovolviac (2) | All buildings in Phase II including Duty-Free Service Center S01, Comprehensive Office Building W01, Customs Inspection Warehouse T01, Bonded Logistics Warehouse E01~E04 / H01~H04 / J01 / K01 / L01 / M01, totalling 196,714 m2 | 6823.41 | 959.692 | 959.692 | 6823.41 | Goods | NCT | 40 | Post |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
4.1 | 光伏 | 370864.11m2 | 12236.96 | 1721.0914 | 1721.0914 | 12236.96 | Goods |  |  | Post
| 亚投行资金建设北区 | 196714.11 | 6823.4145 | 959.6926 | 959.6926 | 6823.4145 | Goods |  |  | Post
4.1.1 | 免税服务中心S01 | 5226.66 | 172.3755 | 24.2441 | 24.2441 | 172.3755 | Goods |  |  | Post
4.1.2 | 综合业务楼W01 | 4929.02 | 162.657 | 22.8772 | 22.8772 | 162.657 | Goods |  |  | Post
4.1.3 | E001 | 13104 | 432.388 | 60.8141 | 60.8141 | 432.388 | Goods |  |  | Post
4.1.4 | E002 | 13104 | 432.388 | 60.8141 | 60.8141 | 432.388 | Goods |  |  | Post
4.1.5 | E003 | 13104 | 432.388 | 60.8141 | 60.8141 | 432.388 | Goods |  |  | Post
4.1.6 | E004 | 13104 | 432.388 | 60.8141 | 60.8141 | 432.388 | Goods |  |  | Post
4.1.7 | E005 | 13104 | 432.388 | 60.8141 | 60.8141 | 432.388 | Goods |  |  | Post
4.1.8 | H001 | 15120 | 498.883 | 70.1664 | 70.1664 | 498.883 | Goods |  |  | Post
4.1.9 | H002 | 15120 | 498.883 | 70.1664 | 70.1664 | 498.883 | Goods |  |  | Post
4.1.10 | H003 | 15120 | 498.883 | 70.1664 | 70.1664 | 498.883 | Goods |  |  | Post
4.1.11 | H004 | 15120 | 498.883 | 70.1664 | 70.1664 | 498.883 | Goods |  |  | Post
4.1.12 | J001 | 10800 | 356.345 | 50.1188 | 50.1188 | 356.345 | Goods |  |  | Post
4.1.13 | K001 | 9360 | 308.7755 | 43.4283 | 43.4283 | 308.7755 | Goods |  |  | Post
4.1.14 | L001 | 17136 | 565.5485 | 79.5427 | 79.5427 | 565.5485 | Goods |  |  | Post
4.1.15 | M001 | 23262.43 | 767.591 | 107.9594 | 107.9594 | 767.591 | Goods |  |  | Post
4.1.21 | T001(海关查验仓库) | 10080 | 332.65 | 46.7862 | 46.7862 | 332.65 | Goods |  |  | Post
| 自建南区 | 87936 | 2901.75 | 408.1224 | 408.1224 | 2901.75 | Goods |  |  | Post
4.1.16 | P001(自建南区) | 16128 | 532.13 | 74.8425 | 74.8425 | 532.13 | Goods |  |  | Post
4.1.17 | Q001(自建南区) | 18768 | 619.26 | 87.097 | 87.097 | 619.26 | Goods |  |  | Post
4.1.18 | Q002(自建南区) | 18768 | 619.26 | 87.097 | 87.097 | 619.26 | Goods |  |  | Post
4.1.19 | R001(自建南区) | 17136 | 565.55 | 79.5429 | 79.5429 | 565.55 | Goods |  |  | Post
4.1.20 | R002(自建南区) | 17136 | 565.55 | 79.5429 | 79.5429 | 565.55 | Goods |  |  | Post
| 先行启动区 | 86214 | 2844.45 | 961.4906 | 961.4906 | 6823.41 | Goods |  |  | Post
4.1.22 | 海关查验中心(先行启动区) | 11022 | 363.68 | 51.1505 | 51.1505 | 363.68 | Goods |  |  | Post
4.1.23 | 保税仓库1 | 11707 | 386.18 | 54.315 | 54.315 | 386.18 | Goods |  |  | Post
4.1.24 | 保税仓库2 | 11707 | 386.18 | 54.315 | 54.315 | 386.18 | Goods |  |  | Post
4.1.25 | 保税仓库3 | 11707 | 386.18 | 54.315 | 54.315 | 386.18 | Goods |  |  | Post
4.1.26 | 国际快件中心 | 18327 | 604.76 | 85.0577 | 85.0577 | 604.76 | Goods |  |  | Post
4.1.27 | 国际快件中心 | 11664 | 384.82 | 54.1238 | 54.1238 | 384.82 | Goods |  |  | Post
HGAC-GD03 | Geothermal Energy for Business Logistics Center | Geothermal Energy for Business Logistics Center (Phase I) | 3364 | 473.1364 | 473.1364 | 3364 | Goods | NCT | 40 | Post |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
HGAC-GD04 | Smart Operations System | Hardware and Software for Smart Operations System | 4000 | 562.5879 | 562.5879 | 4000 | Goods | NCT | 40 | Post |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
| 4.2 | 智慧运营平台 | 4000 |  |  | 4000 | Goods |  |  | Post
HGAC-GD05 | Integrated Information System | Smart Customs Auxiliary Supervision Platform, Application Suppory Platform, Enterprise Customs Clearance Service Platform, Multi-Modal Transport Platform, Vehicle-Pedestrian Supervision and Control Equipment, Video Surveillance Equipment, Office Information Equipment, Safety / Energy Efficiency Monitoring / Firefighting Euipment, Digital Platform, Digital Warehouse, One-Stop Safety Inspection Area, Quanrantine Processing Area | 18818.98 | 2646.8326 | 2646.8326 | 18818.98 | Goods | ICOT | 40 | Prior | 是 |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
4.3 | 综合信息化平台 |  | 18818.98 | 2646.8326 | 2646.8326 | 18818.98
4.3.1 | 智慧海关辅助监管平台 |  | 3355 | 471.8706 | 471.8706 | 3355
4.3.2 | 应用支撑平台 |  | 920 | 129.3952 | 129.3952 | 920
4.3.3 | 企业通关服务平台 |  | 3160 | 444.4444 | 444.4444 | 3160
4.3.4 | 多式联运平台 |  | 2100 | 295.3586 | 295.3586 | 2100
4.3.5 | 园区车辆行人管控设备 |  | 341.9 | 48.0872 | 48.0872 | 341.9
4.3.6 | 园区视频设备 |  | 656.15 | 92.2855 | 92.2855 | 656.15
4.3.7 | 园区办公信息化设备 |  | 355.67 | 50.0239 | 50.0239 | 355.67
4.3.8 | 园区安全、能效、消防设备 |  | 211.46 | 29.7412 | 29.7412 | 211.46
4.3.9 | 数字化月台 |  | 33.6 | 4.7257 | 4.7257 | 33.6
4.3.10 | 数字化仓库 |  | 333.3 | 46.8776 | 46.8776 | 333.3
4.3.11 | 一站式安检区 |  | 7000 | 984.5288 | 984.5288 | 7000
4.3.12 | 检疫处理区 |  | 351.9 | 49.4937 | 49.4937 | 351.9
Total |  |  | 78732.7855 | 11073.5282 | 10600.3918 | 75368.7855
Component 4: | Capacity Building
HGAC-CS01 | Project Management | Project management technical support, training, study tours, knowledge product development and dissemination | 1000 | 140.647 | 140.647 | 1000 | Consulting Services | IOCS/QCBS | 51 | Prior |  | Yes |  | 2024.9 | 2024.10 | 2024.11 | 2028.12
HGAC-CS02 | Project M&E | External environmental monitoring, external resettlement monitoring, external social / gender monitoring, project performance monitoring, etc. | 1000 | 140.647 | 140.647 | 1000 | Consulting Services | IOCS/QCBS | 51 | Prior |  | Yes |  | 2024.9 | 2024.10 | 2024.11 | 2028.12
HGAC-CS03 | LEED Certification | LEED certification consulting services | 761 | 107.0323 | 107.0323 | 761 | Consulting Services | IOCS/QCBS | 42 | Prior |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
HGAC-CS04 | Green Building Certification | Green building certifcation consulting services | 116 | 16.315 | 16.315 | 116 | Consulting Services | NCS/CQS | 42 | Post |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
HGAC-CS05 | Other Consulting Services | Other capacity building consulting services | 1000 | 140.647 | 140.647 | 1000 | Consulting Services | IOCS/QCBS | 42 | Prior |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
Total |  |  | 3877 | 545.2883 | 545.2883 | 3877
GRAND TOTAL |  |  | 285045.6957 | 40090.8152 | 40090.8152 | 285045.6957
|  | CW土建 | 242748.7602 | 34141.8791
|  | Goods货物 | 38419.9355 | 5403.6477
|  | Consulting Services咨询服务 | 3877 | 545.2883
|  |  | 285045.6957 | 40090.8152
提前采购
|  | CW-09 | 2856.9409
|  | CW-10 | 2812.9395
|  | GD-01 | 761.3988
|  | CS-01 | 140.647
|  | CS-02 | 140.647
6712.5732

## 时间表_1225-CHN (hidden)
湖北国际航空货运物流园项目采购时间表 (2024年12月更新)
序号 | 合同号 | 采购内容 | 项目实施单位 | 成本估算 |  | 亚投行 贷款 |  | 采购 类别 | 采购 方式 | 审查 方式 | 公告日期 | 合同 签订日期 | 合同 月数 | 提前 采购 | 合同 期(月) | 2024 |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
|  |  |  | 人民币(万元) | 美元(万元) | 占比 | 国内配套 | [8 empty] | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| 组成部分1: | 海关业务和保税设施
1 | HGAC-CW01 | 海关运营设施 | 鄂州临空集团 | 6876.7533 | 942.021 | 100% |  | 土建 | NCT | 后审 | 2025Q1 | 2025Q1 | 30 |  | 18 | bar: 2025 Q1; 2027 Q2
2 | HGAC-CW02 | 保税物流仓库(一) | 鄂州临空集团 | 13277.6977 | 1818.8627 | 100% |  | 土建 | NCT | 前审 | 2025Q2 | 2025Q3 | 24 |  | 18 | bar: 2025 Q1; 2027 Q2
3 | HGAC-CW03 | 保税物流仓库(二) | 鄂州临空集团 | 25772.9634 | 3530.5429 | 100% |  | 土建 | NCT | 前审 | 2025Q3 | 2025Q4 | 12 |  | 18 | bar: 2025 Q1; 2027 Q2
4 | HGAC-CW04 | 保税物流仓库(三) | 鄂州临空集团 | 54208.0131 | 7425.7552 | 100% |  | 土建 | IOCT | 前审 | 2025Q3 | 2025Q4 | 24 |  | 18 | bar: 2027 Q1
5 | HGAC-CW05 | 保税物流仓库(四) | 鄂州临空集团 | 47558.926 | 6514.9214 | 100% |  | 土建 | IOCT | 前审 | 2025Q3 | 2025Q4 | 24 |  | 18 | bar: 2027 Q1
6 | HGAC-CW06 | 保税物流与加工仓库 | 鄂州临空集团 | 23398.367 | 3205.2558 | 100% |  | 土建 | NCT | 前审 | 2025Q3 | 2025Q4 | 30 |  | 18 | bar: 2026 Q1
7 | HGAC-CW07 | 附属工程 | 鄂州临空集团 | 3292.1052 | 450.9733 | 100% |  | 土建 | NCT | 后审 | 2025Q3 | 2025Q4 | 24 |  | 12 | bar: 2025 Q1; 2027 Q2
| 合计 |  |  | 174384.8256 | bar: 2027 Q2
| 组成部分2 | 贸易和货运服务设施
8 | HGAC-CW08 | 贸易和货运服务设施 | 鄂州临空集团 | 28051.0846 | 3842.6143 | 100% |  | 土建 | NCT | 前审 | 2026Q3 | 2026Q4 | 30 |  | 18 | bar: 2025 Q1
合计 |  |  |  | 28051.0846
| 组成部分3 | 低碳、智慧和配套设施
9 | HGAC-CW09 | 园区道路 | 鄂州临空集团 | 20312.85 | 2782.5822 | 100% |  | 土建 | NCT | 前审 | 2026Q4 | 2027Q1 | 24 |  | 12 | bar: 2025 Q1; 2026 Q1 to 2028 Q4
10 | HGAC-CW10 | 土方工程 | 鄂州临空集团 | 20000 | 2739.726 | 100% |  | 货物 | NCT | 前审 | 2025Q1 | 2025Q1 | 24 |  | 12 | 2025 Q1: 开工; 2026 Q1: (第一个土建合同)
11 | HGAC-GD01 | 屋顶光伏(一) | 鄂州临空集团 | 5413.5455 | 741.5816 | 100% |  | 货物 | NCT | 前审 | 2025Q3 | 2025Q4 | 24 |  | 12 | 2025 Q1: 开工; 2026 Q1: (第一个货物合同)
12 | HGAC-GD02 | 屋顶光伏(二) | 鄂州临空集团 | 6823.41 | 934.7137 | 100% |  | 货物 | NCT | 前审 | 2025Q4 | 2026Q1 | 24 |  | 42 | bar: 2025 Q2
13 | HGAC-GD03 | 新能源利用 | 鄂州临空集团 | 3364 | 460.8219 | 100% |  | 货物 | NCT | 前审 | 2025Q4 | 2026Q1 | 24 |  | 48 | bar: 2025 Q1
14 | HGAC-GD04 | 智慧运营系统 | 鄂州临空集团 | 4000 | 547.9452 | 100% |  | 货物 | NCT | 前审 | 2026Q1 | 2026Q2 | 24 |  | 48 | bar: 2025 Q1
15 | HGAC-GD05 | 综合信息化平台 | 鄂州临空集团 | 18818.98 | 2577.9425 | 100% |  | 货物 | IOCT | 前审 | 2025Q1 | 2025Q1 | 36 |  | 42 | bar: 2025 Q2
合计 |  |  |  | 78732.7855
| 组成部分4: | 能力建设
16 | HGAC-SS01 | 项目管理 |  | 1000 |  |  |  | 咨询服务 | IOCS/QCBS | 前审 |  |  |  |  | 48 | bar: 2024 Q3 to 2025 Q1
17 | HGAC-SS02 | 项目监测评价 |  | 1000 |  |  |  | 咨询服务 | IOCS/QCBS | 前审 |  |  |  |  | 48 | bar: 2024 Q3 to 2025 Q1
18 | HGAC-SS03 | 国际绿建认证或国内绿建标准认证 |  | 761 |  |  |  | 咨询服务 | IOCS/QCBS | 前审 |  |  |  |  | 42 | bar: 2025 Q2
19 | HGAC-SS04 | 绿建三星认证咨询 |  | 116 |  |  |  | 咨询服务 | NCS/CQS | 后审 |  |  |  |  | 42 | bar: 2025 Q2
20 | HGAC-SS05 | 海关监管模式创新课题研究 |  | 350 |  |  |  | 咨询服务 | NCS/CQS | 后审 |  |  |  |  | 24 | bar: 2025 Q2
21 | HGAC-SS06 | 多检合一创新课题研究 |  | 350 |  |  |  | 咨询服务 | NCS/CQS | 后审 |  |  |  |  | 24 | bar: 2025 Q2
22 | HGAC-SS07 | 多式联运创新课题研究 | 鄂州临空集团 | 300 | 41.0959 | 100% |  | 咨询服务 | NCS/CQS | 前审 | 2025Q1 | 2024Q1 | 60 |  | 24 | bar: 2025 Q2
合计 |  |  |  | 3877
总计 |  |  |  | 285045.6957
注: 汇率取自2024/4/12亚投行贷款考察备忘录， $1 = ￥7.11。

## 采购计划0422_中文 (2) (hidden)
附件1-亚投行贷款湖北航空货运产业园项目采购计划 (2024年4月)
1美元=人民币 | 亚投行项目评估考察备忘录
7.11 | 2024-04-12
合同编号 | 合同名称 | 合同内容描述 | 合同估算价 |  | 亚投行贷款额 |  | 合同类型 | 采购方式 | 合同期 (月) | 审查 方式 | 采用招标文件类型 | 提前 采购 | 追溯贷款 | 预计 公告日期 | 预计 开标时间 | 预计合同 签订时间 | 预计合同 完成时间 | 备注
|  |  | 人民币 (万元) | 美元 (万元) | 美元 (万元) | 人民币 (万元)
组成部分1: | 海关业务和保税设施
HGAC-CW01 | 海关运营设施 | (1) 海关查验仓库T01，面积10,911 m2 ; (2) 卡口与围网: #2海关卡口 949 m2、围网7,730 m | 6876.7533 | 967.1946 | 967.1946 | 6876.7533 | 土建 | NCT | 18 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
1.1 | T01 | T01 海关查验仓库 | 5931.3338 |  | 0 | 5931.3338
1.1.1 |  | 土建工程 | 4137.5599 |  | 0 | 4137.5599
1.1.2 |  | 给排水工程 | 13.9661 |  | 0 | 13.9661
1.1.3 |  | 电气工程 | 125.6947 |  | 0 | 125.6947
1.1.4 |  | 暖通工程 | 97.7626 |  | 0 | 97.7626
1.1.5 |  | 消防工程 | 216.4742 |  | 0 | 216.4742
1.1.6 |  | 设备工程 | 59.6525 |  | 0 | 59.6525
1.1.7 |  | 场平工程 | 218.22 |  | 0 | 218.22
1.1.8 |  | 室外工程 | 1024.0038 |  | 0 | 1024.0038
1.1.8 |  | 绿建工程 | 38 |  | 0 | 38
|  | 废弃物绿色处理 | 1 |  | 0 | 1
|  | 雨洪管理设施 | 4 |  | 0 | 4
|  | LEED认证增量措施 | 33 |  | 0 | 33
1.2 |  | 2#海关卡口 | 481.6195 |  | 0 | 481.6195
1.2.1 |  | 地基处理 | 3.3215 |  | 0 | 3.3215
1.2.2 |  | 土建工程 | 455.52 |  | 0 | 455.52
1.2.3 |  | 给排水工程 | 2.847 |  | 0 | 2.847
1.2.4 |  | 暖通工程 | 3.796 |  | 0 | 3.796
1.2.5 |  | 电气工程 | 8.541 |  | 0 | 8.541
1.2.6 |  | 抗震支架 | 5.694 |  | 0 | 5.694
1.2.7 |  | 标识标牌 | 1.9 |  | 0 | 1.9
1.4 |  | 海关围网 | 463.8 |  | 0 | 463.8
HGAC-CW02 | 保税物流仓库 (一) | 保税物流仓库M01，建筑面积总计20,396 m2 | 13277.6977 | 1867.468 | 1867.468 | 13277.6977 | 土建 | NCT | 18 | 前审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.8 | M01 物流仓库 |  | 13277.6977 | 1867.468 | 1867.468 | 13277.6977 |  |  |  | 前审
2.8.1 | 土建工程 |  | 9630.4162 | 1354.4889 | 1354.4889 | 9630.4162 |  |  |  | 前审
2.8.2 | 给排水工程 |  | 32.5069 | 4.572 | 4.572 | 32.5069 |  |  |  | 前审
2.8.3 | 电气工程 |  | 292.5619 | 41.1479 | 41.1479 | 292.5619 |  |  |  | 前审
2.8.4 | 暖通工程 |  | 227.5482 | 32.004 | 32.004 | 227.5482 |  |  |  | 前审
2.8.5 | 消防工程 |  | 503.8566 | 70.8659 | 70.8659 | 503.8566 |  |  |  | 前审
2.8.6 | 设备工程 |  | 138.8447 | 19.5281 | 19.5281 | 138.8447 |  |  |  | 前审
2.8.7 | 场平工程 |  | 507.92 | 71.4374 | 71.4374 | 507.92 |  |  |  | 前审
| 室外工程 |  | 1881.0431 | 264.563 | 264.563 | 1881.0431 |  |  |  | 前审
2.8.8 | 绿建工程 |  | 63 | 8.8608 | 8.8608 | 63 |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 |  |  |  | 前审
| 雨洪管理设施 |  | 11 | 1.5471 | 1.5471 | 11 |  |  |  | 前审
| LEED认证增量措施 |  | 51 | 7.173 | 7.173 | 51 |  |  |  | 前审
HGAC-CW03 | 保税物流仓库 (二) | 保税物流仓库J01 / K01、架空平台3，建筑面积总计42,780 m2 | 25772.9634 | 3624.8894 | 3624.8894 | 25772.9634 | 土建 | NCT | 18 | 前审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15 | J01 物流仓库 |  | 11277.3601 | 1586.1266 | 1586.1266 | 11277.3601 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.1 | 土建工程 |  | 8671.015 | 1219.552 | 1219.552 | 8671.015 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.2 | 给排水工程 |  | 29.2685 | 4.1165 | 4.1165 | 29.2685 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.3 | 电气工程 |  | 263.4163 | 37.0487 | 37.0487 | 263.4163 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.4 | 暖通工程 |  | 204.8794 | 28.8157 | 28.8157 | 204.8794 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.5 | 消防工程 |  | 453.6614 | 63.8061 | 63.8061 | 453.6614 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.6 | 设备工程 |  | 125.0127 | 17.5827 | 17.5827 | 125.0127 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.7 | 场平工程 |  | 457.32 | 64.3207 | 64.3207 | 457.32 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| 室外工程 |  | 1015.7868 | 142.8673 | 142.8673 | 1015.7868
2.15.8 | 绿建工程 |  | 57 | 8.0169 | 8.0169 | 57 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| 雨洪管理设施 |  | 9 | 1.2658 | 1.2658 | 9 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| LEED认证增量措施 |  | 47 | 6.6104 | 6.6104 | 47 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16 | K01 物流仓库 |  | 11277.3601 | 1586.1266 | 1586.1266 | 11277.3601 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.1 | 土建工程 |  | 8671.015 | 1219.552 | 1219.552 | 8671.015 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.2 | 给排水工程 |  | 29.2685 | 4.1165 | 4.1165 | 29.2685 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.3 | 电气工程 |  | 263.4163 | 37.0487 | 37.0487 | 263.4163 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.4 | 暖通工程 |  | 204.8794 | 28.8157 | 28.8157 | 204.8794 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.5 | 消防工程 |  | 453.6614 | 63.8061 | 63.8061 | 453.6614 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.6 | 设备工程 |  | 125.0127 | 17.5827 | 17.5827 | 125.0127 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.7 | 场平工程 |  | 457.32 | 64.3207 | 64.3207 | 457.32 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| 室外工程 |  | 1015.7868 | 142.8673 | 142.8673 | 1015.7868
2.16.8 | 绿建工程 |  | 57 | 8.0169 | 8.0169 | 57 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| 雨洪管理设施 |  | 9 | 1.2658 | 1.2658 | 9 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| LEED认证增量措施 |  | 47 | 6.6104 | 6.6104 | 47 | 土建 | NCT | 18个月 | 后审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.18 | 架空平台3 |  | 4178.7488 | 587.7284 | 587.7284 | 4178.7488
2.18.1 | 建筑工程 |  | 4053.3863 | 570.0965 | 570.0965 | 4053.3863
2.18.2 | 安装工程 |  | 125.3625 | 17.6319 | 17.6319 | 125.3625
HGAC-CW04 | 保税物流仓库 (三) | 保税物流仓库H01 / H02 / E05,、架空平台2，建筑面积总计121,805 m2 | 54208.0131 | 7624.1931 | 7624.1931 | 54208.0131 | 土建 | IOCT | 18 | 前审 | 是 |  |  | 2027.3 | 2027.4 | 2027.5 | 2028.12
2.1 | H01 物流仓库 |  | 15502.4051 | 2180.3664 | 2180.3664 | 15502.4051
2.10.1 | 土建工程 |  | 12124.8594 | 1705.3248 | 1705.3248 | 12124.8594
2.10.2 | 给排水工程 |  | 40.9267 | 5.7562 | 5.7562 | 40.9267
2.10.3 | 电气工程 |  | 368.3405 | 51.806 | 51.806 | 368.3405
2.10.4 | 暖通工程 |  | 286.487 | 40.2935 | 40.2935 | 286.487
2.10.5 | 消防工程 |  | 634.3642 | 89.2214 | 89.2214 | 634.3642
2.10.6 | 设备工程 |  | 174.8079 | 24.5862 | 24.5862 | 174.8079
2.10.7 | 场平工程 |  | 639.48 | 89.9409 | 89.9409 | 639.48
| 室外工程 |  | 1161.1395 | 163.3108 | 163.3108 | 1161.1395
2.10.8 | 绿建工程 |  | 72 | 10.1266 | 10.1266 | 72
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1
| 雨洪管理设施 |  | 13 | 1.8284 | 1.8284 | 13
| LEED认证增量措施 |  | 58 | 8.1575 | 8.1575 | 58
2.11 | H02 物流仓库 |  | 15296.8552 | 2151.4564 | 2151.4564 | 15296.8552
2.11.1 | 土建工程 |  | 12124.8594 | 1705.3248 | 1705.3248 | 12124.8594
2.11.2 | 给排水工程 |  | 40.9267 | 5.7562 | 5.7562 | 40.9267
2.11.3 | 电气工程 |  | 368.3405 | 51.806 | 51.806 | 368.3405
2.11.4 | 暖通工程 |  | 286.487 | 40.2935 | 40.2935 | 286.487
2.11.5 | 消防工程 |  | 634.3642 | 89.2214 | 89.2214 | 634.3642
2.11.6 | 设备工程 |  | 174.8079 | 24.5862 | 24.5862 | 174.8079
2.11.7 | 场平工程 |  | 639.48 | 89.9409 | 89.9409 | 639.48
| 室外工程 |  | 955.5896 | 134.4008 | 134.4008 | 955.5896
2.11.8 | 绿建工程 |  | 72 | 10.1266 | 10.1266 | 72
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1
| 雨洪管理设施 |  | 13 | 1.8284 | 1.8284 | 13
| LEED认证增量措施 |  | 58 | 8.1575 | 8.1575 | 58
2.9 | E05 物流仓库 |  | 13789.8727 | 1939.5039 | 1939.5039 | 13789.8727
2.9.1 | 土建工程 |  | 10541.2786 | 1482.599 | 1482.599 | 10541.2786
2.9.2 | 给排水工程 |  | 35.5814 | 5.0044 | 5.0044 | 35.5814
2.9.3 | 电气工程 |  | 320.233 | 45.0398 | 45.0398 | 320.233
2.9.4 | 暖通工程 |  | 249.0701 | 35.031 | 35.031 | 249.0701
2.9.5 | 消防工程 |  | 551.5123 | 77.5685 | 77.5685 | 551.5123
2.9.6 | 设备工程 |  | 151.9769 | 21.3751 | 21.3751 | 151.9769
2.9.7 | 场平工程 |  | 555.96 | 78.1941 | 78.1941 | 555.96
| 室外工程 |  | 1319.2604 | 185.55 | 185.55 | 1319.2604
2.9.8 | 绿建工程 |  | 65 | 9.1421 | 9.1421 | 65
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1
| 雨洪管理设施 |  | 11 | 1.5471 | 1.5471 | 11
| LEED认证增量措施 |  | 53 | 7.4543 | 7.4543 | 53
2.17 | 架空平台2 |  | 9618.88 | 1352.8664 | 1352.8664 | 9618.88
2.17.1 | 建筑工程 |  | 9330.3136 | 1312.2804 | 1312.2804 | 9330.3136
2.17.2 | 安装工程 |  | 288.5664 | 40.586 | 40.586 | 288.5664
HGAC-CW05 | 保税物流仓库 (四) | 保税物流仓库H03 / H04 / L01，建筑面积总计100,098 m2 | 47558.926 | 6689.0191 | 6689.0191 | 47558.926 | 土建 | IOCT | 18 | 前审 | 是 |  |  | 2027.3 | 2027.4 | 2027.5 | 2028.12
2.12 | H03 物流仓库 |  | 15098.9985 | 2123.6285 | 2123.6285 | 15098.9985 |  |  |  | 前审
2.12.1 | 土建工程 |  | 12124.8594 | 1705.3248 | 1705.3248 | 12124.8594 |  |  |  | 前审
2.12.2 | 给排水工程 |  | 40.9267 | 5.7562 | 5.7562 | 40.9267 |  |  |  | 前审
2.12.3 | 电气工程 |  | 368.3405 | 51.806 | 51.806 | 368.3405 |  |  |  | 前审
2.12.4 | 暖通工程 |  | 286.487 | 40.2935 | 40.2935 | 286.487 |  |  |  | 前审
2.12.5 | 消防工程 |  | 634.3642 | 89.2214 | 89.2214 | 634.3642 |  |  |  | 前审
2.12.6 | 设备工程 |  | 174.8079 | 24.5862 | 24.5862 | 174.8079 |  |  |  | 前审
2.12.7 | 场平工程 |  | 639.48 | 89.9409 | 89.9409 | 639.48 |  |  |  | 前审
| 室外工程 |  | 757.7328 | 106.5728 | 106.5728 | 757.7328 |  |  |  | 前审
2.12.8 | 绿建工程 |  | 72 | 10.1266 | 10.1266 | 72 |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 |  |  |  | 前审
| 雨洪管理设施 |  | 13 | 1.8284 | 1.8284 | 13 |  |  |  | 前审
| LEED认证增量措施 |  | 58 | 8.1575 | 8.1575 | 58 |  |  |  | 前审
2.13 | H04 物流仓库 |  | 15276.6249 | 2148.6111 | 2148.6111 | 15276.6249 |  |  |  | 前审
2.13.1 | 土建工程 |  | 12124.8594 | 1705.3248 | 1705.3248 | 12124.8594 |  |  |  | 前审
2.13.2 | 给排水工程 |  | 40.9267 | 5.7562 | 5.7562 | 40.9267 |  |  |  | 前审
2.13.3 | 电气工程 |  | 368.3405 | 51.806 | 51.806 | 368.3405 |  |  |  | 前审
2.13.4 | 暖通工程 |  | 286.487 | 40.2935 | 40.2935 | 286.487 |  |  |  | 前审
2.13.5 | 消防工程 |  | 634.3642 | 89.2214 | 89.2214 | 634.3642 |  |  |  | 前审
2.13.6 | 设备工程 |  | 174.8079 | 24.5862 | 24.5862 | 174.8079 |  |  |  | 前审
2.13.7 | 场平工程 |  | 639.48 | 89.9409 | 89.9409 | 639.48 |  |  |  | 前审
| 室外工程 |  | 935.3592 | 131.5554 | 131.5554 | 935.3592 |  |  |  | 前审
2.13.8 | 绿建工程 |  | 72 | 10.1266 | 10.1266 | 72 |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 |  |  |  | 前审
| 雨洪管理设施 |  | 13 | 1.8284 | 1.8284 | 13 |  |  |  | 前审
| LEED认证增量措施 |  | 58 | 8.1575 | 8.1575 | 58 |  |  |  | 前审
2.14 | L01 物流仓库 |  | 17183.3027 | 2416.7796 | 2416.7796 | 17183.3027 |  |  |  | 前审
2.14.1 | 土建工程 |  | 13708.4402 | 1928.0507 | 1928.0507 | 13708.4402 |  |  |  | 前审
2.14.2 | 给排水工程 |  | 46.272 | 6.508 | 6.508 | 46.272 |  |  |  | 前审
2.14.3 | 电气工程 |  | 416.448 | 58.5722 | 58.5722 | 416.448 |  |  |  | 前审
2.14.4 | 暖通工程 |  | 323.904 | 45.5561 | 45.5561 | 323.904 |  |  |  | 前审
2.14.5 | 消防工程 |  | 717.216 | 100.8743 | 100.8743 | 717.216 |  |  |  | 前审
2.14.6 | 设备工程 |  | 197.6389 | 27.7973 | 27.7973 | 197.6389 |  |  |  | 前审
2.14.7 | 场平工程 |  | 723 | 101.6878 | 101.6878 | 723 |  |  |  | 前审
| 室外工程 |  | 972.3836 | 136.7628 | 136.7628 | 972.3836 |  |  |  | 前审
2.14.8 | 绿建工程 |  | 78 | 10.9705 | 10.9705 | 78 |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 |  |  |  | 前审
| 雨洪管理设施 |  | 14 | 1.9691 | 1.9691 | 14 |  |  |  | 前审
| LEED认证增量措施 |  | 63 | 8.8608 | 8.8608 | 63 |  |  |  | 前审
HGAC-CW06 | 保税加工仓库 | 保税加工仓库E01 / E02 / E03 / E04，建筑面积总计57,184 m2 | 23398.367 | 3290.9096 | 3290.9096 | 23398.367 | 土建 | NCT | 18 | 前审 | 是 |  |  | 2026.3 | 2026.4 | 2026.5 | 2027.12
2.4 | E01 物流仓库 |  | 5921.3919 | 832.8259 | 832.8259 | 5921.3919 |  |  |  | 前审
2.4.1 | 土建工程 |  | 3574 | 502.6723 | 502.6723 | 3574 |  |  |  | 前审
2.4.2 | 给排水工程 |  | 18.2989 | 2.5737 | 2.5737 | 18.2989 |  |  |  | 前审
2.4.3 | 电气工程 |  | 164.6899 | 23.1631 | 23.1631 | 164.6899 |  |  |  | 前审
2.4.4 | 暖通工程 |  | 128.0922 | 18.0158 | 18.0158 | 128.0922 |  |  |  | 前审
2.4.5 | 消防工程 |  | 283.6326 | 39.8921 | 39.8921 | 283.6326 |  |  |  | 前审
2.4.6 | 设备工程 |  | 78.1589 | 10.9928 | 10.9928 | 78.1589 |  |  |  | 前审
2.4.7 | 场平工程 |  | 571.84 | 80.4276 | 80.4276 | 571.84 |  |  |  | 前审
| 室外工程 |  | 1036.6793 | 145.8058 | 145.8058 | 1036.6793 |  |  |  | 前审
2.4.8 | 绿建工程 |  | 66 | 9.2827 | 9.2827 | 66 |  |  |  | 前审
| 废弃物绿色处理 |  | 2 | 0.28129 | 0.28129 | 2 |  |  |  | 前审
| 雨洪管理设施 |  | 11 | 1.5471 | 1.5471 | 11 |  |  |  | 前审
| LEED认证增量措施 |  | 53 | 7.4543 | 7.4543 | 53 |  |  |  | 前审
2.5 | E02 物流仓库 |  | 5952.1709 | 837.1548 | 837.1548 | 5952.1709 |  |  |  | 前审
2.5.1 | 土建工程 |  | 3574 | 502.6723 | 502.6723 | 3574 |  |  |  | 前审
2.5.2 | 给排水工程 |  | 18.2989 | 2.5737 | 2.5737 | 18.2989 |  |  |  | 前审
2.5.3 | 电气工程 |  | 164.6899 | 23.1631 | 23.1631 | 164.6899 |  |  |  | 前审
2.5.4 | 暖通工程 |  | 128.0922 | 18.0158 | 18.0158 | 128.0922 |  |  |  | 前审
2.5.5 | 消防工程 |  | 283.6326 | 39.8921 | 39.8921 | 283.6326 |  |  |  | 前审
2.5.6 | 设备工程 |  | 78.1589 | 10.9928 | 10.9928 | 78.1589 |  |  |  | 前审
2.5.7 | 场平工程 |  | 571.84 | 80.4276 | 80.4276 | 571.84 |  |  |  | 前审
| 室外工程 |  | 1068.4583 | 150.2754 | 150.2754 | 1068.4583 |  |  |  | 前审
2.5.8 | 绿建工程 |  | 65 | 9.1421 | 9.1421 | 65 |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 |  |  |  | 前审
| 雨洪管理设施 |  | 11 | 1.5471 | 1.5471 | 11 |  |  |  | 前审
| LEED认证增量措施 |  | 53 | 7.4543 | 7.4543 | 53 |  |  |  | 前审
2.6 | E03 物流仓库 |  | 5747.9617 | 808.4334 | 808.4334 | 5747.9617 |  |  |  | 前审
2.6.1 | 土建工程 |  | 3574 | 502.6723 | 502.6723 | 3574 |  |  |  | 前审
2.6.2 | 给排水工程 |  | 18.2989 | 2.5737 | 2.5737 | 18.2989 |  |  |  | 前审
2.6.3 | 电气工程 |  | 164.6899 | 23.1631 | 23.1631 | 164.6899 |  |  |  | 前审
2.6.4 | 暖通工程 |  | 128.0922 | 18.0158 | 18.0158 | 128.0922 |  |  |  | 前审
2.6.5 | 消防工程 |  | 283.6326 | 39.8921 | 39.8921 | 283.6326 |  |  |  | 前审
2.6.6 | 设备工程 |  | 78.1589 | 10.9928 | 10.9928 | 78.1589 |  |  |  | 前审
2.6.7 | 场平工程 |  | 571.84 | 80.4276 | 80.4276 | 571.84 |  |  |  | 前审
| 室外工程 |  | 864.2492 | 121.554 | 121.554 | 864.2492 |  |  |  | 前审
2.6.8 | 绿建工程 |  | 65 | 9.1421 | 9.1421 | 65 |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 |  |  |  | 前审
| 雨洪管理设施 |  | 11 | 1.5471 | 1.5471 | 11 |  |  |  | 前审
| LEED认证增量措施 |  | 53 | 7.4543 | 7.4543 | 53 |  |  |  | 前审
2.7 | E04 物流仓库 |  | 5776.8425 | 812.4954 | 812.4954 | 5776.8425 |  |  |  | 前审
2.7.1 | 土建工程 |  | 3574 | 502.6723 | 502.6723 | 3574 |  |  |  | 前审
2.7.2 | 给排水工程 |  | 18.2989 | 2.5737 | 2.5737 | 18.2989 |  |  |  | 前审
2.7.3 | 电气工程 |  | 164.6899 | 23.1631 | 23.1631 | 164.6899 |  |  |  | 前审
2.7.4 | 暖通工程 |  | 128.0922 | 18.0158 | 18.0158 | 128.0922 |  |  |  | 前审
2.7.5 | 消防工程 |  | 283.6326 | 39.8921 | 39.8921 | 283.6326 |  |  |  | 前审
2.7.6 | 设备工程 |  | 78.1589 | 10.9928 | 10.9928 | 78.1589 |  |  |  | 前审
2.7.7 | 场平工程 |  | 571.84 | 80.4276 | 80.4276 | 571.84 |  |  |  | 前审
| 室外工程 |  | 893.13 | 125.616 | 125.616 | 893.13 |  |  |  | 前审
2.7.8 | 绿建工程 |  | 65 | 9.1421 | 9.1421 | 65 |  |  |  | 前审
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 |  |  |  | 前审
| 雨洪管理设施 |  | 11 | 1.5471 | 1.5471 | 11 |  |  |  | 前审
| LEED认证增量措施 |  | 53 | 7.4543 | 7.4543 | 53 |  |  |  | 前审
HGAC-CW07 | 附属工程 | 集卡坡道3、集卡坡道4、集卡坡道5、门卫室、设备用房 | 3292.1052 | 463.0246 | 463.0246 | 3292.1052 | 土建 | NCT | 12 | 前审 |  |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.5
小计 |  |  | 174384.8256 | 967.1946 | 967.1946 | 174384.8256
组成部分2: | 贸易和货运服务设施
HGAC-CW08 | 贸易和货运服务设施 | (1) 免税服务中心S01，建筑面积10,450 m2; (2) 综合办公楼W01，建筑面积39,432 m2 | 28051.0846 | 3945.3002 | 3945.3002 | 28051.0846 | 土建 | NCT | 18 | 前审 | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
3.2 | S01 免税服务中心 |  | 8098.2373 | 1138.9926 | 1138.9926 | 8098.2373
3.2.1 | 土建工程 |  | 4284.5 | 602.602 | 602.602 | 4284.5
3.2.2 | 给排水工程 |  | 26.125 | 3.6744 | 3.6744 | 26.125
3.2.3 | 电气工程 |  | 151.525 | 21.3115 | 21.3115 | 151.525
3.2.4 | 暖通工程 |  | 120.175 | 16.9023 | 16.9023 | 120.175
3.2.5 | 消防工程 |  | 146.3 | 20.5767 | 20.5767 | 146.3
3.2.6 | 设备工程 |  | 41.8 | 5.879 | 5.879 | 41.8
3.2.7 | 场平工程 |  | 209 | 29.3952 | 29.3952 | 209
| 室外工程 |  | 2754.8123 | 387.456 | 387.456 | 2754.8123
3.2.8 | 绿建工程 |  | 364 | 51.1955 | 51.1955 | 364
| 其他可再生能源措施 |  | 289 | 40.647 | 40.647 | 289
| 废弃物绿色处理 |  | 4 | 0.56259 | 0.56259 | 4
| 雨洪管理设施 |  | 4 | 0.56259 | 0.56259 | 4
| LEED认证增量措施 |  | 32 | 4.5007 | 4.5007 | 32
| 绿建三星增量措施 |  | 35 | 4.9226 | 4.9226 | 35
3.1 | W01 综合办公楼 |  | 19952.8472 | 2806.3076 | 2806.3076 | 19952.8472
3.1.1 | 土建工程 |  | 14787.06 | 2079.7553 | 2079.7553 | 14787.06
3.1.2 | 给排水工程 |  | 98.5804 | 13.865 | 13.865 | 98.5804
3.1.3 | 电气工程 |  | 571.7663 | 80.4172 | 80.4172 | 571.7663
3.1.4 | 暖通工程 |  | 453.4698 | 63.7792 | 63.7792 | 453.4698
3.1.5 | 消防工程 |  | 552.0502 | 77.6442 | 77.6442 | 552.0502
3.1.6 | 设备工程 |  | 157.7286 | 22.1841 | 22.1841 | 157.7286
3.1.7 | 场平工程 |  | 788.6432 | 110.9203 | 110.9203 | 788.6432
| 室外工程 |  | 2458.5486 | 345.7874 | 345.7874 | 2458.5486
3.1.8 | 绿建工程 |  | 85 | 11.955 | 11.955 | 85
| 废弃物绿色处理 |  | 4 | 0.56259 | 0.56259 | 4
| 雨洪管理设施 |  | 15 | 2.1097 | 2.1097 | 15
| LEED认证增量措施 |  | 66 | 9.2827 | 9.2827 | 66
小计 |  |  | 28051.0846 | 3945.3002 | 3945.3002 | 28051.0846
组成部分3: | 低碳、智慧和配套设施
HGAC-CW09 | 园区道路 | (1) 高架联络道#1 (路基面积2,667 m2)、高架联络道#2 (路基面积2,375 m2); (2) 4条北区道路(规划二路581.6 m、规划三路990 m、规划四路1,075 m、规划五路354 m), 以及相关基础设施 | 20312.85 | 2856.9409 | 2856.9409 | 20312.85 | 土建 | NCT | 12 | 前审 | 是 | 是 |  | 2024.9 | 2024.10 | 2024.11 | 2025.11 | 土建类别第一个
6 | 配套设施 |  | 2688.05 | 378.0661 | 378.0661 | 2688.05 |  |  |  | 前审
6.1 | 1#高架联络道 |  | 399.45 | 56.1814 | 56.1814 | 399.45 |  |  |  | 前审
6.1.1 | 路基 |  | 2145.6 | 301.7722 | 301.7722 | 2145.6 |  |  |  | 前审
6.1.2 | 钢箱梁 |  | 143 | 20.1125 | 20.1125 | 143 |  |  |  | 前审
6.1.3 | 装饰棚 |  | 6521.05 | 917.166 | 917.166 | 6521.05 |  |  |  | 前审
6.2 | 2#高架联络道 |  | 6521.05 | 917.166 | 917.166 | 6521.05 |  |  |  | 前审
6.2.1 | 路基 |  | 356.25 | 50.1055 | 50.1055 | 356.25 |  |  |  | 前审
6.2.3 | 钢箱梁 |  | 5956.8 | 837.8059 | 837.8059 | 5956.8 |  |  |  | 前审
6.2.4 | 装饰棚 |  | 208 | 29.2546 | 29.2546 | 208 |  |  |  | 前审
6.3 | 规划二路 |  | 1959.93 | 275.6582 | 275.6582 | 1959.93 |  |  |  | 前审
6.3.1 | 路基 |  | 1959.93 | 275.6582 | 275.6582 | 1959.93 |  |  |  | 前审
6.4 | 规划三路 |  | 3742.2 | 526.3291 | 526.3291 | 3742.2 |  |  |  | 前审
6.4.1 | 路基 |  | 3742.2 | 526.3291 | 526.3291 | 3742.2 |  |  |  | 前审
6.5 | 规划四路 |  | 4063.5 | 571.519 | 571.519 | 4063.5 |  |  |  | 前审
6.5.1 | 路基 |  | 4063.5 | 571.519 | 571.519 | 4063.5 |  |  |  | 前审
6.6 | 规划五路 |  | 1338.12 | 188.2025 | 188.2025 | 1338.12 |  |  |  | 前审
6.6.1 | 路基 |  | 1338.12 | 188.2025 | 188.2025 | 1338.12 |  |  |  | 前审
HGAC-CW10 | 土方工程 | 二期北区土方工程 | 20000 | 2812.9395 | 2812.9395 | 20000 | 土建 | NCT | 12 | 前审 |  | 是 |  | 2024.9 | 2024.10 | 2024.11 | 2025.11
HGAC-GD01 | 屋顶光伏(一) | (1) 一期(先行启动区)海关查验中心、国际快件中心#1 /#2、保税物流中心(B类)#1 / #2 / #3、国际货站顶部光伏设备采购与安装，共计76,134 m2；(2)自建南区建筑(·P01 / R01 / R02保税物流仓库、Q01 / Q02保税加工仓库)顶部光伏设备采购与安装，共计87,936 m2。总计(1) + (2) = 164,070 m2 | 5413.5455 | 761.3988 | 761.3988 | 5413.5455 | 货物 | NCT | 12 | 前审 | 是 | 是 |  | 2024.9 | 2024.10 | 2024.11 | 2025.11 | 货物类别第一个
4.1.22 | 海关查验中心 | 11022 | 363.6765 | 51.15 | 363.6765 | 51.15
4.1.23 | 保税仓库1 | 11707 | 386.1825 | 54.3154 | 386.1825 | 54.3154
4.1.24 | 保税仓库2 | 11707 | 386.1825 | 54.3154 | 386.1825 | 54.3154
4.1.25 | 保税仓库3 | 11707 | 386.1825 | 54.3154 | 386.1825 | 54.3154
4.1.26 | 国际快件中心 | 18327 | 604.7635 | 85.0582 | 604.7635 | 85.0582
4.1.27 | 快件中心 | 11664 | 384.8185 | 54.1236 | 384.8185 | 54.1236
4.1.16 | P001 | 16128 | 532.1305 | 74.8425 | 532.1305 | 74.8425
4.1.17 | Q001 | 18768 | 619.256 | 87.0965 | 619.256 | 87.0965
4.1.18 | Q002 | 18768 | 619.256 | 87.0965 | 619.256 | 87.0965
4.1.19 | R001 | 17136 | 565.5485 | 79.5427 | 565.5485 | 79.5427
4.1.20 | R002 | 17136 | 565.5485 | 79.5427 | 565.5485 | 79.5427
HGAC-GD02 | 屋顶光伏(二) | 亚投行资金建设北区所有建筑，包括免税服务中心S01、综合业务楼W01，海关查验仓库T01、保税物流仓库E01~E04 / H01~H04 / J01 / K01 / L01 / M01，总计196,714 m2 | 6823.41 | 959.692 | 959.692 | 6823.41 | 货物 | NCT | 40 | 后审 |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
4.1 | 光伏 | 370864.11m2 | 12236.96 | 1721.0914 | 1721.0914 | 12236.96
| 亚投行资金建设北区 | 196714.11 | 6823.4145 | 959.6926 | 959.6926 | 6823.4145
4.1.1 | 免税服务中心S01 | 5226.66 | 172.3755 | 24.2441 | 24.2441 | 172.3755
4.1.2 | 综合业务楼W01 | 4929.02 | 162.657 | 22.8772 | 22.8772 | 162.657
4.1.3 | E001 | 13104 | 432.388 | 60.8141 | 60.8141 | 432.388
4.1.4 | E002 | 13104 | 432.388 | 60.8141 | 60.8141 | 432.388
4.1.5 | E003 | 13104 | 432.388 | 60.8141 | 60.8141 | 432.388
4.1.6 | E004 | 13104 | 432.388 | 60.8141 | 60.8141 | 432.388
4.1.7 | E005 | 13104 | 432.388 | 60.8141 | 60.8141 | 432.388
4.1.8 | H001 | 15120 | 498.883 | 70.1664 | 70.1664 | 498.883
4.1.9 | H002 | 15120 | 498.883 | 70.1664 | 70.1664 | 498.883
4.1.10 | H003 | 15120 | 498.883 | 70.1664 | 70.1664 | 498.883
4.1.11 | H004 | 15120 | 498.883 | 70.1664 | 70.1664 | 498.883
4.1.12 | J001 | 10800 | 356.345 | 50.1188 | 50.1188 | 356.345
4.1.13 | K001 | 9360 | 308.7755 | 43.4283 | 43.4283 | 308.7755
4.1.14 | L001 | 17136 | 565.5485 | 79.5427 | 79.5427 | 565.5485
4.1.15 | M001 | 23262.43 | 767.591 | 107.9594 | 107.9594 | 767.591
4.1.21 | T001(海关查验仓库) | 10080 | 332.65 | 46.7862 | 46.7862 | 332.65
| 自建南区 | 87936 | 2901.75 | 408.1224 | 408.1224 | 2901.75
4.1.16 | P001(自建南区) | 16128 | 532.13 | 74.8425 | 74.8425 | 532.13
4.1.17 | Q001(自建南区) | 18768 | 619.26 | 87.097 | 87.097 | 619.26
4.1.18 | Q002(自建南区) | 18768 | 619.26 | 87.097 | 87.097 | 619.26
4.1.19 | R001(自建南区) | 17136 | 565.55 | 79.5429 | 79.5429 | 565.55
4.1.20 | R002(自建南区) | 17136 | 565.55 | 79.5429 | 79.5429 | 565.55
| 先行启动区 | 86214 | 2844.45 | 961.4906 | 961.4906 | 6823.41
4.1.22 | 海关查验中心(先行启动区) | 11022 | 363.68 | 51.1505 | 51.1505 | 363.68
4.1.23 | 保税仓库1 | 11707 | 386.18 | 54.315 | 54.315 | 386.18
4.1.24 | 保税仓库2 | 11707 | 386.18 | 54.315 | 54.315 | 386.18
4.1.25 | 保税仓库3 | 11707 | 386.18 | 54.315 | 54.315 | 386.18
4.1.26 | 国际快件中心 | 18327 | 604.76 | 85.0577 | 85.0577 | 604.76
4.1.27 | 国际快件中心 | 11664 | 384.82 | 54.1238 | 54.1238 | 384.82
HGAC-GD03 | 新能源利用 | 商贸物流中心(一期先行启动区)地热泵工程 | 3364 | 473.1364 | 473.1364 | 3364 | 货物 | NCT | 40 | 后审 |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
HGAC-GD04 | 智慧运营系统 | 园区智慧运营系统设备与软件 | 4000 | 562.5879 | 562.5879 | 4000 | 货物 | NCT | 40 | 后审 |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
| 4.2 | 智慧运营平台 | 4000 |  |  | 4000
HGAC-GD05 | 综合信息化平台 | 智慧海关辅助监管平台、应用支撑平台、企业通关服务平台、多式联运平台、园区车辆行人管控设备、园区视频设备、园区办公信息化设备、园区安全 / 能效 /消防设备、数字化月台、数字化仓库、一站式安检区、检疫处理区 | 18818.98 | 2646.8326 | 2646.8326 | 18818.98 | 货物 | ICOT | 40 | 前审 | 是 |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
4.3 | 综合信息化平台 |  | 18818.98 | 2646.8326 | 2646.8326 | 18818.98
4.3.1 | 智慧海关辅助监管平台 |  | 3355 | 471.8706 | 471.8706 | 3355
4.3.2 | 应用支撑平台 |  | 920 | 129.3952 | 129.3952 | 920
4.3.3 | 企业通关服务平台 |  | 3160 | 444.4444 | 444.4444 | 3160
4.3.4 | 多式联运平台 |  | 2100 | 295.3586 | 295.3586 | 2100
4.3.5 | 园区车辆行人管控设备 |  | 341.9 | 48.0872 | 48.0872 | 341.9
4.3.6 | 园区视频设备 |  | 656.15 | 92.2855 | 92.2855 | 656.15
4.3.7 | 园区办公信息化设备 |  | 355.67 | 50.0239 | 50.0239 | 355.67
4.3.8 | 园区安全、能效、消防设备 |  | 211.46 | 29.7412 | 29.7412 | 211.46
4.3.9 | 数字化月台 |  | 33.6 | 4.7257 | 4.7257 | 33.6
4.3.10 | 数字化仓库 |  | 333.3 | 46.8776 | 46.8776 | 333.3
4.3.11 | 一站式安检区 |  | 7000 | 984.5288 | 984.5288 | 7000
4.3.12 | 检疫处理区 |  | 351.9 | 49.4937 | 49.4937 | 351.9
小计 |  |  | 78732.7855 | 11073.5282 | 10600.3918 | 75368.7855
组成部分4: | 能力建设
HGAC-CS01 | 项目管理 | 项目管理技术支持、培训、考察、知识产品开发推广等 | 1000 | 140.647 | 140.647 | 1000 | 咨询服务 | IOCS/QCBS | 51 | 前审 |  | 是 |  | 2024.9 | 2024.10 | 2024.11 | 2028.12
HGAC-CS02 | 项目监测评价 | 外部环境监测、外部移民监测、外部社会和性别监测、项目绩效评估等 | 1000 | 140.647 | 140.647 | 1000 | 咨询服务 | IOCS/QCBS | 51 | 前审 |  | 是 |  | 2024.9 | 2024.10 | 2024.11 | 2028.12
HGAC-CS03 | LEED认证咨询 | 园区建筑LEED认证咨询服务 | 761 | 107.0323 | 107.0323 | 761 | 咨询服务 | IOCS/QCBS | 42 | 前审 |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
HGAC-CS04 | 绿建三星认证咨询 | 园区建筑绿色建筑认证咨询服务 | 116 | 16.315 | 16.315 | 116 | 咨询服务 | NCS/CQS | 42 | 后审 |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
HGAC-CS05 | 其它能力建设服务 | 其它能力建设服务 | 1000 | 140.647 | 140.647 | 1000 | 咨询服务 | IOCS/QCBS | 42 | 前审 |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
小计 |  |  | 3877 | 545.2883 | 545.2883 | 3877
总计 |  |  | 285045.6957 | 40090.8152 | 40090.8152 | 285045.6957
|  | CW土建 | 242748.7602 | 34141.8791
|  | Goods货物 | 38419.9355 | 5403.6477
|  | Consulting Services咨询服务 | 3877 | 545.2883
|  |  | 285045.6957 | 40090.8152
提前采购
|  | CW-09 | 2856.9409
|  | CW-10 | 2812.9395
|  | GD-01 | 761.3988
|  | CS-01 | 140.647
|  | CS-02 | 140.647
6712.5732

## PP_0422-ENG (2) (hidden)
Attachment 1-China: Hubei Global Air Cargo Logistics Hub Project----Procurement Plan (April 2024)
$1 = CNY | AIIB Loan Appraisal Mission MoM
7.11 | 2024-04-12
Contract No. | Contract Name | Description | Cost Estimate |  | % of AIIB Financing |  | Procurement Category | Procurement Method | Contract Duration (Months) | Bank Review (Prior / Post) | 采用招标文件类型 | Advance Contracting | 追溯贷款 | Date of SPN | Bid Openning | Contract Signing | Contract Closing | Notes
|  |  | CNY million | $ million
Component 1: | Customs Operation and Bonded Facilities
HGAC-CW01 | Customs Operation Facilities | (1) Customs Inspection Center T01 (10,911 m2) ; (2) Customs Kiosk & Fence: #2 Customs Kiosk (949 m2), Fence (7,730 m) | 6876.7533 | 967.1946 | 967.1946 | 6876.7533 | Works | NCT | 18 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
1.1 | Bonded Logistics Warehouse (1) | T01 海关查验仓库 | 5931.3338 |  | 0 | 5931.3338 | Works |  |  | Post
1.1.1 | Bonded Logistics Warehouse (2) | 土建工程 | 4137.5599 |  | 0 | 4137.5599 | Works |  |  | Post
1.1.2 | Bonded Logistics Warehouse (3) | 给排水工程 | 13.9661 |  | 0 | 13.9661 | Works |  |  | Post
1.1.3 | Bonded Logistics Warehouse (4) | 电气工程 | 125.6947 |  | 0 | 125.6947 | Works |  |  | Post
1.1.4 | Bonded and Processing Warehouses | 暖通工程 | 97.7626 |  | 0 | 97.7626 | Works |  |  | Post
1.1.5 | Auxiliary Facilities | 消防工程 | 216.4742 |  | 0 | 216.4742 | Works |  |  | Post
1.1.6 |  | 设备工程 | 59.6525 |  | 0 | 59.6525 | Works |  |  | Post
1.1.7 |  | 场平工程 | 218.22 |  | 0 | 218.22 | Works |  |  | Post
1.1.8 |  | 室外工程 | 1024.0038 |  | 0 | 1024.0038 | Works |  |  | Post
1.1.8 |  | 绿建工程 | 38 |  | 0 | 38 | Works |  |  | Post
|  | 废弃物绿色处理 | 1 |  | 0 | 1 | Works |  |  | Post
|  | 雨洪管理设施 | 4 |  | 0 | 4 | Works |  |  | Post
|  | LEED认证增量措施 | 33 |  | 0 | 33 | Works |  |  | Post
1.2 |  | 2#海关卡口 | 481.6195 |  | 0 | 481.6195 | Works |  |  | Post
1.2.1 |  | 地基处理 | 3.3215 |  | 0 | 3.3215 | Works |  |  | Post
1.2.2 |  | 土建工程 | 455.52 |  | 0 | 455.52 | Works |  |  | Post
1.2.3 |  | 给排水工程 | 2.847 |  | 0 | 2.847 | Works |  |  | Post
1.2.4 |  | 暖通工程 | 3.796 |  | 0 | 3.796 | Works |  |  | Post
1.2.5 |  | 电气工程 | 8.541 |  | 0 | 8.541 | Works |  |  | Post
1.2.6 |  | 抗震支架 | 5.694 |  | 0 | 5.694 | Works |  |  | Post
1.2.7 |  | 标识标牌 | 1.9 |  | 0 | 1.9 | Works |  |  | Post
1.4 |  | 海关围网 | 463.8 |  | 0 | 463.8 | Works |  |  | Post
HGAC-CW02 | Bonded Logistics Warehouses (1) | Bonded Logistics Warehoue M01 (20,396 m2) | 13277.6977 | 1867.468 | 1867.468 | 13277.6977 | Works | NCT | 18 | Prior | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.8 | Bonded Logistics Warehouse (2) |  | 13277.6977 | 1867.468 | 1867.468 | 13277.6977 | Works |  |  | Post
2.8.1 | Bonded Logistics Warehouse (3) |  | 9630.4162 | 1354.4889 | 1354.4889 | 9630.4162 | Works |  |  | Post
2.8.2 | Bonded Logistics Warehouse (4) |  | 32.5069 | 4.572 | 4.572 | 32.5069 | Works |  |  | Post
2.8.3 | Bonded Logistics Warehouse (5) |  | 292.5619 | 41.1479 | 41.1479 | 292.5619 | Works |  |  | Post
2.8.4 | Bonded Logistics Warehouse (6) |  | 227.5482 | 32.004 | 32.004 | 227.5482 | Works |  |  | Post
2.8.5 | Bonded Logistics Warehouse (7) |  | 503.8566 | 70.8659 | 70.8659 | 503.8566 | Works |  |  | Post
2.8.6 | Bonded Logistics Warehouse (8) |  | 138.8447 | 19.5281 | 19.5281 | 138.8447 | Works |  |  | Post
2.8.7 | Bonded Logistics Warehouse (9) |  | 507.92 | 71.4374 | 71.4374 | 507.92 | Works |  |  | Post
| Bonded Logistics Warehouse (10) |  | 1881.0431 | 264.563 | 264.563 | 1881.0431 | Works |  |  | Post
2.8.8 | Bonded Logistics Warehouse (11) |  | 63 | 8.8608 | 8.8608 | 63 | Works |  |  | Post
| Bonded Logistics Warehouse (12) |  | 1 | 0.14065 | 0.14065 | 1 | Works |  |  | Post
| Bonded Logistics Warehouse (13) |  | 11 | 1.5471 | 1.5471 | 11 | Works |  |  | Post
| Bonded Logistics Warehouse (14) |  | 51 | 7.173 | 7.173 | 51 | Works |  |  | Post
HGAC-CW03 | Bonded Logistics Warehouses (2) | Bonded Logistics Warehouse J01 / K010, Elevated Platform #3 (42,780 m2) | 25772.9634 | 3624.8894 | 3624.8894 | 25772.9634 | Works | NCT | 18 | Prior | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15 | Bonded Logistics Warehouse (16) |  | 11277.3601 | 1586.1266 | 1586.1266 | 11277.3601 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.1 | Bonded Logistics Warehouse (17) |  | 8671.015 | 1219.552 | 1219.552 | 8671.015 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.2 | Bonded Logistics Warehouse (18) |  | 29.2685 | 4.1165 | 4.1165 | 29.2685 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.3 | Bonded Logistics Warehouse (19) |  | 263.4163 | 37.0487 | 37.0487 | 263.4163 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.4 | Bonded Logistics Warehouse (20) |  | 204.8794 | 28.8157 | 28.8157 | 204.8794 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.5 | Bonded Logistics Warehouse (21) |  | 453.6614 | 63.8061 | 63.8061 | 453.6614 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.6 | Bonded Logistics Warehouse (22) |  | 125.0127 | 17.5827 | 17.5827 | 125.0127 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.15.7 | Bonded Logistics Warehouse (23) |  | 457.32 | 64.3207 | 64.3207 | 457.32 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (24) |  | 1015.7868 | 142.8673 | 142.8673 | 1015.7868 | Works |  |  | Post
2.15.8 | Bonded Logistics Warehouse (25) |  | 57 | 8.0169 | 8.0169 | 57 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (26) |  | 1 | 0.14065 | 0.14065 | 1 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (27) |  | 9 | 1.2658 | 1.2658 | 9 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (28) |  | 47 | 6.6104 | 6.6104 | 47 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16 | Bonded Logistics Warehouse (29) |  | 11277.3601 | 1586.1266 | 1586.1266 | 11277.3601 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.1 | Bonded Logistics Warehouse (30) |  | 8671.015 | 1219.552 | 1219.552 | 8671.015 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.2 | Bonded Logistics Warehouse (31) |  | 29.2685 | 4.1165 | 4.1165 | 29.2685 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.3 | Bonded Logistics Warehouse (32) |  | 263.4163 | 37.0487 | 37.0487 | 263.4163 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.4 | Bonded Logistics Warehouse (33) |  | 204.8794 | 28.8157 | 28.8157 | 204.8794 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.5 | Bonded Logistics Warehouse (34) |  | 453.6614 | 63.8061 | 63.8061 | 453.6614 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.6 | Bonded Logistics Warehouse (35) |  | 125.0127 | 17.5827 | 17.5827 | 125.0127 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.16.7 | Bonded Logistics Warehouse (36) |  | 457.32 | 64.3207 | 64.3207 | 457.32 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (37) |  | 1015.7868 | 142.8673 | 142.8673 | 1015.7868 | Works |  |  | Post
2.16.8 | Bonded Logistics Warehouse (38) |  | 57 | 8.0169 | 8.0169 | 57 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (39) |  | 1 | 0.14065 | 0.14065 | 1 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (40) |  | 9 | 1.2658 | 1.2658 | 9 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
| Bonded Logistics Warehouse (41) |  | 47 | 6.6104 | 6.6104 | 47 | Works | NCT | 18个月 | Post | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
2.18 | Bonded Logistics Warehouse (42) |  | 4178.7488 | 587.7284 | 587.7284 | 4178.7488 | Works |  |  | Post
2.18.1 | Bonded Logistics Warehouse (43) |  | 4053.3863 | 570.0965 | 570.0965 | 4053.3863 | Works |  |  | Post
2.18.2 | Bonded Logistics Warehouse (44) |  | 125.3625 | 17.6319 | 17.6319 | 125.3625 | Works |  |  | Post
HGAC-CW04 | Bonded Logistics Warehouses (3) | Bonded Logistics Warehouse H01 / H02 / E05 and Elevated Platform #2 (121,805 m2) | 54208.0131 | 7624.1931 | 7624.1931 | 54208.0131 | Works | IOCT | 18 | Prior | 是 |  |  | 2027.3 | 2027.4 | 2027.5 | 2028.12
2.1 | Bonded Logistics Warehouse (46) |  | 15502.4051 | 2180.3664 | 2180.3664 | 15502.4051 | Works |  |  | Post
2.10.1 | Bonded Logistics Warehouse (47) |  | 12124.8594 | 1705.3248 | 1705.3248 | 12124.8594 | Works |  |  | Post
2.10.2 | Bonded Logistics Warehouse (48) |  | 40.9267 | 5.7562 | 5.7562 | 40.9267 | Works |  |  | Post
2.10.3 | Bonded Logistics Warehouse (49) |  | 368.3405 | 51.806 | 51.806 | 368.3405 | Works |  |  | Post
2.10.4 | Bonded Logistics Warehouse (50) |  | 286.487 | 40.2935 | 40.2935 | 286.487 | Works |  |  | Post
2.10.5 | Bonded Logistics Warehouse (51) |  | 634.3642 | 89.2214 | 89.2214 | 634.3642 | Works |  |  | Post
2.10.6 | Bonded Logistics Warehouse (52) |  | 174.8079 | 24.5862 | 24.5862 | 174.8079 | Works |  |  | Post
2.10.7 | Bonded Logistics Warehouse (53) |  | 639.48 | 89.9409 | 89.9409 | 639.48 | Works |  |  | Post
| Bonded Logistics Warehouse (54) |  | 1161.1395 | 163.3108 | 163.3108 | 1161.1395 | Works |  |  | Post
2.10.8 | Bonded Logistics Warehouse (55) |  | 72 | 10.1266 | 10.1266 | 72 | Works |  |  | Post
| Bonded Logistics Warehouse (56) |  | 1 | 0.14065 | 0.14065 | 1 | Works |  |  | Post
| Bonded Logistics Warehouse (57) |  | 13 | 1.8284 | 1.8284 | 13 | Works |  |  | Post
| Bonded Logistics Warehouse (58) |  | 58 | 8.1575 | 8.1575 | 58 | Works |  |  | Post
2.11 | Bonded Logistics Warehouse (59) |  | 15296.8552 | 2151.4564 | 2151.4564 | 15296.8552 | Works |  |  | Post
2.11.1 | Bonded Logistics Warehouse (60) |  | 12124.8594 | 1705.3248 | 1705.3248 | 12124.8594 | Works |  |  | Post
2.11.2 | Bonded Logistics Warehouse (61) |  | 40.9267 | 5.7562 | 5.7562 | 40.9267 | Works |  |  | Post
2.11.3 | Bonded Logistics Warehouse (62) |  | 368.3405 | 51.806 | 51.806 | 368.3405 | Works |  |  | Post
2.11.4 | Bonded Logistics Warehouse (63) |  | 286.487 | 40.2935 | 40.2935 | 286.487 | Works |  |  | Post
2.11.5 | Bonded Logistics Warehouse (64) |  | 634.3642 | 89.2214 | 89.2214 | 634.3642 | Works |  |  | Post
2.11.6 | Bonded Logistics Warehouse (65) |  | 174.8079 | 24.5862 | 24.5862 | 174.8079 | Works |  |  | Post
2.11.7 | Bonded Logistics Warehouse (66) |  | 639.48 | 89.9409 | 89.9409 | 639.48 | Works |  |  | Post
| Bonded Logistics Warehouse (67) |  | 955.5896 | 134.4008 | 134.4008 | 955.5896 | Works |  |  | Post
2.11.8 | Bonded Logistics Warehouse (68) |  | 72 | 10.1266 | 10.1266 | 72 | Works |  |  | Post
| Bonded Logistics Warehouse (69) |  | 1 | 0.14065 | 0.14065 | 1 | Works |  |  | Post
| Bonded Logistics Warehouse (70) |  | 13 | 1.8284 | 1.8284 | 13 | Works |  |  | Post
| Bonded Logistics Warehouse (71) |  | 58 | 8.1575 | 8.1575 | 58 | Works |  |  | Post
2.9 | Bonded Logistics Warehouse (72) |  | 13789.8727 | 1939.5039 | 1939.5039 | 13789.8727 | Works |  |  | Post
2.9.1 | Bonded Logistics Warehouse (73) |  | 10541.2786 | 1482.599 | 1482.599 | 10541.2786 | Works |  |  | Post
2.9.2 | Bonded Logistics Warehouse (74) |  | 35.5814 | 5.0044 | 5.0044 | 35.5814 | Works |  |  | Post
2.9.3 | Bonded Logistics Warehouse (75) |  | 320.233 | 45.0398 | 45.0398 | 320.233 | Works |  |  | Post
2.9.4 | Bonded Logistics Warehouse (76) |  | 249.0701 | 35.031 | 35.031 | 249.0701 | Works |  |  | Post
2.9.5 | Bonded Logistics Warehouse (77) |  | 551.5123 | 77.5685 | 77.5685 | 551.5123 | Works |  |  | Post
2.9.6 | Bonded Logistics Warehouse (78) |  | 151.9769 | 21.3751 | 21.3751 | 151.9769 | Works |  |  | Post
2.9.7 | Bonded Logistics Warehouse (79) |  | 555.96 | 78.1941 | 78.1941 | 555.96 | Works |  |  | Post
| Bonded Logistics Warehouse (80) |  | 1319.2604 | 185.55 | 185.55 | 1319.2604 | Works |  |  | Post
2.9.8 | Bonded Logistics Warehouse (81) |  | 65 | 9.1421 | 9.1421 | 65 | Works |  |  | Post
| Bonded Logistics Warehouse (82) |  | 1 | 0.14065 | 0.14065 | 1 | Works |  |  | Post
| Bonded Logistics Warehouse (83) |  | 11 | 1.5471 | 1.5471 | 11 | Works |  |  | Post
| Bonded Logistics Warehouse (84) |  | 53 | 7.4543 | 7.4543 | 53 | Works |  |  | Post
2.17 | Bonded Logistics Warehouse (85) |  | 9618.88 | 1352.8664 | 1352.8664 | 9618.88 | Works |  |  | Post
2.17.1 | Bonded Logistics Warehouse (86) |  | 9330.3136 | 1312.2804 | 1312.2804 | 9330.3136 | Works |  |  | Post
2.17.2 | Bonded Logistics Warehouse (87) |  | 288.5664 | 40.586 | 40.586 | 288.5664 | Works |  |  | Post
HGAC-CW05 | Bonded Logistics Warehouses (4) | Bonded Logistics Warehouse H03 / H04 / L01 (100,098 m2) | 47558.926 | 6689.0191 | 6689.0191 | 47558.926 | Works | IOCT | 18 | Prior | 是 |  |  | 2027.3 | 2027.4 | 2027.5 | 2028.12
2.12 | H03 物流仓库 |  | 15098.9985 | 2123.6285 | 2123.6285 | 15098.9985 | Works |  |  | Post
2.12.1 | 土建工程 |  | 12124.8594 | 1705.3248 | 1705.3248 | 12124.8594 | Works |  |  | Post
2.12.2 | 给排水工程 |  | 40.9267 | 5.7562 | 5.7562 | 40.9267 | Works |  |  | Post
2.12.3 | 电气工程 |  | 368.3405 | 51.806 | 51.806 | 368.3405 | Works |  |  | Post
2.12.4 | 暖通工程 |  | 286.487 | 40.2935 | 40.2935 | 286.487 | Works |  |  | Post
2.12.5 | 消防工程 |  | 634.3642 | 89.2214 | 89.2214 | 634.3642 | Works |  |  | Post
2.12.6 | 设备工程 |  | 174.8079 | 24.5862 | 24.5862 | 174.8079 | Works |  |  | Post
2.12.7 | 场平工程 |  | 639.48 | 89.9409 | 89.9409 | 639.48 | Works |  |  | Post
| 室外工程 |  | 757.7328 | 106.5728 | 106.5728 | 757.7328 | Works |  |  | Post
2.12.8 | 绿建工程 |  | 72 | 10.1266 | 10.1266 | 72 | Works |  |  | Post
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 | Works |  |  | Post
| 雨洪管理设施 |  | 13 | 1.8284 | 1.8284 | 13 | Works |  |  | Post
| LEED认证增量措施 |  | 58 | 8.1575 | 8.1575 | 58 | Works |  |  | Post
2.13 | H04 物流仓库 |  | 15276.6249 | 2148.6111 | 2148.6111 | 15276.6249 | Works |  |  | Post
2.13.1 | 土建工程 |  | 12124.8594 | 1705.3248 | 1705.3248 | 12124.8594 | Works |  |  | Post
2.13.2 | 给排水工程 |  | 40.9267 | 5.7562 | 5.7562 | 40.9267 | Works |  |  | Post
2.13.3 | 电气工程 |  | 368.3405 | 51.806 | 51.806 | 368.3405 | Works |  |  | Post
2.13.4 | 暖通工程 |  | 286.487 | 40.2935 | 40.2935 | 286.487 | Works |  |  | Post
2.13.5 | 消防工程 |  | 634.3642 | 89.2214 | 89.2214 | 634.3642 | Works |  |  | Post
2.13.6 | 设备工程 |  | 174.8079 | 24.5862 | 24.5862 | 174.8079 | Works |  |  | Post
2.13.7 | 场平工程 |  | 639.48 | 89.9409 | 89.9409 | 639.48 | Works |  |  | Post
| 室外工程 |  | 935.3592 | 131.5554 | 131.5554 | 935.3592 | Works |  |  | Post
2.13.8 | 绿建工程 |  | 72 | 10.1266 | 10.1266 | 72 | Works |  |  | Post
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 | Works |  |  | Post
| 雨洪管理设施 |  | 13 | 1.8284 | 1.8284 | 13 | Works |  |  | Post
| LEED认证增量措施 |  | 58 | 8.1575 | 8.1575 | 58 | Works |  |  | Post
2.14 | L01 物流仓库 |  | 17183.3027 | 2416.7796 | 2416.7796 | 17183.3027 | Works |  |  | Post
2.14.1 | 土建工程 |  | 13708.4402 | 1928.0507 | 1928.0507 | 13708.4402 | Works |  |  | Post
2.14.2 | 给排水工程 |  | 46.272 | 6.508 | 6.508 | 46.272 | Works |  |  | Post
2.14.3 | 电气工程 |  | 416.448 | 58.5722 | 58.5722 | 416.448 | Works |  |  | Post
2.14.4 | 暖通工程 |  | 323.904 | 45.5561 | 45.5561 | 323.904 | Works |  |  | Post
2.14.5 | 消防工程 |  | 717.216 | 100.8743 | 100.8743 | 717.216 | Works |  |  | Post
2.14.6 | 设备工程 |  | 197.6389 | 27.7973 | 27.7973 | 197.6389 | Works |  |  | Post
2.14.7 | 场平工程 |  | 723 | 101.6878 | 101.6878 | 723 | Works |  |  | Post
| 室外工程 |  | 972.3836 | 136.7628 | 136.7628 | 972.3836 | Works |  |  | Post
2.14.8 | 绿建工程 |  | 78 | 10.9705 | 10.9705 | 78 | Works |  |  | Post
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 | Works |  |  | Post
| 雨洪管理设施 |  | 14 | 1.9691 | 1.9691 | 14 | Works |  |  | Post
| LEED认证增量措施 |  | 63 | 8.8608 | 8.8608 | 63 | Works |  |  | Post
HGAC-CW06 | Bonded Processing Warehouses | Bonded Processing Warehouse E01 / E02 / E03 / E04 (57,184 m2) | 23398.367 | 3290.9096 | 3290.9096 | 23398.367 | Works | NCT | 18 | Prior | 是 |  |  | 2026.3 | 2026.4 | 2026.5 | 2027.12
2.4 | E01 物流仓库 |  | 5921.3919 | 832.8259 | 832.8259 | 5921.3919 | Works |  |  | Post
2.4.1 | 土建工程 |  | 3574 | 502.6723 | 502.6723 | 3574 | Works |  |  | Post
2.4.2 | 给排水工程 |  | 18.2989 | 2.5737 | 2.5737 | 18.2989 | Works |  |  | Post
2.4.3 | 电气工程 |  | 164.6899 | 23.1631 | 23.1631 | 164.6899 | Works |  |  | Post
2.4.4 | 暖通工程 |  | 128.0922 | 18.0158 | 18.0158 | 128.0922 | Works |  |  | Post
2.4.5 | 消防工程 |  | 283.6326 | 39.8921 | 39.8921 | 283.6326 | Works |  |  | Post
2.4.6 | 设备工程 |  | 78.1589 | 10.9928 | 10.9928 | 78.1589 | Works |  |  | Post
2.4.7 | 场平工程 |  | 571.84 | 80.4276 | 80.4276 | 571.84 | Works |  |  | Post
| 室外工程 |  | 1036.6793 | 145.8058 | 145.8058 | 1036.6793 | Works |  |  | Post
2.4.8 | 绿建工程 |  | 66 | 9.2827 | 9.2827 | 66 | Works |  |  | Post
| 废弃物绿色处理 |  | 2 | 0.28129 | 0.28129 | 2 | Works |  |  | Post
| 雨洪管理设施 |  | 11 | 1.5471 | 1.5471 | 11 | Works |  |  | Post
| LEED认证增量措施 |  | 53 | 7.4543 | 7.4543 | 53 | Works |  |  | Post
2.5 | E02 物流仓库 |  | 5952.1709 | 837.1548 | 837.1548 | 5952.1709 | Works |  |  | Post
2.5.1 | 土建工程 |  | 3574 | 502.6723 | 502.6723 | 3574 | Works |  |  | Post
2.5.2 | 给排水工程 |  | 18.2989 | 2.5737 | 2.5737 | 18.2989 | Works |  |  | Post
2.5.3 | 电气工程 |  | 164.6899 | 23.1631 | 23.1631 | 164.6899 | Works |  |  | Post
2.5.4 | 暖通工程 |  | 128.0922 | 18.0158 | 18.0158 | 128.0922 | Works |  |  | Post
2.5.5 | 消防工程 |  | 283.6326 | 39.8921 | 39.8921 | 283.6326 | Works |  |  | Post
2.5.6 | 设备工程 |  | 78.1589 | 10.9928 | 10.9928 | 78.1589 | Works |  |  | Post
2.5.7 | 场平工程 |  | 571.84 | 80.4276 | 80.4276 | 571.84 | Works |  |  | Post
| 室外工程 |  | 1068.4583 | 150.2754 | 150.2754 | 1068.4583 | Works |  |  | Post
2.5.8 | 绿建工程 |  | 65 | 9.1421 | 9.1421 | 65 | Works |  |  | Post
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 | Works |  |  | Post
| 雨洪管理设施 |  | 11 | 1.5471 | 1.5471 | 11 | Works |  |  | Post
| LEED认证增量措施 |  | 53 | 7.4543 | 7.4543 | 53 | Works |  |  | Post
2.6 | E03 物流仓库 |  | 5747.9617 | 808.4334 | 808.4334 | 5747.9617 | Works |  |  | Post
2.6.1 | 土建工程 |  | 3574 | 502.6723 | 502.6723 | 3574 | Works |  |  | Post
2.6.2 | 给排水工程 |  | 18.2989 | 2.5737 | 2.5737 | 18.2989 | Works |  |  | Post
2.6.3 | 电气工程 |  | 164.6899 | 23.1631 | 23.1631 | 164.6899 | Works |  |  | Post
2.6.4 | 暖通工程 |  | 128.0922 | 18.0158 | 18.0158 | 128.0922 | Works |  |  | Post
2.6.5 | 消防工程 |  | 283.6326 | 39.8921 | 39.8921 | 283.6326 | Works |  |  | Post
2.6.6 | 设备工程 |  | 78.1589 | 10.9928 | 10.9928 | 78.1589 | Works |  |  | Post
2.6.7 | 场平工程 |  | 571.84 | 80.4276 | 80.4276 | 571.84 | Works |  |  | Post
| 室外工程 |  | 864.2492 | 121.554 | 121.554 | 864.2492 | Works |  |  | Post
2.6.8 | 绿建工程 |  | 65 | 9.1421 | 9.1421 | 65 | Works |  |  | Post
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 | Works |  |  | Post
| 雨洪管理设施 |  | 11 | 1.5471 | 1.5471 | 11 | Works |  |  | Post
| LEED认证增量措施 |  | 53 | 7.4543 | 7.4543 | 53 | Works |  |  | Post
2.7 | E04 物流仓库 |  | 5776.8425 | 812.4954 | 812.4954 | 5776.8425 | Works |  |  | Post
2.7.1 | 土建工程 |  | 3574 | 502.6723 | 502.6723 | 3574 | Works |  |  | Post
2.7.2 | 给排水工程 |  | 18.2989 | 2.5737 | 2.5737 | 18.2989 | Works |  |  | Post
2.7.3 | 电气工程 |  | 164.6899 | 23.1631 | 23.1631 | 164.6899 | Works |  |  | Post
2.7.4 | 暖通工程 |  | 128.0922 | 18.0158 | 18.0158 | 128.0922 | Works |  |  | Post
2.7.5 | 消防工程 |  | 283.6326 | 39.8921 | 39.8921 | 283.6326 | Works |  |  | Post
2.7.6 | 设备工程 |  | 78.1589 | 10.9928 | 10.9928 | 78.1589 | Works |  |  | Post
2.7.7 | 场平工程 |  | 571.84 | 80.4276 | 80.4276 | 571.84 | Works |  |  | Post
| 室外工程 |  | 893.13 | 125.616 | 125.616 | 893.13 | Works |  |  | Post
2.7.8 | 绿建工程 |  | 65 | 9.1421 | 9.1421 | 65 | Works |  |  | Post
| 废弃物绿色处理 |  | 1 | 0.14065 | 0.14065 | 1 | Works |  |  | Post
| 雨洪管理设施 |  | 11 | 1.5471 | 1.5471 | 11 | Works |  |  | Post
| LEED认证增量措施 |  | 53 | 7.4543 | 7.4543 | 53 | Works |  |  | Post
HGAC-CW07 | Auxiliary Facilities | Contrainer Truck Ramp #3 / #4 / #5, Guard Station, Equipment Room | 3292.1052 | 463.0246 | 463.0246 | 3292.1052 | Works | NCT | 12 | Prior |  |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.5
Total |  |  | 174384.8256 | 967.1946 | 967.1946 | 174384.8256
Component 2: | Trade and Freight Service Facilities
HGAC-CW08 | Trade and Freight Service Facilities | (1) Duty-Free Service Center S01 (10,450 m2); (2) Comprehensive Office Building W01 (39,432 m2) | 28051.0846 | 3945.3002 | 3945.3002 | 28051.0846 | Works | NCT | 18 | Prior | 是 |  |  | 2025.3 | 2025.4 | 2025.5 | 2026.12
3.2 | S01 免税服务中心 |  | 8098.2373 | 1138.9926 | 1138.9926 | 8098.2373
3.2.1 | 土建工程 |  | 4284.5 | 602.602 | 602.602 | 4284.5
3.2.2 | 给排水工程 |  | 26.125 | 3.6744 | 3.6744 | 26.125
3.2.3 | 电气工程 |  | 151.525 | 21.3115 | 21.3115 | 151.525
3.2.4 | 暖通工程 |  | 120.175 | 16.9023 | 16.9023 | 120.175
3.2.5 | 消防工程 |  | 146.3 | 20.5767 | 20.5767 | 146.3
3.2.6 | 设备工程 |  | 41.8 | 5.879 | 5.879 | 41.8
3.2.7 | 场平工程 |  | 209 | 29.3952 | 29.3952 | 209
| 室外工程 |  | 2754.8123 | 387.456 | 387.456 | 2754.8123
3.2.8 | 绿建工程 |  | 364 | 51.1955 | 51.1955 | 364
| 其他可再生能源措施 |  | 289 | 40.647 | 40.647 | 289
| 废弃物绿色处理 |  | 4 | 0.56259 | 0.56259 | 4
| 雨洪管理设施 |  | 4 | 0.56259 | 0.56259 | 4
| LEED认证增量措施 |  | 32 | 4.5007 | 4.5007 | 32
| 绿建三星增量措施 |  | 35 | 4.9226 | 4.9226 | 35
3.1 | W01 综合办公楼 |  | 19952.8472 | 2806.3076 | 2806.3076 | 19952.8472
3.1.1 | 土建工程 |  | 14787.06 | 2079.7553 | 2079.7553 | 14787.06
3.1.2 | 给排水工程 |  | 98.5804 | 13.865 | 13.865 | 98.5804
3.1.3 | 电气工程 |  | 571.7663 | 80.4172 | 80.4172 | 571.7663
3.1.4 | 暖通工程 |  | 453.4698 | 63.7792 | 63.7792 | 453.4698
3.1.5 | 消防工程 |  | 552.0502 | 77.6442 | 77.6442 | 552.0502
3.1.6 | 设备工程 |  | 157.7286 | 22.1841 | 22.1841 | 157.7286
3.1.7 | 场平工程 |  | 788.6432 | 110.9203 | 110.9203 | 788.6432
| 室外工程 |  | 2458.5486 | 345.7874 | 345.7874 | 2458.5486
3.1.8 | 绿建工程 |  | 85 | 11.955 | 11.955 | 85
| 废弃物绿色处理 |  | 4 | 0.56259 | 0.56259 | 4
| 雨洪管理设施 |  | 15 | 2.1097 | 2.1097 | 15
| LEED认证增量措施 |  | 66 | 9.2827 | 9.2827 | 66
Total |  |  | 28051.0846 | 3945.3002 | 3945.3002 | 28051.0846
Component 3: | Low-Carbon, Smart and Supporting Utilities
HGAC-CW09 | Roads | (1) Elevated Connecting Bridge #1 (Roadbed Area = 2,667 m2) / #2 (Roadbed Area = 2,375 m2); (2) 4 Roads in Phase II Area (Guihua Road No. 2 = 581.6 m / Guihua Road No. 3 = 990 m / Guihua Road No. 4 = 1,075 m / Guihua Road No. 5 = 354 m), and associated infrastructures | 20312.85 | 2856.9409 | 2856.9409 | 20312.85 | Works | NCT | 12 | Prior | 是 | Yes |  | 2024.9 | 2024.10 | 2024.11 | 2025.11 | 1st Works Contract
6 | 配套设施 |  | 2688.05 | 378.0661 | 378.0661 | 2688.05 |  |  |  | 前审 |  | Yes
6.1 | 1#高架联络道 |  | 399.45 | 56.1814 | 56.1814 | 399.45 |  |  |  | 前审 |  | Yes
6.1.1 | 路基 |  | 2145.6 | 301.7722 | 301.7722 | 2145.6 |  |  |  | 前审 |  | Yes
6.1.2 | 钢箱梁 |  | 143 | 20.1125 | 20.1125 | 143 |  |  |  | 前审 |  | Yes
6.1.3 | 装饰棚 |  | 6521.05 | 917.166 | 917.166 | 6521.05 |  |  |  | 前审 |  | Yes
6.2 | 2#高架联络道 |  | 6521.05 | 917.166 | 917.166 | 6521.05 |  |  |  | 前审 |  | Yes
6.2.1 | 路基 |  | 356.25 | 50.1055 | 50.1055 | 356.25 |  |  |  | 前审 |  | Yes
6.2.3 | 钢箱梁 |  | 5956.8 | 837.8059 | 837.8059 | 5956.8 |  |  |  | 前审 |  | Yes
6.2.4 | 装饰棚 |  | 208 | 29.2546 | 29.2546 | 208 |  |  |  | 前审 |  | Yes
6.3 | 规划二路 |  | 1959.93 | 275.6582 | 275.6582 | 1959.93 |  |  |  | 前审 |  | Yes
6.3.1 | 路基 |  | 1959.93 | 275.6582 | 275.6582 | 1959.93 |  |  |  | 前审 |  | Yes
6.4 | 规划三路 |  | 3742.2 | 526.3291 | 526.3291 | 3742.2 |  |  |  | 前审 |  | Yes
6.4.1 | 路基 |  | 3742.2 | 526.3291 | 526.3291 | 3742.2 |  |  |  | 前审 |  | Yes
6.5 | 规划四路 |  | 4063.5 | 571.519 | 571.519 | 4063.5 |  |  |  | 前审 |  | Yes
6.5.1 | 路基 |  | 4063.5 | 571.519 | 571.519 | 4063.5 |  |  |  | 前审 |  | Yes
6.6 | 规划五路 |  | 1338.12 | 188.2025 | 188.2025 | 1338.12 |  |  |  | 前审 |  | Yes
6.6.1 | 路基 |  | 1338.12 | 188.2025 | 188.2025 | 1338.12 |  |  |  | 前审 |  | Yes
HGAC-CW10 | Earth Works | Earth Works for Phase II | 20000 | 2812.9395 | 2812.9395 | 20000 | Works | NCT | 12 | Prior |  | Yes |  | 2024.9 | 2024.10 | 2024.11 | 2025.11
HGAC-GD01 | Roof-Top Photovolviac (1) | (1) Roof-Top Volvtaic for Phase II buildings including Customs Inspection Center (Phase I), International Express Center #1 / #2, Bonded Logistics Center (Type B) #1 / #2 / #3 and International Cargo Terminal, totalling 76,134 m2；(2) Phase II buildings including Bonded Logistics Warehouse P01 / R01 / R02 and Bonded Processing Warehouse Q01 / Q02, totalling 87,936 m2. (1) + (2) = 164,070 m2 | 5413.5455 | 761.3988 | 761.3988 | 5413.5455 | Goods | NCT | 12 | Prior | 是 | Yes |  | 2024.9 | 2024.10 | 2024.11 | 2025.11 | 1st Goods Contract
4.1.22 | 海关查验中心 | 11022 | 363.6765 | 51.15 | 363.6765 | 51.15
4.1.23 | 保税仓库1 | 11707 | 386.1825 | 54.3154 | 386.1825 | 54.3154
4.1.24 | 保税仓库2 | 11707 | 386.1825 | 54.3154 | 386.1825 | 54.3154
4.1.25 | 保税仓库3 | 11707 | 386.1825 | 54.3154 | 386.1825 | 54.3154
4.1.26 | 国际快件中心 | 18327 | 604.7635 | 85.0582 | 604.7635 | 85.0582
4.1.27 | 快件中心 | 11664 | 384.8185 | 54.1236 | 384.8185 | 54.1236
4.1.16 | P001 | 16128 | 532.1305 | 74.8425 | 532.1305 | 74.8425
4.1.17 | Q001 | 18768 | 619.256 | 87.0965 | 619.256 | 87.0965
4.1.18 | Q002 | 18768 | 619.256 | 87.0965 | 619.256 | 87.0965
4.1.19 | R001 | 17136 | 565.5485 | 79.5427 | 565.5485 | 79.5427
4.1.20 | R002 | 17136 | 565.5485 | 79.5427 | 565.5485 | 79.5427
HGAC-GD02 | Roof-Top Photovolviac (2) | All buildings in Phase II including Duty-Free Service Center S01, Comprehensive Office Building W01, Customs Inspection Warehouse T01, Bonded Logistics Warehouse E01~E04 / H01~H04 / J01 / K01 / L01 / M01, totalling 196,714 m2 | 6823.41 | 959.692 | 959.692 | 6823.41 | Goods | NCT | 40 | Post |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
4.1 | 光伏 | 370864.11m2 | 12236.96 | 1721.0914 | 1721.0914 | 12236.96 | Goods |  |  | Post
| 亚投行资金建设北区 | 196714.11 | 6823.4145 | 959.6926 | 959.6926 | 6823.4145 | Goods |  |  | Post
4.1.1 | 免税服务中心S01 | 5226.66 | 172.3755 | 24.2441 | 24.2441 | 172.3755 | Goods |  |  | Post
4.1.2 | 综合业务楼W01 | 4929.02 | 162.657 | 22.8772 | 22.8772 | 162.657 | Goods |  |  | Post
4.1.3 | E001 | 13104 | 432.388 | 60.8141 | 60.8141 | 432.388 | Goods |  |  | Post
4.1.4 | E002 | 13104 | 432.388 | 60.8141 | 60.8141 | 432.388 | Goods |  |  | Post
4.1.5 | E003 | 13104 | 432.388 | 60.8141 | 60.8141 | 432.388 | Goods |  |  | Post
4.1.6 | E004 | 13104 | 432.388 | 60.8141 | 60.8141 | 432.388 | Goods |  |  | Post
4.1.7 | E005 | 13104 | 432.388 | 60.8141 | 60.8141 | 432.388 | Goods |  |  | Post
4.1.8 | H001 | 15120 | 498.883 | 70.1664 | 70.1664 | 498.883 | Goods |  |  | Post
4.1.9 | H002 | 15120 | 498.883 | 70.1664 | 70.1664 | 498.883 | Goods |  |  | Post
4.1.10 | H003 | 15120 | 498.883 | 70.1664 | 70.1664 | 498.883 | Goods |  |  | Post
4.1.11 | H004 | 15120 | 498.883 | 70.1664 | 70.1664 | 498.883 | Goods |  |  | Post
4.1.12 | J001 | 10800 | 356.345 | 50.1188 | 50.1188 | 356.345 | Goods |  |  | Post
4.1.13 | K001 | 9360 | 308.7755 | 43.4283 | 43.4283 | 308.7755 | Goods |  |  | Post
4.1.14 | L001 | 17136 | 565.5485 | 79.5427 | 79.5427 | 565.5485 | Goods |  |  | Post
4.1.15 | M001 | 23262.43 | 767.591 | 107.9594 | 107.9594 | 767.591 | Goods |  |  | Post
4.1.21 | T001(海关查验仓库) | 10080 | 332.65 | 46.7862 | 46.7862 | 332.65 | Goods |  |  | Post
| 自建南区 | 87936 | 2901.75 | 408.1224 | 408.1224 | 2901.75 | Goods |  |  | Post
4.1.16 | P001(自建南区) | 16128 | 532.13 | 74.8425 | 74.8425 | 532.13 | Goods |  |  | Post
4.1.17 | Q001(自建南区) | 18768 | 619.26 | 87.097 | 87.097 | 619.26 | Goods |  |  | Post
4.1.18 | Q002(自建南区) | 18768 | 619.26 | 87.097 | 87.097 | 619.26 | Goods |  |  | Post
4.1.19 | R001(自建南区) | 17136 | 565.55 | 79.5429 | 79.5429 | 565.55 | Goods |  |  | Post
4.1.20 | R002(自建南区) | 17136 | 565.55 | 79.5429 | 79.5429 | 565.55 | Goods |  |  | Post
| 先行启动区 | 86214 | 2844.45 | 961.4906 | 961.4906 | 6823.41 | Goods |  |  | Post
4.1.22 | 海关查验中心(先行启动区) | 11022 | 363.68 | 51.1505 | 51.1505 | 363.68 | Goods |  |  | Post
4.1.23 | 保税仓库1 | 11707 | 386.18 | 54.315 | 54.315 | 386.18 | Goods |  |  | Post
4.1.24 | 保税仓库2 | 11707 | 386.18 | 54.315 | 54.315 | 386.18 | Goods |  |  | Post
4.1.25 | 保税仓库3 | 11707 | 386.18 | 54.315 | 54.315 | 386.18 | Goods |  |  | Post
4.1.26 | 国际快件中心 | 18327 | 604.76 | 85.0577 | 85.0577 | 604.76 | Goods |  |  | Post
4.1.27 | 国际快件中心 | 11664 | 384.82 | 54.1238 | 54.1238 | 384.82 | Goods |  |  | Post
HGAC-GD03 | Geothermal Energy for Business Logistics Center | Geothermal Energy for Business Logistics Center (Phase I) | 3364 | 473.1364 | 473.1364 | 3364 | Goods | NCT | 40 | Post |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
HGAC-GD04 | Smart Operations System | Hardware and Software for Smart Operations System | 4000 | 562.5879 | 562.5879 | 4000 | Goods | NCT | 40 | Post |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
| 4.2 | 智慧运营平台 | 4000 |  |  | 4000 | Goods |  |  | Post
HGAC-GD05 | Integrated Information System | Smart Customs Auxiliary Supervision Platform, Application Suppory Platform, Enterprise Customs Clearance Service Platform, Multi-Modal Transport Platform, Vehicle-Pedestrian Supervision and Control Equipment, Video Surveillance Equipment, Office Information Equipment, Safety / Energy Efficiency Monitoring / Firefighting Euipment, Digital Platform, Digital Warehouse, One-Stop Safety Inspection Area, Quanrantine Processing Area | 18818.98 | 2646.8326 | 2646.8326 | 18818.98 | Goods | ICOT | 40 | Prior | 是 |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
4.3 | 综合信息化平台 |  | 18818.98 | 2646.8326 | 2646.8326 | 18818.98
4.3.1 | 智慧海关辅助监管平台 |  | 3355 | 471.8706 | 471.8706 | 3355
4.3.2 | 应用支撑平台 |  | 920 | 129.3952 | 129.3952 | 920
4.3.3 | 企业通关服务平台 |  | 3160 | 444.4444 | 444.4444 | 3160
4.3.4 | 多式联运平台 |  | 2100 | 295.3586 | 295.3586 | 2100
4.3.5 | 园区车辆行人管控设备 |  | 341.9 | 48.0872 | 48.0872 | 341.9
4.3.6 | 园区视频设备 |  | 656.15 | 92.2855 | 92.2855 | 656.15
4.3.7 | 园区办公信息化设备 |  | 355.67 | 50.0239 | 50.0239 | 355.67
4.3.8 | 园区安全、能效、消防设备 |  | 211.46 | 29.7412 | 29.7412 | 211.46
4.3.9 | 数字化月台 |  | 33.6 | 4.7257 | 4.7257 | 33.6
4.3.10 | 数字化仓库 |  | 333.3 | 46.8776 | 46.8776 | 333.3
4.3.11 | 一站式安检区 |  | 7000 | 984.5288 | 984.5288 | 7000
4.3.12 | 检疫处理区 |  | 351.9 | 49.4937 | 49.4937 | 351.9
Total |  |  | 78732.7855 | 11073.5282 | 10600.3918 | 75368.7855
Component 4: | Capacity Building
HGAC-CS01 | Project Management | Project management technical support, training, study tours, knowledge product development and dissemination | 1000 | 140.647 | 140.647 | 1000 | Consulting Services | IOCS/QCBS | 51 | Prior |  | Yes |  | 2024.9 | 2024.10 | 2024.11 | 2028.12
HGAC-CS02 | Project M&E | External environmental monitoring, external resettlement monitoring, external social / gender monitoring, project performance monitoring, etc. | 1000 | 140.647 | 140.647 | 1000 | Consulting Services | IOCS/QCBS | 51 | Prior |  | Yes |  | 2024.9 | 2024.10 | 2024.11 | 2028.12
HGAC-CS03 | LEED Certification | LEED certification consulting services | 761 | 107.0323 | 107.0323 | 761 | Consulting Services | IOCS/QCBS | 42 | Prior |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
HGAC-CS04 | Green Building Certification | Green building certifcation consulting services | 116 | 16.315 | 16.315 | 116 | Consulting Services | NCS/CQS | 42 | Post |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
HGAC-CS05 | Other Consulting Services | Other capacity building consulting services | 1000 | 140.647 | 140.647 | 1000 | Consulting Services | IOCS/QCBS | 42 | Prior |  |  |  | 2025.6 | 2025.7 | 2025.8 | 2028.12
Total |  |  | 3877 | 545.2883 | 545.2883 | 3877
GRAND TOTAL |  |  | 285045.6957 | 40090.8152 | 40090.8152 | 285045.6957
|  | CW土建 | 242748.7602 | 34141.8791
|  | Goods货物 | 38419.9355 | 5403.6477
|  | Consulting Services咨询服务 | 3877 | 545.2883
|  |  | 285045.6957 | 40090.8152
提前采购
|  | CW-09 | 2856.9409
|  | CW-10 | 2812.9395
|  | GD-01 | 761.3988
|  | CS-01 | 140.647
|  | CS-02 | 140.647
6712.5732

## 20231229预算(绿化纳入单工) (hidden)
序号 | 工程和费用名称 | 估算价值(万元) |  |  |  | 技术经济指标 |  |  | 备 注 | 比例
|  | 建筑工程 | 设备及安装工程费 | 其他费用 | 合 计 | 室内面积或数量 |  | （万元）
一 | 工程费用 | 290573.79 | 54671.88 | 1462 | 346707.67 |  |  |  | （1+2+3） | 73.22%
1 | 海关业务基础设施 | 47980.39 | 360 | 0 | 48340.39 | 85816 |  |  |  | 10.21%
1.2 | 2#国际货站 | 11330.15 | 90 | 0 | 11420.15 | 19474 | ㎡ | 0.586 |  | 2.41%
1.2.1 | 场平 | 435.73 |  |  | 435.73 | 21786.6 | ㎡ | 0.02 |  | 0.09%
1.2.2 | 地基处理 | 97.37 |  |  | 97.37 | 19474 | ㎡ | 0.005 |  | 0.02%
1.2.3 | 基础工程 | 116.84 |  |  | 116.84 | 19474 | ㎡ | 0.006 |  | 0.02%
1.2.4 | 土建工程 | 4868.5 |  |  | 4868.5 | 19474 | ㎡ | 0.25 |  | 1.03%
1.2.5 | 装饰装修工程 | 2921.1 |  |  | 2921.1 | 19474 | ㎡ | 0.15 |  | 0.62%
1.2.6 | 给排水工程 | 292.11 |  |  | 292.11 | 19474 | ㎡ | 0.015 |  | 0.06%
1.2.7 | 暖通工程 | 778.96 |  |  | 778.96 | 19474 | ㎡ | 0.04 |  | 0.16%
1.2.8 | 电气工程 | 1363.18 |  |  | 1363.18 | 19474 | ㎡ | 0.07 |  | 0.29%
1.2.9 | 电梯工程 |  | 90 |  | 90 | 2 | 部 | 45 |  | 0.02%
1.2.10 | 抗震支架 | 116.84 |  |  | 116.84 | 19474 | ㎡ | 0.006 |  | 0.02%
1.2.11 | 标识标牌 | 38.95 |  |  | 38.95 | 19474 | ㎡ | 0.002 |  | 0.01%
1.2.12 | 绿化工程 | 300.56 |  |  | 300.56 | 10018.78 | ㎡ | 0.03 |  | 0.06%
1.3 | 3#国际货站 | 11330.15 | 90 | 0 | 11420.15 | 19474 | ㎡ | 0.586 |  | 2.41%
1.3.1 | 场平 | 435.73 |  |  | 435.73 | 21786.6 | ㎡ | 0.02 |  | 0.09%
1.3.2 | 地基处理 | 97.37 |  |  | 97.37 | 19474 | ㎡ | 0.005 |  | 0.02%
1.3.3 | 基础工程 | 116.84 |  |  | 116.84 | 19474 | ㎡ | 0.006 |  | 0.02%
1.3.4 | 土建工程 | 4868.5 |  |  | 4868.5 | 19474 | ㎡ | 0.25 |  | 1.03%
1.3.5 | 装饰装修工程 | 2921.1 |  |  | 2921.1 | 19474 | ㎡ | 0.15 |  | 0.62%
1.3.6 | 给排水工程 | 292.11 |  |  | 292.11 | 19474 | ㎡ | 0.015 |  | 0.06%
1.3.7 | 暖通工程 | 778.96 |  |  | 778.96 | 19474 | ㎡ | 0.04 |  | 0.16%
1.3.8 | 电气工程 | 1363.18 |  |  | 1363.18 | 19474 | ㎡ | 0.07 |  | 0.29%
1.3.9 | 电梯工程 |  | 90 |  | 90 | 2 | 部 | 45 |  | 0.02%
1.3.10 | 抗震支架 | 116.84 |  |  | 116.84 | 19474 | ㎡ | 0.006 |  | 0.02%
1.3.11 | 标识标牌 | 38.95 |  |  | 38.95 | 19474 | ㎡ | 0.002 |  | 0.01%
1.3.12 | 绿化工程 | 300.56 |  |  | 300.56 | 10018.78 | ㎡ | 0.03 |  | 0.06%
1.4 | 4#国际快件中心 | 24087.58 | 180 | 0 | 24267.58 | 45398 | ㎡ | 0.535 |  | 5.13%
1.4.1 | 场平 | 506.31 |  |  | 506.31 | 25315.4 | ㎡ | 0.02 |  | 0.11%
1.4.2 | 地基处理 | 226.99 |  |  | 226.99 | 45398 | ㎡ | 0.005 |  | 0.05%
1.4.3 | 基础工程 | 272.39 |  |  | 272.39 | 45398 | ㎡ | 0.006 |  | 0.06%
1.4.4 | 土建工程 | 10441.54 |  |  | 10441.54 | 45398 | ㎡ | 0.23 |  | 2.21%
1.4.5 | 装饰装修工程 | 5901.74 |  |  | 5901.74 | 45398 | ㎡ | 0.13 |  | 1.25%
1.4.6 | 给排水工程 | 680.97 |  |  | 680.97 | 45398 | ㎡ | 0.015 |  | 0.14%
1.4.7 | 暖通工程 | 1815.92 |  |  | 1815.92 | 45398 | ㎡ | 0.04 |  | 0.38%
1.4.8 | 电气工程 | 3177.86 |  |  | 3177.86 | 45398 | ㎡ | 0.07 |  | 0.67%
1.4.9 | 电梯工程 |  | 180 |  | 180 | 4 | 部 | 45 |  | 0.04%
1.4.10 | 抗震支架 | 272.39 |  |  | 272.39 | 45398 | ㎡ | 0.006 |  | 0.06%
1.4.11 | 标识标牌 | 90.8 |  |  | 90.8 | 45398 | ㎡ | 0.002 |  | 0.02%
1.4.12 | 绿化工程 | 700.68 |  |  | 700.68 | 23355.89 |  | 0.03 |  | 0.15%
1.5 | 2#海关卡口 | 496.26 |  |  | 496.26 | 949 | ㎡ | 0.523 |  | 0.1%
1.5.1 | 地基处理 | 3.32 |  |  | 3.32 | 949 | ㎡ | 0.004 |  | 0%
1.5.2 | 土建工程 | 455.52 |  |  | 455.52 | 949 | ㎡ | 0.48 |  | 0.1%
1.5.3 | 给排水工程 | 2.85 |  |  | 2.85 | 949 | ㎡ | 0.003 |  | 0%
1.5.4 | 暖通工程 | 3.8 |  |  | 3.8 | 949 | ㎡ | 0.004 |  | 0%
1.5.5 | 电气工程 | 8.54 |  |  | 8.54 | 949 | ㎡ | 0.009 |  | 0%
1.5.6 | 抗震支架 | 5.69 |  |  | 5.69 | 949 | ㎡ | 0.006 |  | 0%
1.5.7 | 标识标牌 | 1.9 |  |  | 1.9 | 949 | ㎡ | 0.002 |  | 0%
1.5.8 | 绿化工程 | 14.65 |  |  | 14.65 | 488.23 |  | 0.03 |  | 0%
1.6 | 4#海关卡口 | 272.45 |  |  | 272.45 | 521 | ㎡ | 0.523 |  | 0.06%
1.6.1 | 地基处理 | 1.82 |  |  | 1.82 | 521 | ㎡ | 0.004 |  | 0%
1.6.2 | 土建工程 | 250.08 |  |  | 250.08 | 521 | ㎡ | 0.48 |  | 0.05%
1.6.3 | 给排水工程 | 1.56 |  |  | 1.56 | 521 | ㎡ | 0.003 |  | 0%
1.6.4 | 暖通工程 | 2.08 |  |  | 2.08 | 521 | ㎡ | 0.004 |  | 0%
1.6.5 | 电气工程 | 4.69 |  |  | 4.69 | 521 | ㎡ | 0.009 |  | 0%
1.6.6 | 抗震支架 | 3.13 |  |  | 3.13 | 521 | ㎡ | 0.006 |  | 0%
1.6.7 | 标识标牌 | 1.04 |  |  | 1.04 | 521 | ㎡ | 0.002 |  | 0%
1.6.8 | 绿化工程 | 8.04 |  |  | 8.04 | 268.04 | ㎡ | 0.03 |  | 0%
1.7 | 海关围网 | 463.8 |  |  | 463.8 | 7730 | 延米 | 0.06 |  | 0.1%
2 | 保税仓储和加工 | 96278.3 | 360 | 0 | 96638.3 | 173680 |  |  |  | 20.41%
2.1 | 8#保税加工中心 | 20479.53 | 180 | 0 | 20659.53 | 39225 | ㎡ | 0.527 |  | 4.36%
2.1.1 | 场平 | 496.98 |  |  | 496.98 | 24849 | ㎡ | 0.02 |  | 0.1%
2.1.2 | 地基处理 | 196.13 |  |  | 196.13 | 39225 | ㎡ | 0.005 |  | 0.04%
2.1.3 | 基础工程 | 235.35 |  |  | 235.35 | 39225 | ㎡ | 0.006 |  | 0.05%
2.1.4 | 土建工程 | 9414 |  |  | 9414 | 39225 | ㎡ | 0.24 |  | 1.99%
2.1.5 | 装饰装修工程 | 4707 |  |  | 4707 | 39225 | ㎡ | 0.12 |  | 0.99%
2.1.6 | 给排水工程 | 588.38 |  |  | 588.38 | 39225 | ㎡ | 0.015 |  | 0.12%
2.1.7 | 暖通工程 | 1176.75 |  |  | 1176.75 | 39225 | ㎡ | 0.03 |  | 0.25%
2.1.8 | 电气工程 | 2745.75 |  |  | 2745.75 | 39225 | ㎡ | 0.07 |  | 0.58%
2.1.9 | 电梯工程 |  | 180 |  | 180 | 4 | 部 | 45 |  | 0.04%
2.1.10 | 抗震支架 | 235.35 |  |  | 235.35 | 39225 | ㎡ | 0.006 |  | 0.05%
2.1.11 | 标识标牌 | 78.45 |  |  | 78.45 | 39225 | ㎡ | 0.002 |  | 0.02%
2.1.12 | 绿化工程 | 605.4 |  |  | 605.4 | 20180.07 | ㎡ | 0.03 |  | 0.13%
2.2 | 9#保税加工中心 | 12021.04 | 180 | 0 | 12201.04 | 20936 | ㎡ | 0.583 |  | 2.58%
2.2.1 | 场平 | 497.16 |  |  | 497.16 | 24857.8 | ㎡ | 0.02 |  | 0.1%
2.2.2 | 地基处理 | 104.68 |  |  | 104.68 | 20936 | ㎡ | 0.005 |  | 0.02%
2.2.3 | 基础工程 | 146.55 |  |  | 146.55 | 20936 | ㎡ | 0.007 |  | 0.03%
2.2.4 | 土建工程 | 5443.36 |  |  | 5443.36 | 20936 | ㎡ | 0.26 |  | 1.15%
2.2.5 | 装饰装修工程 | 2931.04 |  |  | 2931.04 | 20936 | ㎡ | 0.14 |  | 0.62%
2.2.6 | 给排水工程 | 314.04 |  |  | 314.04 | 20936 | ㎡ | 0.015 |  | 0.07%
2.2.7 | 暖通工程 | 628.08 |  |  | 628.08 | 20936 | ㎡ | 0.03 |  | 0.13%
2.2.8 | 电气工程 | 1465.52 |  |  | 1465.52 | 20936 | ㎡ | 0.07 |  | 0.31%
2.2.9 | 电梯工程 |  | 180 |  | 180 | 4 | 部 | 45 |  | 0.04%
2.2.10 | 抗震支架 | 125.62 |  |  | 125.62 | 20936 | ㎡ | 0.006 |  | 0.03%
2.2.11 | 标识标牌 | 41.87 |  |  | 41.87 | 20936 | ㎡ | 0.002 |  | 0.01%
| 绿化工程 | 323.13 |  |  | 323.13 | 10770.93 | ㎡ | 0.03 |  | 0.07%
2.3 | 10#危险品库区 | 2890.95 | 0 | 0 | 2890.95 | 4500 | ㎡ | 0.642 |  | 0.61%
2.3.1 | 场平 | 99 |  |  | 99 | 4950 | ㎡ | 0.02 |  | 0.02%
2.3.2 | 地基处理 | 22.5 |  |  | 22.5 | 4500 | ㎡ | 0.005 |  | 0%
2.3.3 | 基础工程 | 31.5 |  |  | 31.5 | 4500 | ㎡ | 0.007 |  | 0.01%
2.3.4 | 土建工程 | 1170 |  |  | 1170 | 4500 | ㎡ | 0.26 |  | 0.25%
2.3.5 | 装饰装修工程 | 810 |  |  | 810 | 4500 | ㎡ | 0.18 |  | 0.17%
2.3.6 | 给排水工程 | 67.5 |  |  | 67.5 | 4500 | ㎡ | 0.015 |  | 0.01%
2.3.7 | 暖通工程 | 225 |  |  | 225 | 4500 | ㎡ | 0.05 |  | 0.05%
2.3.8 | 电气工程 | 360 |  |  | 360 | 4500 | ㎡ | 0.08 |  | 0.08%
2.3.9 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.3.10 | 抗震支架 | 27 |  |  | 27 | 4500 | ㎡ | 0.006 |  | 0.01%
2.3.11 | 标识标牌 | 9 |  |  | 9 | 4500 | ㎡ | 0.002 |  | 0%
| 绿化工程 | 69.45 |  |  | 69.45 | 2315.11 | ㎡ | 0.03 |  | 0.01%
2.4 | 11#保税物流中心 | 10339.38 | 0 | 0 | 10339.38 | 19884 | ㎡ | 0.52 |  | 2.18%
2.4.1 | 场平 | 209.79 |  |  | 209.79 | 10489.6 | ㎡ | 0.02 |  | 0.04%
2.4.1 | 地基处理 | 99.42 |  |  | 99.42 | 19884 | ㎡ | 0.005 |  | 0.02%
2.4.2 | 基础工程 | 119.3 |  |  | 119.3 | 19884 | ㎡ | 0.006 |  | 0.03%
2.4.3 | 土建工程 | 4772.16 |  |  | 4772.16 | 19884 | ㎡ | 0.24 |  | 1.01%
2.4.4 | 装饰装修工程 | 2386.08 |  |  | 2386.08 | 19884 | ㎡ | 0.12 |  | 0.5%
2.4.5 | 给排水工程 | 298.26 |  |  | 298.26 | 19884 | ㎡ | 0.015 |  | 0.06%
2.4.6 | 暖通工程 | 596.52 |  |  | 596.52 | 19884 | ㎡ | 0.03 |  | 0.13%
2.4.7 | 电气工程 | 1391.88 |  |  | 1391.88 | 19884 | ㎡ | 0.07 |  | 0.29%
2.4.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.4.9 | 抗震支架 | 119.3 |  |  | 119.3 | 19884 | ㎡ | 0.006 |  | 0.03%
2.4.10 | 标识标牌 | 39.77 |  |  | 39.77 | 19884 | ㎡ | 0.002 |  | 0.01%
| 绿化工程 | 306.89 |  |  | 306.89 | 10229.71 |  | 0.03 |  | 0.06%
2.5 | 12#保税物流中心 | 10339.38 | 0 | 0 | 10339.38 | 19884 | ㎡ | 0.52 |  | 2.18%
2.5.1 | 场平 | 209.79 |  |  | 209.79 | 10489.6 | ㎡ | 0.02 |  | 0.04%
2.5.2 | 地基处理 | 99.42 |  |  | 99.42 | 19884 | ㎡ | 0.005 |  | 0.02%
2.5.3 | 基础工程 | 119.3 |  |  | 119.3 | 19884 | ㎡ | 0.006 |  | 0.03%
2.5.4 | 土建工程 | 4772.16 |  |  | 4772.16 | 19884 | ㎡ | 0.24 |  | 1.01%
2.5.5 | 装饰装修工程 | 2386.08 |  |  | 2386.08 | 19884 | ㎡ | 0.12 |  | 0.5%
2.5.6 | 给排水工程 | 298.26 |  |  | 298.26 | 19884 | ㎡ | 0.015 |  | 0.06%
2.5.7 | 暖通工程 | 596.52 |  |  | 596.52 | 19884 | ㎡ | 0.03 |  | 0.13%
2.5.8 | 电气工程 | 1391.88 |  |  | 1391.88 | 19884 | ㎡ | 0.07 |  | 0.29%
2.5.9 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.5.10 | 抗震支架 | 119.3 |  |  | 119.3 | 19884 | ㎡ | 0.006 |  | 0.03%
2.5.11 | 标识标牌 | 39.77 |  |  | 39.77 | 19884 | ㎡ | 0.002 |  | 0.01%
| 绿化工程 | 306.89 |  |  | 306.89 | 10229.71 |  | 0.03 |  | 0.06%
2.6 | 13#保税物流中心 | 7313.74 | 0 | 0 | 7313.74 | 12591 | ㎡ | 0.581 |  | 1.54%
2.6.1 | 场平 | 257.31 |  |  | 257.31 | 12865.6 | ㎡ | 0.02 |  | 0.05%
2.6.2 | 地基处理 | 62.96 |  |  | 62.96 | 12591 | ㎡ | 0.005 |  | 0.01%
2.6.3 | 基础工程 | 88.14 |  |  | 88.14 | 12591 | ㎡ | 0.007 |  | 0.02%
2.6.4 | 土建工程 | 3147.75 |  |  | 3147.75 | 12591 | ㎡ | 0.25 |  | 0.66%
2.6.5 | 装饰装修工程 | 1888.65 |  |  | 1888.65 | 12591 | ㎡ | 0.15 |  | 0.4%
2.6.6 | 给排水工程 | 188.87 |  |  | 188.87 | 12591 | ㎡ | 0.015 |  | 0.04%
2.6.7 | 暖通工程 | 503.64 |  |  | 503.64 | 12591 | ㎡ | 0.04 |  | 0.11%
2.6.8 | 电气工程 | 881.37 |  |  | 881.37 | 12591 | ㎡ | 0.07 |  | 0.19%
2.6.9 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.6.10 | 抗震支架 | 75.55 |  |  | 75.55 | 12591 | ㎡ | 0.006 |  | 0.02%
2.6.11 | 标识标牌 | 25.18 |  |  | 25.18 | 12591 | ㎡ | 0.002 |  | 0.01%
| 绿化工程 | 194.33 |  |  | 194.33 | 6477.69 | ㎡ | 0.03 |  | 0.04%
2.7 | 14#保税物流中心 | 7313.74 | 0 | 0 | 7313.74 | 12591 | ㎡ | 0.581 |  | 1.54%
2.7.1 | 场平 | 257.31 |  |  | 257.31 | 12865.6 | ㎡ | 0.02 |  | 0.05%
2.7.2 | 地基处理 | 62.96 |  |  | 62.96 | 12591 | ㎡ | 0.005 |  | 0.01%
2.7.3 | 基础工程 | 88.14 |  |  | 88.14 | 12591 | ㎡ | 0.007 |  | 0.02%
2.7.4 | 土建工程 | 3147.75 |  |  | 3147.75 | 12591 | ㎡ | 0.25 |  | 0.66%
2.7.5 | 装饰装修工程 | 1888.65 |  |  | 1888.65 | 12591 | ㎡ | 0.15 |  | 0.4%
2.7.6 | 给排水工程 | 188.87 |  |  | 188.87 | 12591 | ㎡ | 0.015 |  | 0.04%
2.7.7 | 暖通工程 | 503.64 |  |  | 503.64 | 12591 | ㎡ | 0.04 |  | 0.11%
2.7.8 | 电气工程 | 881.37 |  |  | 881.37 | 12591 | ㎡ | 0.07 |  | 0.19%
2.7.9 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.7.10 | 抗震支架 | 75.55 |  |  | 75.55 | 12591 | ㎡ | 0.006 |  | 0.02%
2.7.11 | 标识标牌 | 25.18 |  |  | 25.18 | 12591 | ㎡ | 0.002 |  | 0.01%
| 绿化工程 | 194.33 |  |  | 194.33 | 6477.69 |  | 0.03 |  | 0.04%
2.8 | 15#保税物流中心 | 5751.26 | 0 | 0 | 5751.26 | 9908 | ㎡ | 0.58 |  | 1.21%
2.8.1 | 场平 | 198.48 |  |  | 198.48 | 9924.2 | ㎡ | 0.02 |  | 0.04%
2.8.2 | 地基处理 | 49.54 |  |  | 49.54 | 9908 | ㎡ | 0.005 |  | 0.01%
2.8.3 | 基础工程 | 69.36 |  |  | 69.36 | 9908 | ㎡ | 0.007 |  | 0.01%
2.8.4 | 土建工程 | 2477 |  |  | 2477 | 9908 | ㎡ | 0.25 |  | 0.52%
2.8.5 | 装饰装修工程 | 1486.2 |  |  | 1486.2 | 9908 | ㎡ | 0.15 |  | 0.31%
2.8.6 | 给排水工程 | 148.62 |  |  | 148.62 | 9908 | ㎡ | 0.015 |  | 0.03%
2.8.7 | 暖通工程 | 396.32 |  |  | 396.32 | 9908 | ㎡ | 0.04 |  | 0.08%
2.8.8 | 电气工程 | 693.56 |  |  | 693.56 | 9908 | ㎡ | 0.07 |  | 0.15%
2.8.9 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.8.10 | 抗震支架 | 59.45 |  |  | 59.45 | 9908 | ㎡ | 0.006 |  | 0.01%
2.8.11 | 标识标牌 | 19.82 |  |  | 19.82 | 9908 | ㎡ | 0.002 |  | 0%
| 绿化工程 | 152.92 |  |  | 152.92 | 5097.36 |  | 0.03 |  | 0.03%
2.9 | 16#保税物流中心 | 6609.76 | 0 | 0 | 6609.76 | 11387 | ㎡ | 0.58 |  | 1.4%
2.9.1 | 场平 | 228.1 |  |  | 228.1 | 11404.8 | ㎡ | 0.02 |  | 0.05%
2.9.2 | 地基处理 | 56.94 |  |  | 56.94 | 11387 | ㎡ | 0.005 |  | 0.01%
2.9.3 | 基础工程 | 79.71 |  |  | 79.71 | 11387 | ㎡ | 0.007 |  | 0.02%
2.9.4 | 土建工程 | 2846.75 |  |  | 2846.75 | 11387 | ㎡ | 0.25 |  | 0.6%
2.9.5 | 装饰装修工程 | 1708.05 |  |  | 1708.05 | 11387 | ㎡ | 0.15 |  | 0.36%
2.9.6 | 给排水工程 | 170.81 |  |  | 170.81 | 11387 | ㎡ | 0.015 |  | 0.04%
2.9.7 | 暖通工程 | 455.48 |  |  | 455.48 | 11387 | ㎡ | 0.04 |  | 0.1%
2.9.8 | 电气工程 | 797.09 |  |  | 797.09 | 11387 | ㎡ | 0.07 |  | 0.17%
2.9.9 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.9.10 | 抗震支架 | 68.32 |  |  | 68.32 | 11387 | ㎡ | 0.006 |  | 0.01%
2.9.11 | 标识标牌 | 22.77 |  |  | 22.77 | 11387 | ㎡ | 0.002 |  | 0%
| 绿化工程 | 175.75 |  |  | 175.75 | 5858.26 |  | 0.03 |  | 0.04%
2.1 | 17#保税物流中心 | 6609.76 | 0 | 0 | 6609.76 | 11387 | ㎡ | 0.58 |  | 1.4%
2.10.1 | 场平 | 228.1 |  |  | 228.1 | 11404.8 | ㎡ | 0.02 |  | 0.05%
2.10.2 | 地基处理 | 56.94 |  |  | 56.94 | 11387 | ㎡ | 0.005 |  | 0.01%
2.10.3 | 基础工程 | 79.71 |  |  | 79.71 | 11387 | ㎡ | 0.007 |  | 0.02%
2.10.4 | 土建工程 | 2846.75 |  |  | 2846.75 | 11387 | ㎡ | 0.25 |  | 0.6%
2.10.5 | 装饰装修工程 | 1708.05 |  |  | 1708.05 | 11387 | ㎡ | 0.15 |  | 0.36%
2.10.6 | 给排水工程 | 170.81 |  |  | 170.81 | 11387 | ㎡ | 0.015 |  | 0.04%
2.10.7 | 暖通工程 | 455.48 |  |  | 455.48 | 11387 | ㎡ | 0.04 |  | 0.1%
2.10.8 | 电气工程 | 797.09 |  |  | 797.09 | 11387 | ㎡ | 0.07 |  | 0.17%
2.10.9 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.10.10 | 抗震支架 | 68.32 |  |  | 68.32 | 11387 | ㎡ | 0.006 |  | 0.01%
2.10.11 | 标识标牌 | 22.77 |  |  | 22.77 | 11387 | ㎡ | 0.002 |  | 0%
| 绿化工程 | 175.75 |  |  | 175.75 | 5858.26 |  | 0.03 |  | 0.04%
2.11 | 18#保税物流中心 | 6609.76 | 0 | 0 | 6609.76 | 11387 | ㎡ | 0.58 |  | 1.4%
2.11.1 | 场平 | 228.1 |  |  | 228.1 | 11404.8 | ㎡ | 0.02 |  | 0.05%
2.11.2 | 地基处理 | 56.94 |  |  | 56.94 | 11387 | ㎡ | 0.005 |  | 0.01%
2.11.3 | 基础工程 | 79.71 |  |  | 79.71 | 11387 | ㎡ | 0.007 |  | 0.02%
2.11.4 | 土建工程 | 2846.75 |  |  | 2846.75 | 11387 | ㎡ | 0.25 |  | 0.6%
2.11.5 | 装饰装修工程 | 1708.05 |  |  | 1708.05 | 11387 | ㎡ | 0.15 |  | 0.36%
2.11.6 | 给排水工程 | 170.81 |  |  | 170.81 | 11387 | ㎡ | 0.015 |  | 0.04%
2.11.7 | 暖通工程 | 455.48 |  |  | 455.48 | 11387 | ㎡ | 0.04 |  | 0.1%
2.11.8 | 电气工程 | 797.09 |  |  | 797.09 | 11387 | ㎡ | 0.07 |  | 0.17%
2.11.9 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.11.10 | 抗震支架 | 68.32 |  |  | 68.32 | 11387 | ㎡ | 0.006 |  | 0.01%
2.11.11 | 标识标牌 | 22.77 |  |  | 22.77 | 11387 | ㎡ | 0.002 |  | 0%
| 绿化工程 | 175.75 |  |  | 175.75 | 5858.26 |  | 0.03 |  | 0.04%
3 | 贸易和货运服务设施 | 98900.47 | 810 | 0 | 99710.47 | 87525 |  |  |  | 21.06%
3.1 | 19#综合配套中心 | 60729.52 | 360 | 0 | 61089.52 |  | ㎡ |  |  | 12.9%
3.1.1 | 地上 | 39849.52 | 360 | 0 | 40209.52 | 57525 | ㎡ | 0.699 |  | 8.49%
3.1.1.1 | 场平 | 187 |  |  | 187 | 9350 | ㎡ | 0.02 |  | 0.04%
3.1.1.2 | 地基处理 | 287.63 |  |  | 287.63 | 57525 | ㎡ | 0.005 |  | 0.06%
3.1.1.3 | 基础工程 | 8053.5 |  |  | 8053.5 | 57525 | ㎡ | 0.14 |  | 1.7%
3.1.1.4 | 土建工程 | 14381.25 |  |  | 14381.25 | 57525 | ㎡ | 0.25 |  | 3.04%
3.1.1.5 | 装饰装修工程 | 8628.75 |  |  | 8628.75 | 57525 | ㎡ | 0.15 |  | 1.82%
3.1.1.6 | 给排水工程 | 747.83 |  |  | 747.83 | 57525 | ㎡ | 0.013 |  | 0.16%
3.1.1.7 | 暖通工程 | 2301 |  |  | 2301 | 57525 | ㎡ | 0.04 |  | 0.49%
3.1.1.8 | 电气工程 | 3451.5 |  |  | 3451.5 | 57525 | ㎡ | 0.06 |  | 0.73%
3.1.1.9 | 电梯工程 |  | 360 |  | 360 | 8 | 部 | 45 |  | 0.08%
3.1.1.10 | 抗震支架 | 345.15 |  |  | 345.15 | 57525 | ㎡ | 0.006 |  | 0.07%
3.1.1.11 | 标识标牌 | 115.05 |  |  | 115.05 | 57525 | ㎡ | 0.002 |  | 0.02%
| 绿化工程 | 1350.87 |  |  | 1350.87 | 45028.94 |  | 0.03 |  | 0.29%
3.1.2 | 地下 | 20880 | 0 | 0 | 20880 | 30000 | ㎡ | 0.696 |  | 4.41%
3.1.2.1 | 地基处理 | 150 |  |  | 150 | 30000 | ㎡ | 0.005 |  | 0.03%
3.1.2.2 | 基础工程 | 4200 |  |  | 4200 | 30000 | ㎡ | 0.14 |  | 0.89%
3.1.2.3 | 土建工程 | 7500 |  |  | 7500 | 30000 | ㎡ | 0.25 |  | 1.58%
3.1.2.4 | 装饰装修工程 | 4500 |  |  | 4500 | 30000 | ㎡ | 0.15 |  | 0.95%
3.1.2.5 | 给排水工程 | 390 |  |  | 390 | 30000 | ㎡ | 0.013 |  | 0.08%
3.1.2.6 | 暖通工程 | 1500 |  |  | 1500 | 30000 | ㎡ | 0.05 |  | 0.32%
3.1.2.7 | 电气工程 | 1800 |  |  | 1800 | 30000 | ㎡ | 0.06 |  | 0.38%
3.1.2.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
3.1.2.9 | 人防工程 | 600 |  |  |  | 15000 | ㎡ | 0.04 |  | 0%
3.1.2.10 | 抗震支架 | 180 |  |  | 180 | 30000 | ㎡ | 0.006 |  | 0.04%
3.1.2.11 | 标识标牌 | 60 |  |  | 60 | 30000 | ㎡ | 0.002 |  | 0.01%
3.2 | 21#商贸物流大楼 | 38170.95 | 450 | 0 | 38620.95 | 55000 | ㎡ |  |  | 8.16%
3.2.1 | 地上 | 24250.95 | 450 | 0 | 24700.95 | 35000 | ㎡ | 0.706 |  | 5.22%
3.2.1.1 | 场平 | 92.07 |  |  | 92.07 | 4603.74 | ㎡ | 0.02 |  | 0.02%
3.2.1.2 | 地基处理 | 175 |  |  | 175 | 35000 | ㎡ | 0.005 |  | 0.04%
3.2.1.3 | 基础工程 | 4900 |  |  | 4900 | 35000 | ㎡ | 0.14 |  | 1.03%
3.2.1.4 | 土建工程 | 8750 |  |  | 8750 | 35000 | ㎡ | 0.25 |  | 1.85%
3.2.1.5 | 装饰装修工程 | 5250 |  |  | 5250 | 35000 | ㎡ | 0.15 |  | 1.11%
3.2.1.6 | 给排水工程 | 455 |  |  | 455 | 35000 | ㎡ | 0.013 |  | 0.1%
3.2.1.7 | 暖通工程 | 1400 |  |  | 1400 | 35000 | ㎡ | 0.04 |  | 0.3%
3.2.1.8 | 电气工程 | 2100 |  |  | 2100 | 35000 | ㎡ | 0.06 |  | 0.44%
3.2.1.9 | 电梯工程 |  | 450 |  | 450 | 10 | 部 | 45 |  | 0.1%
3.2.1.10 | 抗震支架 | 210 |  |  | 210 | 35000 | ㎡ | 0.006 |  | 0.04%
3.2.1.11 | 标识标牌 | 70 |  |  | 70 | 35000 | ㎡ | 0.002 |  | 0.01%
3.2.1.12 | 绿化工程 | 848.87 |  |  | 848.87 | 28295.82 |  | 0.03 |  | 0.18%
3.2.2 | 地下 | 13920 | 0 | 0 | 13920 | 20000 | ㎡ | 0.696 |  | 2.94%
3.2.2.1 | 地基处理 | 100 |  |  | 100 | 20000 | ㎡ | 0.005 |  | 0.02%
3.2.2.2 | 基础工程 | 2800 |  |  | 2800 | 20000 | ㎡ | 0.14 |  | 0.59%
3.2.2.3 | 土建工程 | 5000 |  |  | 5000 | 20000 | ㎡ | 0.25 |  | 1.06%
3.2.2.4 | 装饰装修工程 | 3000 |  |  | 3000 | 20000 | ㎡ | 0.15 |  | 0.63%
3.2.2.5 | 给排水工程 | 260 |  |  | 260 | 20000 | ㎡ | 0.013 |  | 0.05%
3.2.2.6 | 暖通工程 | 1000 |  |  | 1000 | 20000 | ㎡ | 0.05 |  | 0.21%
3.2.2.7 | 电气工程 | 1200 |  |  | 1200 | 20000 | ㎡ | 0.06 |  | 0.25%
3.2.2.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
3.2.2.9 | 人防工程 | 400 |  |  |  | 10000 | ㎡ | 0.04 |  | 0%
3.2.2.10 | 抗震支架 | 120 |  |  | 120 | 20000 | ㎡ | 0.006 |  | 0.03%
3.2.2.11 | 标识标牌 | 40 |  |  | 40 | 20000 | ㎡ | 0.002 |  | 0.01%
4 | 信息化与相关设备 | 0 | 53141.88 | 0 | 53141.88 |  |  |  |  | 11.22%
4.1 | 弱电信息化工程 |  | 21102.9 |  | 21102.9 |  |  |  | 门禁系统、有线电视、会议系统、监控系统、消防报警系统等。 | 4.46%
4.1.1 | 2#国际货站 |  | 6371.89 |  | 6371.89 | 19474 | ㎡ | 0.327 |  | 1.35%
4.1.2 | 3#国际货站 |  | 6371.89 |  | 6371.89 | 19474 | ㎡ | 0.327 |  | 1.35%
4.1.3 | 4#国际快件中心 |  | 1634.33 |  | 1634.33 | 45398 | ㎡ | 0.036 |  | 0.35%
4.1.4 | 2#海关卡口 |  | 13.48 |  | 13.48 | 949 | ㎡ | 0.014 |  | 0%
4.1.5 | 4#海关卡口 |  | 7.4 |  | 7.4 | 521 | ㎡ | 0.014 |  | 0%
4.1.6 | 8#保税加工中心 |  | 176.51 |  | 176.51 | 39225 | ㎡ | 0.005 |  | 0.04%
4.1.7 | 9#保税加工中心 |  | 94.21 |  | 94.21 | 20936 | ㎡ | 0.005 |  | 0.02%
4.1.8 | 10#危险品库区 |  | 20.25 |  | 20.25 | 4500 | ㎡ | 0.005 |  | 0%
4.1.9 | 11#保税物流中心 |  | 89.48 |  | 89.48 | 19884 | ㎡ | 0.005 |  | 0.02%
4.1.10 | 12#保税物流中心 |  | 89.48 |  | 89.48 | 19884 | ㎡ | 0.005 |  | 0.02%
4.1.11 | 13#保税物流中心 |  | 56.66 |  | 56.66 | 12591 | ㎡ | 0.005 |  | 0.01%
4.1.12 | 14#保税物流中心 |  | 56.66 |  | 56.66 | 12591 | ㎡ | 0.005 |  | 0.01%
4.1.13 | 15#保税物流中心 |  | 44.59 |  | 44.59 | 9908 | ㎡ | 0.005 |  | 0.01%
4.1.14 | 16#保税物流中心 |  | 51.24 |  | 51.24 | 11387 | ㎡ | 0.005 |  | 0.01%
4.1.15 | 17#保税物流中心 |  | 51.24 |  | 51.24 | 11387 | ㎡ | 0.005 |  | 0.01%
4.1.16 | 18#保税物流中心 |  | 51.24 |  | 51.24 | 11387 | ㎡ | 0.005 |  | 0.01%
4.1.17 | 19#综合配套中心 |  | 1050.3 |  | 1050.3 | 87525 | ㎡ | 0.012 |  | 0.22%
4.1.18 | 20#商贸物流大楼 |  | 660 |  | 660 | 55000 | ㎡ | 0.012 |  | 0.14%
4.1.19 | 室外工程 |  | 4212.05 |  | 4212.05 | 679362.9 | ㎡ | 0.006 |  | 0.89%
4.2 | 综合信息化平台 |  | 22038.98 |  | 22038.98 |  |  |  |  | 4.65%
4.3 | 工艺设备 |  | 10000 |  | 10000 |  |  |  |  | 2.11%
5 | 配套设施 | 47414.62 | 0 | 0 | 47414.62 |  |  |  |  | 10.01%
5.1 | 1#高架联络桥 | 8800 | 0 | 0 | 8800 | 11000 | ㎡ | 0.8 |  | 1.86%
5.1.1 | 路基工程 | 1650 |  |  | 1650 | 11000 | ㎡ | 0.15 |  | 0.35%
5.1.2 | 桥梁工程 | 6600 |  |  | 6600 | 11000 | ㎡ | 0.6 |  | 1.39%
5.1.2 | 照明工程 | 550 |  |  | 550 | 11000 | ㎡ | 0.05 |  | 0.12%
5.2 | 2#预留高架联络桥 | 8800 | 0 | 0 | 8800 | 11000 | ㎡ | 0.8 |  | 1.86%
5.2.2 | 路基工程 | 1650 |  |  | 1650 | 11000 | ㎡ | 0.15 |  | 0.35%
5.2.3 | 桥梁工程 | 6600 |  |  | 6600 | 11000 | ㎡ | 0.6 |  | 1.39%
5.2.4 | 照明工程 | 550 |  |  | 550 | 11000 | ㎡ | 0.05 |  | 0.12%
5.3 | 3#平交联络桥 | 4000 | 0 | 0 | 4000 | 5000 | ㎡ | 0.8 |  | 0.84%
5.3.1 | 路基工程 | 750 |  |  | 750 | 5000 | ㎡ | 0.15 |  | 0.16%
5.3.2 | 桥梁工程 | 3000 |  |  | 3000 | 5000 | ㎡ | 0.6 |  | 0.63%
5.3.3 | 照明工程 | 250 |  |  | 250 | 5000 | ㎡ | 0.05 |  | 0.05%
5.4 | 4#高架桥 | 3200 | 0 | 0 | 3200 | 4000 | ㎡ | 0.8 |  | 0.68%
5.4.1 | 路基工程 | 600 |  |  | 600 | 4000 | ㎡ | 0.15 |  | 0.13%
5.4.2 | 桥梁工程 | 2400 |  |  | 2400 | 4000 | ㎡ | 0.6 |  | 0.51%
5.4.3 | 照明工程 | 200 |  |  | 200 | 4000 | ㎡ | 0.05 |  | 0.04%
5.5 | 22#道口 | 750 | 0 | 0 | 750 | 1500 | ㎡ | 0.5 |  | 0.16%
5.5.1 | 路基工程 | 225 |  |  | 225 | 1500 | ㎡ | 0.15 |  | 0.05%
5.5.2 | 桥梁工程 | 450 |  |  | 450 | 1500 | ㎡ | 0.3 |  | 0.1%
5.5.3 | 照明工程 | 75 |  |  | 75 | 1500 | ㎡ | 0.05 |  | 0.02%
5.6 | 道路、场坪 | 21864.62 | 0 | 0 | 21864.62 | 590935.81 | ㎡ | 0.1 |  | 4.62%
5.6.1 | 二期 | 21864.62 |  |  | 21864.62 | 590935.81 |  |  |  | 4.62%
5.6.1.1 | 道路工程 | 21864.62 |  |  | 21864.62 | 118187.162 | ㎡ |  |  | 4.62%
5.6.1.1.1 | 地基处理 | 2363.74 |  |  | 2363.74 | 118187.162 | ㎡ | 0.02 |  | 0.5%
5.6.1.1.2 | 路面工程 | 14182.46 |  |  | 14182.46 | 118187.162 | ㎡ | 0.12 |  | 3%
5.6.1.1.3 | 室外给排水工程 | 2363.74 |  |  | 2363.74 | 590935.81 | ㎡ | 0.004 |  | 0.5%
5.6.1.1.4 | 室外电气工程 | 2954.68 |  |  | 2954.68 | 590935.81 | ㎡ | 0.005 |  | 0.62%
6 | 能力建设 |  |  | 731 | 731 |  |  |  |  | 0.15%
7 | 专题研究 |  |  | 731 | 731 |  |  |  |  | 0.15%
二 | 工程建设其他费 |  |  | 26527.26 | 26527.26 |  |  |  |  | 5.6%
1 | 建设单位管理费 |  |  | 2424.32 | 2424.32 |  |  |  | 参照财建[2016]504号 | 0.51%
2 | 工程建设监理费 |  |  | 3443.48 | 3443.48 |  |  |  | 参照发改价格[2007]670号 | 0.73%
3 | 建设项目前期咨询费用 |  |  | 290 | 290 |  |  |  |  | 0.06%
3.1 | 可研报告及资金申请报告编制 |  |  | 290 | 290 |  |  |  | 参照计价格[1999]1283号 | 0.06%
4 | 水土保持相关费用 |  |  | 1016 | 1016 |  |  |  | 参照水利部保监[2005]22号 | 0.21%
4.1 | 水土保持方案编制费 |  |  | 280 | 280 |  |  |  | 参照水利部保监[2005]22号 | 0.06%
4.2 | 水土保持监测费 |  |  | 608 | 608 |  |  |  | 参照水利部保监[2005]22号 | 0.13%
4.3 | 水土保持设施竣工验收技术评估报告编制费 |  |  | 128 | 128 |  |  |  | 参照水利部保监[2005]22号 | 0.03%
5 | 水土保持补偿费 |  |  | 101.9 | 101.9 | 679362.9 | ㎡ |  | 鄂价环资[2017]93号 | 0.02%
6 | 勘察设计费 |  |  | 8860.76 | 8860.76 |  |  |  |  | 1.87%
6.1 | 工程勘察费 |  |  | 2218.93 | 2218.93 |  |  |  | 参照计价格[2002]10号 | 0.47%
6.2 | 工程设计费 |  |  | 5805.8 | 5805.8 |  |  |  | 参照计价格[2002]10号 | 1.23%
6.3 | 施工图预算编制费 |  |  | 464.46 | 464.46 |  |  |  | 参照计价格[2002]10号 | 0.1%
6.4 | 竣工图编制费 |  |  | 371.57 | 371.57 |  |  |  |  | 0.08%
7 | 建设工程造价咨询服务费 |  |  | 3155.21 | 3155.21 |  |  |  | 参照鄂价工服规[2012]149号 | 0.67%
7.1 | 工程量清单编制 |  |  | 191.65 | 191.65 |  |  |  | 参照鄂价工服规[2012]149号 | 0.04%
7.2 | 控制价编制 |  |  | 121.21 | 121.21 |  |  |  | 参照鄂价工服规[2012]149号 | 0.03%
7.3 | 施工阶段全过程造价控制 |  |  | 1421.83 | 1421.83 |  |  |  | 参照鄂价工服规[2012]149号 | 0.3%
7.4 | 竣工决算审核 |  |  | 1420.51 | 1420.51 |  |  |  | 参照鄂价工服规[2012]149号 | 0.3%
8 | 场地准备及临时设施费 |  |  | 1733.54 | 1733.54 |  |  |  | 工程费用1% | 0.37%
9 | 工程保险费 |  |  | 1733.54 | 1733.54 |  |  |  | 工程费用0.5% | 0.37%
10 | 招标代理服务费 |  |  | 141.03 | 141.03 |  |  |  | 参照计价格[2002]1980号 | 0.03%
10.1 | 工程招标 |  |  | 100.22 | 100.22 |  |  |  |  | 0.02%
10.2 | 服务招标 |  |  | 40.81 | 40.81 |  |  |  |  | 0.01%
10.2.1 | 设计招标 |  |  | 17.76 | 17.76 |  |  |  |  | 0%
10.2.2 | 勘察招标 |  |  | 10 | 10 |  |  |  |  | 0%
10.2.3 | 监理招标 |  |  | 13.06 | 13.06 |  |  |  |  | 0%
11 | 环境影响咨询服务费 |  |  | 72.35 | 72.35 |  |  |  |  | 0.02%
12 | 社会稳定性风险评估 |  |  | 116.03 | 116.03 |  |  |  |  | 0.02%
13 | 节能报告评估 |  |  | 40 | 40 |  |  |  |  | 0.01%
14 | 建筑垃圾服务费 |  |  | 782.14 | 782.14 |  |  |  |  | 0.17%
15 | 地质灾害危害性评估 |  |  | 40 | 40 |  |  |  |  | 0.01%
16 | 交通影响评价费 |  |  | 50 | 50 |  |  |  |  | 0.01%
17 | 高可靠性供电费 |  |  | 100 | 100 |  |  |  |  | 0.02%
18 | 第三方检测费 |  |  | 2426.95 | 2426.95 |  |  |  |  | 0.51%
三 | 预备费 |  |  |  | 18661.75 |  |  |  | (1+2)×5% | 3.94%
四 | 专项费用 |  |  | 55251.96 | 55251.96 |  |  |  |  | 11.67%
1 | 土地费用 |  |  | 50951.96 | 50951.96 |  |  |  |  | 10.76%
1.1 | 土地使用费 |  |  | 30571.18 | 30571.18 | 1019.04 | 亩 | 30 |  | 6.46%
1.2 | 土地拆迁费 |  |  | 20380.79 | 20380.79 | 1019.04 | 亩 | 20 |  | 4.3%
2 | 外电报装 |  |  | 3000 | 3000 |  |  |  |  | 0.63%
3 | 外水报装 |  |  | 600 | 600 |  |  |  |  | 0.13%
4 | 燃气报装 |  |  | 700 | 700 |  |  |  |  | 0.15%
五 | 建设投资 |  |  |  | 447148.63 |  |  |  | （一+二+三） | 94.43%
六 | 建设期利息及贷款费用 |  |  |  | 24123 |  |  |  |  | 5.09%
1 | 建设期利息 |  |  |  | 21930 |  |  |  |  | 4.63%
2 | 先征费（0.25%） |  |  |  | 731 |  |  |  |  | 0.15%
3 | 承诺费（0.25%） |  |  |  | 1462 |  |  |  |  | 0.31%
七 | 流动资金 |  |  |  | 2233.21 |  |  |  |  | 0.47%
八 | 总投资 |  |  |  | 473504.84 |  |  |  | （四+五+六+七） | 100%

## 采购计划_20231218 (hidden)
附件1-湖北国际航空货运物流园项目采购计划
编号 | 合同号 | 采购内容 | 项目实施单位 | 成本估算 |  | 资金来源占比 |  | 采购 类别 | 采购 方式 | 审查 方式 | 公告日期 | 合同 签订日期 | 合同 月数 | 是否 提前采购 | 是否使用 追溯贷款 | 备注
|  |  |  | 人民币(万元) | 美元(万元) | 亚投行 | 国内配套
1 | P000770-CW01 | 2#+3#国际货运站建设 | 鄂州临空集团 | 34982.9616 |  | 100% |  | 土建 | IOCT | 前审 | 2024Q3 | 2025Q1 | 18 | 否 | 否 | 1.2+1.3
2 | P000770-CW02 | 国际快件中心 | 鄂州临空集团 | 25201.228 |  | 100% |  | 土建 | IOCT | 后审 | 2024Q3 | 2024Q4 | 18 | 否 | 否 | 1.3
3 | P000770-CW03 | 8#+9#+11#+12#+13#+14#保税加工中心 | 鄂州临空集团 | 66506.5605 |  | 100% |  | 土建 | IOCT | 前审 | 2024Q3 | 2024Q4 | 24 | 否 | 否 | 2.1+2.2
4 | P000770-CW04 | 20#商贸物流大厦 | 鄂州临空集团 | 37772.0748 |  | 100% |  | 土建 | IOCT | 前审 | 2024Q3 | 2025Q1 | 30 | 否 | 否 | 3.1
5 | P000770-CW05 | 10#危险品仓库 | 鄂州临空集团 | 2841.75 |  | 100% |  | 土建 | IOCT | 后审 | 2024Q3 | 2024Q4 | 12 | 否 | 否 | 5.1~5.5
6 | P000770-CW06 | 1#高架联络桥+3#平交联络桥+4#高架桥+22#道口 | 鄂州临空集团 | 16750 |  | 100% |  | 土建 | IOCT | 前审 | 2024Q3 | 2025Q1 | 24 | 否 | 否 | 5.6
7 | P000770-CW07 | 道路工程+2#海关卡口+4#海关卡口+海关围网 | 鄂州临空集团 | 23095.324 |  | 100% |  | 土建 | IOCT | 后审 | 2024Q3 | 2024Q4 | 24 | 否 | 否
8 | P000770-CW08 | 15#+16#+17#+18#保税加工中心 | 鄂州临空集团 | 24900.377 |  | 100% |  | 土建 | IOCT | 前审 | 2025Q2 | 2025Q4 | 24 | 否 | 否 | 2.3~2.6
9 | P000770-CW09 | 19#综合配套中心 | 鄂州临空集团 | 59738.65 |  | 100% |  | 土建 | IOCT | 前审 | 2025Q4 | 2026Q2 | 30 | 否 | 否 | 2.7~2.11
10 | P000770-CW10 | 2#预留高架桥 | 鄂州临空集团 | 8800 |  | 100% |  | 土建 | IOCT | 后审 | 2025Q4 | 2026Q1 | 24 | 否 | 否
11 | P000770-CW11 | 整个项目的绿化工程 | 鄂州临空集团 | 6204.826 |  | 100% |  | 土建 | IOCT | 后审 | 2027Q2 | 2027Q3 | 18 | 否 | 否
12 | P000770-GD01 | 国际货站航空集装器CT安检系统 | 鄂州临空集团 | 7000 |  | 100% |  | 货物 | IOCT | 前审 | 2024Q3 | 2024Q4 | 24 | 是 | 是
13 | P000770-GD02 | 2#、3#国际货运站民航专业工程设备 | 鄂州临空集团 | 2751 |  | 100% |  | 货物 | IOCT | 后审 | 2024Q3 | 2024Q4 | 24 | 否 | 否 | 4.1硬件
14 | P000770-GD03 | 2#、3#国际货运站主要运行设备及海关设备 | 鄂州临空集团 | 4026 |  | 100% |  | 货物 | IOCT | 后审 | 2024Q3 | 2024Q4 | 24 | 否 | 否 | 4.2硬件
15 | P000770-GD04 | 2#、3#国际货运站货站内的车辆、可移动设备等 | 鄂州临空集团 | 2237 |  | 100% |  | 货物 | IOCT | 后审 | 2024Q3 | 2024Q4 | 24 | 否 | 否 | 4.3硬件
16 | P000770-GD05 | 国际快件中心工艺设备 | 鄂州临空集团 | 5186 |  | 100% |  | 货物 | IOCT | 前审 | 2026Q1 | 2026Q3 | 24 | 否 | 否 | 4.3硬件
17 | P000770-SS01 | 建设工程造价咨询服务费 | 鄂州临空集团 | 3065.84 |  | 100% |  | 货物 | NOCT | 前审 | 2024Q3 | 2025Q1 | 24 | 否 | 否
19 | P000770-SS03 | 第三方检测费 | 鄂州临空集团 | 2311.3211 |  | 100% |  | 服务 | NOCT | 前审 | 2024Q3 | 2025Q1 | 60 | 否 | 否
20 | P000770-SS04 | 研究费用(国际外贸规则趋势及应对、自贸区发展等) | 鄂州临空集团 | 500 |  | 100% |  | 服务 | NOCT | 前审 | 2024Q2 | 2024Q4 | 36 | 是 | 否 | 4.1软件
21 | P000770-SS05 | 项目管理与能力建设咨询服务 | 鄂州临空集团 | 1000 |  | 100% |  | 服务 | IOCT | 前审 | 2024Q2 | 2024Q4 | 60 | 是 | 否
|  |  | 总计 | 334870.913 | [11 empty] | 编号参见可研附表1(总投资估算表)
|  |  | 土建合计 | 327993.7519 | 262395.0015 | 0.2
|  |  | 货物合计 | 120843.853 | 120843.853 | 1
|  |  | 服务合计 | 6877.1611 | 6877.1611 | 1
|  |  |  | 455714.766 | 390116.0157
[5 empty] | 54182.78 | US(1=7.2)

## 20231207预算 (hidden)
总投资估算表
单位：万元
序号 | 工程和费用名称 | 估算价值(万元) |  |  |  | 技术经济指标 |  |  | 备 注 |  | 比例
|  | 建筑工程 | 设备及安装工程费 | 其他费用 | 合 计 | 室内面积或数量 |  | （万元）
一 | 工程费用 | 290573.7898 | 38258.9421 | 1356 | 330188.7319 |  |  |  | （1+2+3） |  | 73.19% |  | 43503.386
1 | 海关业务基础设施 | 46655.901 | 14758.9876 | 0 | 61414.8886 | [5 empty] | 10.22%
1.2 | 2#国际货站 | 11029.588 | 6461.8928 | 0 | 17491.4808 | 19474 | ㎡ | 0.8982 |  |  | 2.418%
1.2.1 | 场平 | 435.732 |  |  | 435.732 | 21786.6 | ㎡ | 0.02 |  |  | 0.09475%
1.2.2 | 地基处理 | 97.37 |  |  | 97.37 | 19474 | ㎡ | 0.005 |  | 0.01515% | 0.02117%
1.2.3 | 基础工程 | 116.844 |  |  | 116.844 | 19474 | ㎡ | 0.006 |  | 0.01818% | 0.02541%
1.2.4 | 土建工程 | 4868.5 |  |  | 4868.5 | 19474 | ㎡ | 0.25 |  | 0.7576% | 1.059%
1.2.5 | 装饰装修工程 | 2921.1 |  |  | 2921.1 | 19474 | ㎡ | 0.15 |  | 0.4545% | 0.6352%
1.2.6 | 给排水工程 | 292.11 |  |  | 292.11 | 19474 | ㎡ | 0.015 |  | 0.04545% | 0.06352%
1.2.7 | 暖通工程 | 778.96 |  |  | 778.96 | 19474 | ㎡ | 0.04 |  | 0.1212% | 0.1694%
1.2.8 | 电气工程 | 1363.18 |  |  | 1363.18 | 19474 | ㎡ | 0.07 |  | 0.1818% | 0.2964%
4.1.2.1 | 后期弱电工程 |  | 6371.8928 |  | 6371.8928 | 19474 | ㎡ | 0.3272 |  |  | 1.386%
1.2.9 | 电梯工程 |  | 90 |  | 90 | 2 | 部 | 45 |  | 0.014% | 0.01957%
1.2.10 | 抗震支架 | 116.844 |  |  | 116.844 | 19474 | ㎡ | 0.006 |  | 0.01818% | 0.02541%
1.2.11 | 标识标牌 | 38.948 |  |  | 38.948 | 19474 | ㎡ | 0.002 |  | 0.006061% | 0.008469%
1.3 | 3#国际货站 | 11029.588 | 6461.8928 | 0 | 17491.4808 | 19474 | ㎡ | 0.8982 |  |  | 2.418%
1.3.1 | 场平 | 435.732 |  |  | 435.732 | 21786.6 | ㎡ | 0.02 |  |  | 0.09475%
1.3.2 | 地基处理 | 97.37 |  |  | 97.37 | 19474 | ㎡ | 0.005 |  | 0.01515% | 0.02117%
1.3.3 | 基础工程 | 116.844 |  |  | 116.844 | 19474 | ㎡ | 0.006 |  | 0.01818% | 0.02541%
1.3.4 | 土建工程 | 4868.5 |  |  | 4868.5 | 19474 | ㎡ | 0.25 |  | 0.7576% | 1.059%
1.3.5 | 装饰装修工程 | 2921.1 |  |  | 2921.1 | 19474 | ㎡ | 0.15 |  | 0.4545% | 0.6352%
1.3.6 | 给排水工程 | 292.11 |  |  | 292.11 | 19474 | ㎡ | 0.015 |  | 0.04545% | 0.06352%
1.3.7 | 暖通工程 | 778.96 |  |  | 778.96 | 19474 | ㎡ | 0.04 |  | 0.1212% | 0.1694%
1.3.8 | 电气工程 | 1363.18 |  |  | 1363.18 | 19474 | ㎡ | 0.07 |  | 0.1818% | 0.2964%
4.1.2.2 | 后期弱电工程 |  | 6371.8928 |  | 6371.8928 | 19474 | ㎡ | 0.3272 |  |  | 1.386%
1.3.9 | 电梯工程 |  | 90 |  | 90 | 2 | 部 | 45 |  | 0.014% | 0.01957%
1.3.10 | 抗震支架 | 116.844 |  |  | 116.844 | 19474 | ㎡ | 0.006 |  | 0.01818% | 0.02541%
1.3.11 | 标识标牌 | 38.948 |  |  | 38.948 | 19474 | ㎡ | 0.002 |  | 0.006061% | 0.008469%
1.4 | 4#国际快件中心 | 23386.9 | 1814.328 | 0 | 25201.228 | 45398 | ㎡ | 0.55512 |  |  | 5.125%
1.4.1 | 场平 | 506.308 |  |  | 506.308 | 25315.4 | ㎡ | 0.02 |  |  | 0.1101%
1.4.2 | 地基处理 | 226.99 |  |  | 226.99 | 45398 | ㎡ | 0.005 |  | 0.01515% | 0.04936%
1.4.3 | 基础工程 | 272.388 |  |  | 272.388 | 45398 | ㎡ | 0.006 |  | 0.01818% | 0.05923%
1.4.4 | 土建工程 | 10441.54 |  |  | 10441.54 | 45398 | ㎡ | 0.23 |  | 0.7576% | 2.27%
1.4.5 | 装饰装修工程 | 5901.74 |  |  | 5901.74 | 45398 | ㎡ | 0.13 |  | 0.4545% | 1.283%
1.4.6 | 给排水工程 | 680.97 |  |  | 680.97 | 45398 | ㎡ | 0.015 |  | 0.04545% | 0.1481%
1.4.7 | 暖通工程 | 1815.92 |  |  | 1815.92 | 45398 | ㎡ | 0.04 |  | 0.1212% | 0.3949%
1.4.8 | 电气工程 | 3177.86 |  |  | 3177.86 | 45398 | ㎡ | 0.07 |  | 0.1818% | 0.691%
4.1.2.3 | 后期弱电工程 |  | 1634.328 |  | 1634.328 | 45398 | ㎡ | 0.036 |  |  | 0.3554%
1.4.9 | 电梯工程 |  | 180 |  | 180 | 4 | 部 | 45 |  | 0.014% | 0.03914%
1.4.10 | 抗震支架 | 272.388 |  |  | 272.388 | 45398 | ㎡ | 0.006 |  | 0.01818% | 0.05923%
1.4.11 | 标识标牌 | 90.796 |  |  | 90.796 | 45398 | ㎡ | 0.002 |  | 0.006061% | 0.01974%
1.5 | 2#海关卡口 | 481.6175 | 13.4758 | 0 | 495.0933 | 949 | ㎡ | 0.5217 |  |  | 0.1047%
1.5.1 | 地基处理 | 3.3215 |  |  | 3.3215 | 949 | ㎡ | 0.0035 |  | 0.01515% | 0.0007222%
1.5.2 | 土建工程 | 455.52 |  |  | 455.52 | 949 | ㎡ | 0.48 |  | 0.7576% | 0.09905%
1.5.3 | 给排水工程 | 2.847 |  |  | 2.847 | 949 | ㎡ | 0.003 |  | 0.04545% | 0.0006191%
1.5.4 | 暖通工程 | 3.796 |  |  | 3.796 | 949 | ㎡ | 0.004 |  | 0.1212% | 0.0008254%
1.5.5 | 电气工程 | 8.541 |  |  | 8.541 | 949 | ㎡ | 0.009 |  | 0.1818% | 0.001857%
4.1.2.4 | 后期弱电工程 |  | 13.4758 |  | 13.4758 | 949 | ㎡ | 0.0142 |  |  | 0.00293%
1.5.6 | 抗震支架 | 5.694 |  |  | 5.694 | 949 | ㎡ | 0.006 |  | 0.01818% | 0.001238%
1.5.7 | 标识标牌 | 1.898 |  |  | 1.898 | 949 | ㎡ | 0.002 |  | 0.006061% | 0.0004127%
1.6 | 4#海关卡口 | 264.4075 | 7.3982 | 0 | 271.8057 | 521 | ㎡ | 0.5217 |  |  | 0.05749%
1.6.1 | 地基处理 | 1.8235 |  |  | 1.8235 | 521 | ㎡ | 0.0035 |  | 0.01515% | 0.0003965%
1.6.2 | 土建工程 | 250.08 |  |  | 250.08 | 521 | ㎡ | 0.48 |  | 0.7576% | 0.05438%
1.6.3 | 给排水工程 | 1.563 |  |  | 1.563 | 521 | ㎡ | 0.003 |  | 0.04545% | 0.0003399%
1.6.4 | 暖通工程 | 2.084 |  |  | 2.084 | 521 | ㎡ | 0.004 |  | 0.1212% | 0.0004532%
1.6.5 | 电气工程 | 4.689 |  |  | 4.689 | 521 | ㎡ | 0.009 |  | 0.1818% | 0.00102%
4.1.2.5 | 后期弱电工程 |  | 7.3982 |  | 7.3982 | 521 | ㎡ | 0.0142 |  |  | 0.001609%
1.6.6 | 抗震支架 | 3.126 |  |  | 3.126 | 521 | ㎡ | 0.006 |  | 0.01818% | 0.0006797%
1.6.7 | 标识标牌 | 1.042 |  |  | 1.042 | 521 | ㎡ | 0.002 |  | 0.006061% | 0.0002266%
1.7 | 海关围网 | 463.8 |  |  | 463.8 | 7730 | 延米 | 0.06 |  |  | 0.1009% |  |  | 52.82t/年
2 | 保税仓储和加工 | 93597.713 | 650.9745 | 0 | 94248.6875 | [5 empty] | 20.43%
2.1 | 8#保税加工中心 | 19874.13 | 356.5125 | 0 | 20230.6425 | 39225 | ㎡ | 0.51576 |  |  | 4.361%
2.1.1 | 场平 | 496.98 |  |  | 496.98 | 24849 | ㎡ | 0.02 |  |  | 0.1081%
2.1.2 | 地基处理 | 196.125 |  |  | 196.125 | 39225 | ㎡ | 0.005 |  | 0.01515% | 0.04265%
2.1.3 | 基础工程 | 235.35 |  |  | 235.35 | 39225 | ㎡ | 0.006 |  | 0.01818% | 0.05118%
2.1.4 | 土建工程 | 9414 |  |  | 9414 | 39225 | ㎡ | 0.24 |  | 0.7576% | 2.047%
2.1.5 | 装饰装修工程 | 4707 |  |  | 4707 | 39225 | ㎡ | 0.12 |  | 0.4545% | 1.024%
2.1.6 | 给排水工程 | 588.375 |  |  | 588.375 | 39225 | ㎡ | 0.015 |  | 0.04545% | 0.1279%
2.1.7 | 暖通工程 | 1176.75 |  |  | 1176.75 | 39225 | ㎡ | 0.03 |  | 0.1212% | 0.2559%
2.1.8 | 电气工程 | 2745.75 |  |  | 2745.75 | 39225 | ㎡ | 0.07 |  | 0.1818% | 0.5971%
4.1.2.7 | 后期弱电工程 |  | 176.5125 |  | 176.5125 | 39225 | ㎡ | 0.0045 |  |  | 0.03838%
2.1.9 | 电梯工程 |  | 180 |  | 180 | 4 | 部 | 45 |  | 0.014% | 0.03914%
2.1.10 | 抗震支架 | 235.35 |  |  | 235.35 | 39225 | ㎡ | 0.006 |  | 0.01818% | 0.05118%
2.1.11 | 标识标牌 | 78.45 |  |  | 78.45 | 39225 | ㎡ | 0.002 |  | 0.006061% | 0.01706%
2.2 | 9#保税加工中心 | 11697.916 | 274.212 | 0 | 11972.128 | 20936 | ㎡ | 0.57184 |  |  | 2.583% |  | 租金 | 272388
2.2.1 | 场平 | 497.156 |  |  | 497.156 | 24857.8 | ㎡ | 0.02 |  |  | 0.1081%
2.2.2 | 地基处理 | 104.68 |  |  | 104.68 | 20936 | ㎡ | 0.005 |  | 0.01515% | 0.02276%
2.2.3 | 基础工程 | 146.552 |  |  | 146.552 | 20936 | ㎡ | 0.007 |  | 0.01818% | 0.03187%
2.2.4 | 土建工程 | 5443.36 |  |  | 5443.36 | 20936 | ㎡ | 0.26 |  | 0.7576% | 1.184%
2.2.5 | 装饰装修工程 | 2931.04 |  |  | 2931.04 | 20936 | ㎡ | 0.14 |  | 0.4545% | 0.6373%
2.2.6 | 给排水工程 | 314.04 |  |  | 314.04 | 20936 | ㎡ | 0.015 |  | 0.04545% | 0.06829%
2.2.7 | 暖通工程 | 628.08 |  |  | 628.08 | 20936 | ㎡ | 0.03 |  | 0.1212% | 0.1366%
2.2.8 | 电气工程 | 1465.52 |  |  | 1465.52 | 20936 | ㎡ | 0.07 |  | 0.1818% | 0.3187%
4.1.2.8 | 后期弱电工程 |  | 94.212 |  | 94.212 | 20936 | ㎡ | 0.0045 |  |  | 0.02049%
2.2.9 | 电梯工程 |  | 180 |  | 180 | 4 | 部 | 45 |  | 0.014% | 0.03914%
2.2.10 | 抗震支架 | 125.616 |  |  | 125.616 | 20936 | ㎡ | 0.006 |  | 0.01818% | 0.02731%
2.2.11 | 标识标牌 | 41.872 |  |  | 41.872 | 20936 | ㎡ | 0.002 |  | 0.006061% | 0.009105%
2.3 | 10#危险品库区 | 2821.5 | 20.25 | 0 | 2841.75 | 4500 | ㎡ | 0.6315 |  |  | 0.6135% |  | 租金 | 5447.76 | 万个
2.3.1 | 场平 | 99 |  |  | 99 | 4950 | ㎡ | 0.02 |  |  | 0.02153%
2.3.2 | 地基处理 | 22.5 |  |  | 22.5 | 4500 | ㎡ | 0.005 |  | 0.01515% | 0.004893%
2.3.3 | 基础工程 | 31.5 |  |  | 31.5 | 4500 | ㎡ | 0.007 |  | 0.01818% | 0.00685%
2.3.4 | 土建工程 | 1170 |  |  | 1170 | 4500 | ㎡ | 0.26 |  | 0.7576% | 0.2544%
2.3.5 | 装饰装修工程 | 810 |  |  | 810 | 4500 | ㎡ | 0.18 |  | 0.4545% | 0.1761%
2.3.6 | 给排水工程 | 67.5 |  |  | 67.5 | 4500 | ㎡ | 0.015 |  | 0.04545% | 0.01468%
2.3.7 | 暖通工程 | 225 |  |  | 225 | 4500 | ㎡ | 0.05 |  | 0.1212% | 0.04893%
2.3.8 | 电气工程 | 360 |  |  | 360 | 4500 | ㎡ | 0.08 |  | 0.1818% | 0.07828%
4.1.2.9 | 后期弱电工程 |  | 20.25 |  | 20.25 | 4500 | ㎡ | 0.0045 |  |  | 0.004403%
2.3.9 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0.014% | 0%
2.3.10 | 抗震支架 | 27 |  |  | 27 | 4500 | ㎡ | 0.006 |  | 0.01818% | 0.005871%
2.3.11 | 标识标牌 | 9 |  |  | 9 | 4500 | ㎡ | 0.002 |  | 0.006061% | 0.001957%
2.4 | 11#保税物流中心 | 10032.488 | 0 | 0 | 10032.488 | 19884 | ㎡ | 0.50455 |  |  | 2.182% |  | 保管 | 32686.56 | 万元
2.4.1 | 场平 | 209.792 |  |  | 209.792 | 10489.6 | ㎡ | 0.02 |  |  | 0.04562%
2.4.1 | 地基处理 | 99.42 |  |  | 99.42 | 19884 | ㎡ | 0.005 |  | 0.01515% | 0.02162%
2.4.2 | 基础工程 | 119.304 |  |  | 119.304 | 19884 | ㎡ | 0.006 |  | 0.01818% | 0.02594%
2.4.3 | 土建工程 | 4772.16 |  |  | 4772.16 | 19884 | ㎡ | 0.24 |  | 0.7576% | 1.038%
2.4.4 | 装饰装修工程 | 2386.08 |  |  | 2386.08 | 19884 | ㎡ | 0.12 |  | 0.4545% | 0.5188%
2.4.5 | 给排水工程 | 298.26 |  |  | 298.26 | 19884 | ㎡ | 0.015 |  | 0.04545% | 0.06486%
2.4.6 | 暖通工程 | 596.52 |  |  | 596.52 | 19884 | ㎡ | 0.03 |  | 0.1212% | 0.1297%
2.4.7 | 电气工程 | 1391.88 |  |  | 1391.88 | 19884 | ㎡ | 0.07 |  | 0.1818% | 0.3027%
2.4.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0.014% | 0%
2.4.9 | 抗震支架 | 119.304 |  |  | 119.304 | 19884 | ㎡ | 0.006 |  | 0.01818% | 0.02594%
2.4.10 | 标识标牌 | 39.768 |  |  | 39.768 | 19884 | ㎡ | 0.002 |  | 0.006061% | 0.008647%
2.5 | 12#保税物流中心 | 10032.488 | 0 | 0 | 10032.488 | 19884 | ㎡ | 0.50455 |  |  | 2.182%
2.5.1 | 场平 | 209.792 |  |  | 209.792 | 10489.6 | ㎡ | 0.02 |  |  | 0.04562%
2.5.2 | 地基处理 | 99.42 |  |  | 99.42 | 19884 | ㎡ | 0.005 |  | 0.01515% | 0.02162%
2.5.3 | 基础工程 | 119.304 |  |  | 119.304 | 19884 | ㎡ | 0.006 |  | 0.01818% | 0.02594%
2.5.4 | 土建工程 | 4772.16 |  |  | 4772.16 | 19884 | ㎡ | 0.24 |  | 0.7576% | 1.038%
2.5.5 | 装饰装修工程 | 2386.08 |  |  | 2386.08 | 19884 | ㎡ | 0.12 |  | 0.4545% | 0.5188%
2.5.6 | 给排水工程 | 298.26 |  |  | 298.26 | 19884 | ㎡ | 0.015 |  | 0.04545% | 0.06486%
2.5.7 | 暖通工程 | 596.52 |  |  | 596.52 | 19884 | ㎡ | 0.03 |  | 0.1212% | 0.1297%
2.5.8 | 电气工程 | 1391.88 |  |  | 1391.88 | 19884 | ㎡ | 0.07 |  | 0.1818% | 0.3027%
2.5.9 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0.014% | 0%
2.5.10 | 抗震支架 | 119.304 |  |  | 119.304 | 19884 | ㎡ | 0.006 |  | 0.01818% | 0.02594%
2.5.11 | 标识标牌 | 39.768 |  |  | 39.768 | 19884 | ㎡ | 0.002 |  | 0.006061% | 0.008647%
2.6 | 13#保税物流中心 | 7119.407 | 0 | 0 | 7119.407 | 12591 | ㎡ | 0.56544 |  |  | 1.548% |  |  | 60500
2.6.1 | 场平 | 257.312 |  |  | 257.312 | 12865.6 | ㎡ | 0.02 |  |  | 0.05595%
2.6.2 | 地基处理 | 62.955 |  |  | 62.955 | 12591 | ㎡ | 0.005 |  | 0.01515% | 0.01369%
2.6.3 | 基础工程 | 88.137 |  |  | 88.137 | 12591 | ㎡ | 0.007 |  | 0.01818% | 0.01917%
2.6.4 | 土建工程 | 3147.75 |  |  | 3147.75 | 12591 | ㎡ | 0.25 |  | 0.7576% | 0.6845%
2.6.5 | 装饰装修工程 | 1888.65 |  |  | 1888.65 | 12591 | ㎡ | 0.15 |  | 0.4545% | 0.4107%
2.6.6 | 给排水工程 | 188.865 |  |  | 188.865 | 12591 | ㎡ | 0.015 |  | 0.04545% | 0.04107%
2.6.7 | 暖通工程 | 503.64 |  |  | 503.64 | 12591 | ㎡ | 0.04 |  | 0.1212% | 0.1095%
2.6.8 | 电气工程 | 881.37 |  |  | 881.37 | 12591 | ㎡ | 0.07 |  | 0.1818% | 0.1917%
2.6.9 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0.014% | 0%
2.6.10 | 抗震支架 | 75.546 |  |  | 75.546 | 12591 | ㎡ | 0.006 |  | 0.01818% | 0.01643%
2.6.11 | 标识标牌 | 25.182 |  |  | 25.182 | 12591 | ㎡ | 0.002 |  | 0.006061% | 0.005476%
2.7 | 14#保税物流中心 | 7119.407 | 0 | 0 | 7119.407 | 12591 | ㎡ | 0.56544 |  |  | 1.548% |  | 租金 | 302500
2.7.1 | 场平 | 257.312 |  |  | 257.312 | 12865.6 | ㎡ | 0.02 |  |  | 0.05595%
2.7.2 | 地基处理 | 62.955 |  |  | 62.955 | 12591 | ㎡ | 0.005 |  | 0.01515% | 0.01369%
2.7.3 | 基础工程 | 88.137 |  |  | 88.137 | 12591 | ㎡ | 0.007 |  | 0.01818% | 0.01917%
2.7.4 | 土建工程 | 3147.75 |  |  | 3147.75 | 12591 | ㎡ | 0.25 |  | 0.7576% | 0.6845%
2.7.5 | 装饰装修工程 | 1888.65 |  |  | 1888.65 | 12591 | ㎡ | 0.15 |  | 0.4545% | 0.4107%
2.7.6 | 给排水工程 | 188.865 |  |  | 188.865 | 12591 | ㎡ | 0.015 |  | 0.04545% | 0.04107%
2.7.7 | 暖通工程 | 503.64 |  |  | 503.64 | 12591 | ㎡ | 0.04 |  | 0.1212% | 0.1095%
2.7.8 | 电气工程 | 881.37 |  |  | 881.37 | 12591 | ㎡ | 0.07 |  | 0.1818% | 0.1917%
2.7.9 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0.014% | 0%
2.7.10 | 抗震支架 | 75.546 |  |  | 75.546 | 12591 | ㎡ | 0.006 |  | 0.01818% | 0.01643%
2.7.11 | 标识标牌 | 25.182 |  |  | 25.182 | 12591 | ㎡ | 0.002 |  | 0.006061% | 0.005476%
2.8 | 15#保税物流中心 | 5598.344 | 0 | 0 | 5598.344 | 9908 | ㎡ | 0.56503 |  |  | 1.217% |  |  | 6050 | 万个
2.8.1 | 场平 | 198.484 |  |  | 198.484 | 9924.2 | ㎡ | 0.02 |  |  | 0.04316%
2.8.2 | 地基处理 | 49.54 |  |  | 49.54 | 9908 | ㎡ | 0.005 |  | 0.01515% | 0.01077%
2.8.3 | 基础工程 | 69.356 |  |  | 69.356 | 9908 | ㎡ | 0.007 |  | 0.01818% | 0.01508%
2.8.4 | 土建工程 | 2477 |  |  | 2477 | 9908 | ㎡ | 0.25 |  | 0.7576% | 0.5386%
2.8.5 | 装饰装修工程 | 1486.2 |  |  | 1486.2 | 9908 | ㎡ | 0.15 |  | 0.4545% | 0.3232%
2.8.6 | 给排水工程 | 148.62 |  |  | 148.62 | 9908 | ㎡ | 0.015 |  | 0.04545% | 0.03232%
2.8.7 | 暖通工程 | 396.32 |  |  | 396.32 | 9908 | ㎡ | 0.04 |  | 0.1212% | 0.08618%
2.8.8 | 电气工程 | 693.56 |  |  | 693.56 | 9908 | ㎡ | 0.07 |  | 0.1818% | 0.1508%
2.8.9 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0.014% | 0%
2.8.10 | 抗震支架 | 59.448 |  |  | 59.448 | 9908 | ㎡ | 0.006 |  | 0.01818% | 0.01293%
2.8.11 | 标识标牌 | 19.816 |  |  | 19.816 | 9908 | ㎡ | 0.002 |  | 0.006061% | 0.004309%
2.9 | 16#保税物流中心 | 6434.011 | 0 | 0 | 6434.011 | 11387 | ㎡ | 0.56503 |  |  | 1.399% |  |  | 36300
2.9.1 | 场平 | 228.096 |  |  | 228.096 | 11404.8 | ㎡ | 0.02 |  |  | 0.0496%
2.9.2 | 地基处理 | 56.935 |  |  | 56.935 | 11387 | ㎡ | 0.005 |  | 0.01515% | 0.01238%
2.9.3 | 基础工程 | 79.709 |  |  | 79.709 | 11387 | ㎡ | 0.007 |  | 0.01818% | 0.01733%
2.9.4 | 土建工程 | 2846.75 |  |  | 2846.75 | 11387 | ㎡ | 0.25 |  | 0.7576% | 0.619%
2.9.5 | 装饰装修工程 | 1708.05 |  |  | 1708.05 | 11387 | ㎡ | 0.15 |  | 0.4545% | 0.3714%
2.9.6 | 给排水工程 | 170.805 |  |  | 170.805 | 11387 | ㎡ | 0.015 |  | 0.04545% | 0.03714%
2.9.7 | 暖通工程 | 455.48 |  |  | 455.48 | 11387 | ㎡ | 0.04 |  | 0.1212% | 0.09904%
2.9.8 | 电气工程 | 797.09 |  |  | 797.09 | 11387 | ㎡ | 0.07 |  | 0.1818% | 0.1733%
2.9.9 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0.014% | 0%
2.9.10 | 抗震支架 | 68.322 |  |  | 68.322 | 11387 | ㎡ | 0.006 |  | 0.01818% | 0.01486%
2.9.11 | 标识标牌 | 22.774 |  |  | 22.774 | 11387 | ㎡ | 0.002 |  | 0.006061% | 0.004952%
2.10 | 17#保税物流中心 | 6434.011 | 0 | 0 | 6434.011 | 11387 | ㎡ | 0.56503 |  |  | 1.399% |  |  |  | 432000
2.10.1 | 场平 | 228.096 |  |  | 228.096 | 11404.8 | ㎡ | 0.02 |  |  | 0.0496%
2.10.2 | 地基处理 | 56.935 |  |  | 56.935 | 11387 | ㎡ | 0.005 |  | 0.01515% | 0.01238%
2.10.3 | 基础工程 | 79.709 |  |  | 79.709 | 11387 | ㎡ | 0.007 |  | 0.01818% | 0.01733%
2.10.4 | 土建工程 | 2846.75 |  |  | 2846.75 | 11387 | ㎡ | 0.25 |  | 0.7576% | 0.619%
2.10.5 | 装饰装修工程 | 1708.05 |  |  | 1708.05 | 11387 | ㎡ | 0.15 |  | 0.4545% | 0.3714%
2.10.6 | 给排水工程 | 170.805 |  |  | 170.805 | 11387 | ㎡ | 0.015 |  | 0.04545% | 0.03714%
2.10.7 | 暖通工程 | 455.48 |  |  | 455.48 | 11387 | ㎡ | 0.04 |  | 0.1212% | 0.09904%
2.10.8 | 电气工程 | 797.09 |  |  | 797.09 | 11387 | ㎡ | 0.07 |  | 0.1818% | 0.1733%
2.10.9 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0.014% | 0%
2.10.10 | 抗震支架 | 68.322 |  |  | 68.322 | 11387 | ㎡ | 0.006 |  | 0.01818% | 0.01486%
2.10.11 | 标识标牌 | 22.774 |  |  | 22.774 | 11387 | ㎡ | 0.002 |  | 0.006061% | 0.004952%
2.11 | 18#保税物流中心 | 6434.011 | 0 | 0 | 6434.011 | 11387 | ㎡ | 0.56503 |  |  | 1.399% |  |  | 821.9178
2.11.1 | 场平 | 228.096 |  |  | 228.096 | 11404.8 | ㎡ | 0.02 |  |  | 0.0496%
2.11.2 | 地基处理 | 56.935 |  |  | 56.935 | 11387 | ㎡ | 0.005 |  | 0.01515% | 0.01238%
2.11.3 | 基础工程 | 79.709 |  |  | 79.709 | 11387 | ㎡ | 0.007 |  | 0.01818% | 0.01733%
2.11.4 | 土建工程 | 2846.75 |  |  | 2846.75 | 11387 | ㎡ | 0.25 |  | 0.7576% | 0.619%
2.11.5 | 装饰装修工程 | 1708.05 |  |  | 1708.05 | 11387 | ㎡ | 0.15 |  | 0.4545% | 0.3714%
2.11.6 | 给排水工程 | 170.805 |  |  | 170.805 | 11387 | ㎡ | 0.015 |  | 0.04545% | 0.03714%
2.11.7 | 暖通工程 | 455.48 |  |  | 455.48 | 11387 | ㎡ | 0.04 |  | 0.1212% | 0.09904%
2.11.8 | 电气工程 | 797.09 |  |  | 797.09 | 11387 | ㎡ | 0.07 |  | 0.1818% | 0.1733%
2.11.9 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0.014% | 0%
2.11.10 | 抗震支架 | 68.322 |  |  | 68.322 | 11387 | ㎡ | 0.006 |  | 0.01818% | 0.01486%
2.11.11 | 标识标牌 | 22.774 |  |  | 22.774 | 11387 | ㎡ | 0.002 |  | 0.006061% | 0.004952%
3 | 贸易和货运服务设施 | 96700.7248 | 810 | 0 | 97510.7248 | [5 empty] | 21.2% |  |  | 25.6849
3.1 | 19#综合配套中心 | 59378.65 | 360 | 0 | 59738.65 |  | ㎡ |  |  |  | 12.99% |  | 租金
3.1.1 | 地上 | 38498.65 | 360 | 0 | 38858.65 | 57525 | ㎡ | 0.67551 |  |  | 8.45%
3.1.1.1 | 场平 | 187 |  |  | 187 | 9350 | ㎡ | 0.02 |  |  | 0.04066%
3.1.1.2 | 地基处理 | 287.625 |  |  | 287.625 | 57525 | ㎡ | 0.005 |  | 0.01515% | 0.06254%
3.1.1.3 | 基础工程 | 8053.5 |  |  | 8053.5 | 57525 | ㎡ | 0.14 |  | 0.01818% | 1.751%
3.1.1.4 | 土建工程 | 14381.25 |  |  | 14381.25 | 57525 | ㎡ | 0.25 |  | 0.7576% | 3.127%
3.1.1.5 | 装饰装修工程 | 8628.75 |  |  | 8628.75 | 57525 | ㎡ | 0.15 |  | 0.4545% | 1.876%
3.1.1.6 | 给排水工程 | 747.825 |  |  | 747.825 | 57525 | ㎡ | 0.013 |  | 0.04545% | 0.1626%
3.1.1.7 | 暖通工程 | 2301 |  |  | 2301 | 57525 | ㎡ | 0.04 |  | 0.1212% | 0.5003%
3.1.1.8 | 电气工程 | 3451.5 |  |  | 3451.5 | 57525 | ㎡ | 0.06 |  | 0.1818% | 0.7505%
3.1.1.9 | 电梯工程 |  | 360 |  | 360 | 8 | 部 | 45 |  | 0.014% | 0.07828%
3.1.1.10 | 抗震支架 | 345.15 |  |  | 345.15 | 57525 | ㎡ | 0.006 |  | 0.01818% | 0.07505%
3.1.1.11 | 标识标牌 | 115.05 |  |  | 115.05 | 57525 | ㎡ | 0.002 |  | 0.006061% | 0.02502%
3.1.2 | 地下 | 20880 | 0 | 0 | 20880 | 30000 | ㎡ | 0.696 |  |  | 4.54%
3.1.2.1 | 地基处理 | 150 |  |  | 150 | 30000 | ㎡ | 0.005 |  | 0.01515% | 0.03262%
3.1.2.2 | 基础工程 | 4200 |  |  | 4200 | 30000 | ㎡ | 0.14 |  | 0.01818% | 0.9133%
3.1.2.3 | 土建工程 | 7500 |  |  | 7500 | 30000 | ㎡ | 0.25 |  | 0.7576% | 1.631%
3.1.2.4 | 装饰装修工程 | 4500 |  |  | 4500 | 30000 | ㎡ | 0.15 |  | 0.4545% | 0.9785%
3.1.2.5 | 给排水工程 | 390 |  |  | 390 | 30000 | ㎡ | 0.013 |  | 0.04545% | 0.0848%
3.1.2.6 | 暖通工程 | 1500 |  |  | 1500 | 30000 | ㎡ | 0.05 |  | 0.1212% | 0.3262%
3.1.2.7 | 电气工程 | 1800 |  |  | 1800 | 30000 | ㎡ | 0.06 |  | 0.1818% | 0.3914%
3.1.2.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0.014% | 0%
3.1.2.9 | 人防工程 | 600 |  |  |  | 15000 | ㎡ | 0.04
3.1.2.10 | 抗震支架 | 180 |  |  | 180 | 30000 | ㎡ | 0.006 |  | 0.01818% | 0.03914%
3.1.2.11 | 标识标牌 | 60 |  |  | 60 | 30000 | ㎡ | 0.002 |  | 0.006061% | 0.01305%
3.2 | 21#商贸物流大楼 | 37322.0748 | 450 | 0 | 37772.0748 |  | ㎡ |  |  |  | 8.213% |  | 租金
3.2.1 | 地上 | 23402.0748 | 450 | 0 | 23852.0748 | 35000 | ㎡ | 0.68149 |  |  | 5.187%
3.2.1.1 | 场平 | 92.0748 |  |  | 92.0748 | 4603.742 | ㎡ | 0.02 |  |  | 0.02002%
3.2.1.2 | 地基处理 | 175 |  |  | 175 | 35000 | ㎡ | 0.005 |  | 0.01515% | 0.03805%
3.2.1.3 | 基础工程 | 4900 |  |  | 4900 | 35000 | ㎡ | 0.14 |  | 0.01818% | 1.065%
3.2.1.4 | 土建工程 | 8750 |  |  | 8750 | 35000 | ㎡ | 0.25 |  | 0.7576% | 1.903%
3.2.1.5 | 装饰装修工程 | 5250 |  |  | 5250 | 35000 | ㎡ | 0.15 |  | 0.4545% | 1.142%
3.2.1.6 | 给排水工程 | 455 |  |  | 455 | 35000 | ㎡ | 0.013 |  | 0.04545% | 0.09894%
3.2.1.7 | 暖通工程 | 1400 |  |  | 1400 | 35000 | ㎡ | 0.04 |  | 0.1212% | 0.3044%
3.2.1.8 | 电气工程 | 2100 |  |  | 2100 | 35000 | ㎡ | 0.06 |  | 0.1818% | 0.4566%
3.2.1.9 | 电梯工程 |  | 450 |  | 450 | 10 | 部 | 45 |  | 0.014% | 0.09785%
3.2.1.10 | 抗震支架 | 210 |  |  | 210 | 35000 | ㎡ | 0.006 |  | 0.01818% | 0.04566%
3.2.1.11 | 标识标牌 | 70 |  |  | 70 | 35000 | ㎡ | 0.002 |  | 0.006061% | 0.01522%
3.2.2 | 地下 | 13920 | 0 | 0 | 13920 | 20000 | ㎡ | 0.696 |  |  | 3.027%
3.2.2.1 | 地基处理 | 100 |  |  | 100 | 20000 | ㎡ | 0.005 |  | 0.01515% | 0.02174%
3.2.2.2 | 基础工程 | 2800 |  |  | 2800 | 20000 | ㎡ | 0.14 |  | 0.01818% | 0.6089%
3.2.2.3 | 土建工程 | 5000 |  |  | 5000 | 20000 | ㎡ | 0.25 |  | 0.7576% | 1.087%
3.2.2.4 | 装饰装修工程 | 3000 |  |  | 3000 | 20000 | ㎡ | 0.15 |  | 0.4545% | 0.6523%
3.2.2.5 | 给排水工程 | 260 |  |  | 260 | 20000 | ㎡ | 0.013 |  | 0.04545% | 0.05654%
3.2.2.6 | 暖通工程 | 1000 |  |  | 1000 | 20000 | ㎡ | 0.05 |  | 0.1212% | 0.2174%
3.2.2.7 | 电气工程 | 1200 |  |  | 1200 | 20000 | ㎡ | 0.06 |  | 0.1818% | 0.2609%
3.2.2.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0.014% | 0%
3.2.2.9 | 人防工程 | 400 |  |  |  | 10000 | ㎡ | 0.04 |  |  | 0%
3.2.2.10 | 抗震支架 | 120 |  |  | 120 | 20000 | ㎡ | 0.006 |  | 0.01818% | 0.02609%
3.2.2.11 | 标识标牌 | 40 |  |  | 40 | 20000 | ㎡ | 0.002 |  | 0.006061% | 0.008698%
4 | 信息化与相关设备 | 0 | 22038.98 | 0 | 22038.98 | [5 empty] | 9.381%
4.1 | 弱电工程 |  |  |  | 0 | [5 empty] | 4.589%
4.1.2 | 后期弱电工程 | [9 empty] | 4.589%
4.1.2.21 | 室外工程 |  | 4212.05 |  | 4212.05 | 679362.9 | ㎡ | 0.0062 |  |  | 0.9159% | 未知(询问设计院无回应，不纳入采购计划)
4.2 | 工艺设备 |  | 22038.98 |  | 22038.98 | [5 empty] | 4.792% | 见后表
4.2.2 | 后期 |  | 22038.98 |  | 22038.98 | [5 empty] | 4.792%
5 | 配套设施 | 53619.451 | 0 | 0 | 53619.451 | [5 empty] | 11.66%
5.1 | 1#高架联络桥 | 8800 | 0 | 0 | 8800 | 11000 | ㎡ | 0.8 |  |  | 1.914%
5.1.1 | 路基工程 | 1650 |  |  | 1650 | 11000 | ㎡ | 0.15 |  |  | 0.3588%
5.1.2 | 桥梁工程 | 6600 |  |  | 6600 | 11000 | ㎡ | 0.6 |  |  | 1.435%
5.1.2 | 照明工程 | 550 |  |  | 550 | 11000 | ㎡ | 0.05 |  |  | 0.1196%
5.2 | 2#预留高架联络桥 | 8800 | 0 | 0 | 8800 | 11000 | ㎡ | 0.8 |  |  | 1.914%
5.2.2 | 路基工程 | 1650 |  |  | 1650 | 11000 | ㎡ | 0.15 |  |  | 0.3588%
5.2.3 | 桥梁工程 | 6600 |  |  | 6600 | 11000 | ㎡ | 0.6 |  |  | 1.435%
5.2.4 | 照明工程 | 550 |  |  | 550 | 11000 | ㎡ | 0.05 |  |  | 0.1196%
5.3 | 3#平交联络桥 | 4000 | 0 | 0 | 4000 | 5000 | ㎡ | 0.8 |  |  | 0.8698%
5.3.1 | 路基工程 | 750 |  |  | 750 | 5000 | ㎡ | 0.15 |  |  | 0.1631%
5.3.2 | 桥梁工程 | 3000 |  |  | 3000 | 5000 | ㎡ | 0.6 |  |  | 0.6523%
5.3.3 | 照明工程 | 250 |  |  | 250 | 5000 | ㎡ | 0.05 |  |  | 0.05436%
5.4 | 4#高架桥 | 3200 | 0 | 0 | 3200 | 4000 | ㎡ | 0.8 |  |  | 0.6958%
5.4.1 | 路基工程 | 600 |  |  | 600 | 4000 | ㎡ | 0.15 |  |  | 0.1305%
5.4.2 | 桥梁工程 | 2400 |  |  | 2400 | 4000 | ㎡ | 0.6 |  |  | 0.5219%
5.4.3 | 照明工程 | 200 |  |  | 200 | 4000 | ㎡ | 0.05 |  |  | 0.04349%
5.5 | 22#道口 | 750 | 0 | 0 | 750 | 1500 | ㎡ | 0.5 |  |  | 0.1631%
5.5.1 | 路基工程 | 225 |  |  | 225 | 1500 | ㎡ | 0.15 |  |  | 0.04893%
5.5.2 | 桥梁工程 | 450 |  |  | 450 | 1500 | ㎡ | 0.3 |  |  | 0.09785%
5.5.3 | 照明工程 | 75 |  |  | 75 | 1500 | ㎡ | 0.05 |  |  | 0.01631%
5.6 | 道路、场坪、绿化等 | 28069.451 | 0 | 0 | 28069.451 | 590935.81 | ㎡ | 0.1 |  |  | 6.104%
[5 empty] | 0 | [5 empty] | 0%
5.6.1 | 二期 | 28069.451 |  |  | 28069.451 | 590935.81 |  |  |  |  | 6.104%
5.6.1.1 | 道路工程 | 21864.625 |  |  | 21864.625 | 118187.162 | ㎡ |  |  |  | 4.754%
5.6.1.1.1 | 地基处理 | 2363.7432 |  |  | 2363.7432 | 118187.162 | ㎡ | 0.02 |  |  | 0.514%
5.6.1.1.2 | 路面工程 | 14182.4594 |  |  | 14182.4594 | 118187.162 | ㎡ | 0.12 |  |  | 3.084%
5.6.2.2 | 场坪工程 | 0 |  |  | 0 | 177280.743 | ㎡ |  |  |  | 0%
5.6.2.2.1 | 地基处理 | 0 |  |  | 0 | 0 | ㎡ | 0.02 |  |  | 0%
5.6.2.2.2 | 场坪工程 | 0 |  |  | 0 | 0 | ㎡ | 0.15 |  |  | 0%
5.6.1.1.3 | 室外给排水工程 | 2363.7432 |  |  | 2363.7432 | 590935.81 | ㎡ | 0.004 |  |  | 0.514%
5.6.1.1.4 | 室外电气工程 | 2954.6791 |  |  | 2954.6791 | 590935.81 | ㎡ | 0.005 |  |  | 0.6425%
5.6.1.2 | 绿化工程 | 6204.826 |  |  | 6204.826 | 206827.5335 | ㎡ | 0.03 |  |  | 1.349%
0%
0%
0%
0%
0%
6 | 能力建设 |  |  | 678 | 678 | [5 empty] | 0.1474%
7 | 专题研究 |  |  | 678 | 678 | [5 empty] | 0.1474%
二 | 工程建设其他费 |  |  | 25877.5207 | 25877.5207 | [5 empty] | 5.627% |  | 437.9978 |  |  | #REF!
1 | 土地费用 |  |  | 0 | 0 | [5 empty] | 0% |  | 1.5286 | 42420
1.1 | 土地使用费 |  |  | 0 | 0 | 1019.0393 | 亩 | 30 |  |  | 0%
1.2 | 土地拆迁费 |  |  | 0 | 0 | 1019.0393 | 亩 | 20 |  |  | 0%
1 | 建设单位管理费 |  |  | 2370.0493 | 2370.0493 |  |  |  | 参照财建[2016]504号 |  | 0.5154%
2 | 工程建设监理费 |  |  | 3300.0903 | 3300.0903 |  |  |  | 参照发改价格[2007]670号 |  | 0.7297% |  |  | -436.4693
3 | 建设项目前期咨询费用 |  |  | 290 | 290 | [5 empty] | 0.06306% |  |  |  |  | 5460
3.1 | 可研报告及资金申请报告编制 |  |  | 290 | 290 |  |  |  | 参照计价格[1999]1283号 |  | 0.06306% |  |  |  |  | 1.6849
4 | 水土保持相关费用 |  |  | 1016 | 1016 |  |  |  | 参照水利部保监[2005]22号 |  | 0.2209%
4.1 | 水土保持方案编制费 |  |  | 280 | 280 |  |  |  | 参照水利部保监[2005]22号 |  | 0.06089%
4.2 | 水土保持监测费 |  |  | 608 | 608 |  |  |  | 参照水利部保监[2005]22号 |  | 0.1322%
4.3 | 水土保持设施竣工验收技术评估报告编制费 |  |  | 128 | 128 |  |  |  | 参照水利部保监[2005]22号 |  | 0.02783%
5 | 水土保持补偿费 |  |  | 101.9044 | 101.9044 | 679362.9 | ㎡ |  | 鄂价环资[2017]93号 |  | 0.02216% |  |  | 1.33 | 10000 | 1.33*100*10000
6 | 勘察设计费 |  |  | 8465.8356 | 8465.8356 | [5 empty] | 1.874%
6.1 | 工程勘察费 |  |  | 2113.2079 | 2113.2079 |  |  |  | 参照计价格[2002]10号 |  | 0.4684%
6.2 | 工程设计费 |  |  | 5552.9963 | 5552.9963 |  |  |  | 参照计价格[2002]10号 |  | 1.229%
6.3 | 施工图预算编制费 |  |  | 444.2397 | 444.2397 |  |  |  | 参照计价格[2002]10号 |  | 0.09831%
6.4 | 竣工图编制费 |  |  | 355.3918 | 355.3918 | [5 empty] | 0.07864%
7 | 建设工程造价咨询服务费 |  |  | #REF! | #REF! |  |  |  | 参照鄂价工服规[2012]149号 |  | 0.6667%
7.1 | 工程量清单编制 |  |  | 183.3944 | 183.3944 |  |  |  | 参照鄂价工服规[2012]149号 |  | 0.04058%
7.2 | 控制价编制 |  |  | 116.2566 | 116.2566 |  |  |  | 参照鄂价工服规[2012]149号 |  | 0.0257%
7.3 | 施工阶段全过程造价控制 |  |  | 1355.7549 | 1355.7549 |  |  |  | 参照鄂价工服规[2012]149号 |  | 0.3004%
7.4 | 竣工决算审核 |  |  | 1379.6471 | 1379.6471 |  |  |  | 参照鄂价工服规[2012]149号 |  | 0.3%
8 | 场地准备及临时设施费 |  |  | 1650.9437 | 1650.9437 |  |  |  | 工程费用1% |  | 0.366%
9 | 工程保险费 |  |  | 1650.9437 | 1650.9437 |  |  |  | 工程费用0.5% |  | 0.366%
10 | 招标代理服务费 |  |  | 138.5051 | 138.5051 |  |  |  | 参照计价格[2002]1980号 |  | 0.03033%
10.1 | 工程招标 |  |  | 98.5689 | 98.5689 | [5 empty] | 0.02157%
10.2 | 服务招标 |  |  | 39.9362 | 39.9362 | [5 empty] | 0.008758%
10.2.1 | 设计招标 |  |  | 17.503 | 17.503 | [5 empty] | 0.003827%
10.2.2 | 勘察招标 |  |  | 9.733 | 9.733 | [5 empty] | 0.002139%
10.2.3 | 监理招标 |  |  | 12.7002 | 12.7002 | [5 empty] | 0.002792%
11 | 环境影响咨询服务费 |  |  | 70.9882 | 70.9882 | [5 empty] | 0.01544%
12 | 社会稳定性风险评估 |  |  | 113.9824 | 113.9824 | [5 empty] | 0.02479%
13 | 节能报告评估 |  |  | 40 | 40 | [5 empty] | 0.008698%
14 | 建筑垃圾服务费 |  |  | 782.1378 | 782.1378 | [5 empty] | 0.1701%
15 | 地质灾害危害性评估 |  |  | 40 | 40 | [5 empty] | 0.008698%
16 | 交通影响评价费 |  |  | 50 | 50 | [5 empty] | 0.01087% |  | 123280.7029
17 | 高可靠性供电费 |  |  | 100 | 100 | [5 empty] | 0.02174%
18 | 第三方检测费 |  |  | 2311.3211 | 2311.3211 | [5 empty] | 0.5124%
三 | 预备费 |  |  |  | 18123.9594 |  |  |  | (1+2)×5% |  | 3.941%
四 | 专项费用 |  |  | 55251.9627 | 55251.9627 | [5 empty] | 12.01%
1 | 土地费用 |  |  | 50951.9627 | 50951.9627 | [5 empty] | 11.08%
1.1 | 土地使用费 |  |  | 30571.1776 | 30571.1776 | 1019.0393 | 亩 | 30 |  |  | 6.648%
1.2 | 土地拆迁费 |  |  | 20380.7851 | 20380.7851 | 1019.0393 | 亩 | 20 |  |  | 4.432%
2 | 外电报装 |  |  | 3000 | 3000 | [5 empty] | 0.6523%
3 | 外水报装 |  |  | 600 | 600 | [5 empty] | 0.1305%
4 | 燃气报装 |  |  | 700 | 700 | [5 empty] | 0.1522%
五 | 建设投资 |  |  |  | 435855.1103 |  |  |  | （一+二+三） |  | 94.78%
六 | 建设期利息及贷款费用 |  |  |  | 22374 | [5 empty] | 4.865%
1 | 建设期利息 |  |  |  | 20340 | [5 empty] | 4.423%
2 | 先征费（0.25%） |  |  |  | 678 | [5 empty] | 0.1474%
3 | 承诺费（0.25%） |  |  |  | 1356 | [5 empty] | 0.2949%
七 | 流动资金 |  |  |  | 1653.26 | [5 empty] | 0.3595%
八 | 总投资 |  |  |  | 459882.3703 |  |  |  | （四+五+六+七） |  | 100%
|  |  | 序号 | 名称 | 费用（万元） | 占总投资比列（%） |  |  |  | 459882.3703
|  |  | 一 | 建设投资 | 435855.1103 | 94.78% |  |  |  | 547044.3977
|  |  | 1 | 工程费用 | 330188.7319 | 73.19% |  |  |  | -87162.0274
|  |  | 2 | 工程建设其他费用 | 25877.5207 | 5.627%
|  |  | 3 | 预备费 | 18123.9594 | 3.941%
|  |  | 4 | 专项费用 | 55251.9627 | 12.01%
|  |  | 二 | 建设期利息及贷款费用 | 22374 | 4.865%
|  |  | 三 | 流动资金 | 1653.26 | 0.3595%
|  |  | 四 | 总投资 | 459882.3703 | 100% |  |  |  | 73682.7895
486.9233
0
62.84
|  | 698435.1722 | 238552.802

## 工艺设备投资(前表4.2))_20231212 (hidden)
1#国际货站工艺设备投资--摘自初步设计概算批复
| 项目 | 概算 | 单位 | 说明
| 总工艺设备投资 | 11507 | 万元
1 | 航空集装器CT安检系统 | 7000 | 万元 | 含软件系统
2 | 民航专业工程设备投资 | 1375.5 | 万元 | 货物安检及人员安检通道设备及分层管理系统，不含前后端输送设备
3 | 主要运行设备及海关设备 | 2013 | 万元 | 调平台、输送机、地秤、升降打板台、移动打板台、核辐射通道等
4 | 货站内的车辆、可移动设备等 | 1118.5 | 万元 | 叉车、牵引车、集装板车、拖斗、货架等
1#国际货站设施规模：站房面积约15150平米、建筑面积22650平米。
2.2亿工艺设备投资为业主负责数据。本次设备估算以初步设计概算为基础进行估算
|  | 概算 | 单位 | 说明
1 | 2#国际货站工艺设备投资 | 4507 | 万元 | 站房面积约15100平米，按1#国际货站站房面积折算2#国际货站工艺设备投资
1.1 | 民航专业工程设备投资 | 1375.5 | 万元
1.2 | 主要运行设备及海关设备 | 2013 | 万元
1.3 | 货站内的车辆、可移动设备等 | 1118.5 | 万元
2 | 3#国际货站工艺设备投资 | 4507 | 万元 | 站房面积约15100平米，按1#国际货站站房面积折算3#国际货站工艺设备投资
2.1 | 民航专业工程设备投资 | 1375.5 | 万元
2.2 | 主要运行设备及海关设备 | 2013 | 万元
2.3 | 货站内的车辆、可移动设备等 | 1118.5 | 万元
3 | 航空集装器CT安检系统 | 7000 | 万元
4 | 8#~9#、11#~14#海关监管库、15~18#保税仓库 | 800 | 万元 | 海关监管库、保税仓库仅考虑土建相关设备，如调平台（叉车考虑由运营商自行提供）。按开面长度估算调平台数量及投资
(注：此部分内容不清晰，未纳入采购计划)
5 | 快件中心工艺设备 | 5186 | 万元
| 合计 | 22000 | 万元

## 20231205可研预算 (hidden)
总投资估算表（扣除先期启动）
序号 | 工程和费用名称 | 估算价值(万元) |  |  |  | 技术经济指标 |  |  | 备 注 | 比例 |  |  |  |  | 公告日期 | 合同 签订日期 | 合同 月数
|  | 建筑工程 | 设备及安装 工程费 | 其他费用 | 合 计 | 室内面积或数量 |  | （万元） | [5 empty] | 合同号
一 | 工程费用 | 316144.55 | 44671.88 | 1456 | 362272.43 |  |  |  | （1+2+3） | 70.59% |  | 314176.66
1 | 海关业务基础设施 | 45278.13 | 360 | 0 | 45638.13 |  |  |  |  | 8.89% |  |  |  | 21367.72
1.2 | 2#国际货站 | 10593.86 | 90 | 0 | 10683.86 | 19474 | ㎡ | 0.549 |  | 2.08% |  |  | CW01 |  |  | 2025Q2 | 18
1.2.1 | 地基处理 | 97.37 |  |  | 97.37 | 19474 | ㎡ | 0.005 |  | 0.02%
1.2.2 | 基础工程 | 116.84 |  |  | 116.84 | 19474 | ㎡ | 0.006 |  | 0.02%
1.2.3 | 土建工程 | 4868.5 |  |  | 4868.5 | 19474 | ㎡ | 0.25 |  | 0.95%
1.2.4 | 装饰装修工程 | 2921.1 |  |  | 2921.1 | 19474 | ㎡ | 0.15 |  | 0.57%
1.2.5 | 给排水工程 | 292.11 |  |  | 292.11 | 19474 | ㎡ | 0.015 |  | 0.06%
1.2.6 | 暖通工程 | 778.96 |  |  | 778.96 | 19474 | ㎡ | 0.04 |  | 0.15%
1.2.7 | 电气工程 | 1363.18 |  |  | 1363.18 | 19474 | ㎡ | 0.07 |  | 0.27%
1.2.8 | 电梯工程 |  | 90 |  | 90 | 2 | 部 | 45 |  | 0.02%
1.2.9 | 抗震支架 | 116.84 |  |  | 116.84 | 19474 | ㎡ | 0.006 |  | 0.02%
1.2.10 | 标识标牌 | 38.95 |  |  | 38.95 | 19474 | ㎡ | 0.002 |  | 0.01%
1.3 | 3#国际货站 | 10593.86 | 90 | 0 | 10683.86 | 19474 | ㎡ | 0.549 |  | 2.08% | 2#+3#国际货站 | 21367.72 | CW01 | CW02 |  | 2025Q2 | 18
1.3.1 | 地基处理 | 97.37 |  |  | 97.37 | 19474 | ㎡ | 0.005 |  | 0.02%
1.3.2 | 基础工程 | 116.84 |  |  | 116.84 | 19474 | ㎡ | 0.006 |  | 0.02%
1.3.3 | 土建工程 | 4868.5 |  |  | 4868.5 | 19474 | ㎡ | 0.25 |  | 0.95%
1.3.4 | 装饰装修工程 | 2921.1 |  |  | 2921.1 | 19474 | ㎡ | 0.15 |  | 0.57%
1.3.5 | 给排水工程 | 292.11 |  |  | 292.11 | 19474 | ㎡ | 0.015 |  | 0.06%
1.3.6 | 暖通工程 | 778.96 |  |  | 778.96 | 19474 | ㎡ | 0.04 |  | 0.15%
1.3.7 | 电气工程 | 1363.18 |  |  | 1363.18 | 19474 | ㎡ | 0.07 |  | 0.27%
1.3.8 | 电梯工程 |  | 90 |  | 90 | 2 | 部 | 45 |  | 0.02%
1.3.9 | 抗震支架 | 116.84 |  |  | 116.84 | 19474 | ㎡ | 0.006 |  | 0.02%
1.3.10 | 标识标牌 | 38.95 |  |  | 38.95 | 19474 | ㎡ | 0.002 |  | 0.01%
1.4 | 4#国际快件中心 | 22880.59 | 180 | 0 | 23060.59 | 45398 | ㎡ | 0.508 |  | 4.49% |  |  |  | CW03 |  | 2025Q2 | 18
1.4.1 | 地基处理 | 226.99 |  |  | 226.99 | 45398 | ㎡ | 0.005 |  | 0.04%
1.4.2 | 基础工程 | 272.39 |  |  | 272.39 | 45398 | ㎡ | 0.006 |  | 0.05%
1.4.3 | 土建工程 | 10441.54 |  |  | 10441.54 | 45398 | ㎡ | 0.23 |  | 2.03%
1.4.4 | 装饰装修工程 | 5901.74 |  |  | 5901.74 | 45398 | ㎡ | 0.13 |  | 1.15%
1.4.5 | 给排水工程 | 680.97 |  |  | 680.97 | 45398 | ㎡ | 0.015 |  | 0.13%
1.4.6 | 暖通工程 | 1815.92 |  |  | 1815.92 | 45398 | ㎡ | 0.04 |  | 0.35%
1.4.7 | 电气工程 | 3177.86 |  |  | 3177.86 | 45398 | ㎡ | 0.07 |  | 0.62%
1.4.8 | 电梯工程 |  | 180 |  | 180 | 4 | 部 | 45 |  | 0.04%
1.4.9 | 抗震支架 | 272.39 |  |  | 272.39 | 45398 | ㎡ | 0.006 |  | 0.05%
1.4.10 | 标识标牌 | 90.8 |  |  | 90.8 | 45398 | ㎡ | 0.002 |  | 0.02%
1.10 | 2#海关卡口 | 481.62 |  |  | 481.62 | 949 | ㎡ | 0.508 |  | 0.09%
1.10.1 | 地基处理 | 3.32 |  |  | 3.32 | 949 | ㎡ | 0.004 |  | 0%
1.10.2 | 土建工程 | 455.52 |  |  | 455.52 | 949 | ㎡ | 0.48 |  | 0.09%
1.10.3 | 给排水工程 | 2.85 |  |  | 2.85 | 949 | ㎡ | 0.003 |  | 0%
1.10.4 | 暖通工程 | 3.8 |  |  | 3.8 | 949 | ㎡ | 0.004 |  | 0%
1.10.5 | 电气工程 | 8.54 |  |  | 8.54 | 949 | ㎡ | 0.009 |  | 0%
1.10.6 | 抗震支架 | 5.69 |  |  | 5.69 | 949 | ㎡ | 0.006 |  | 0%
1.10.7 | 标识标牌 | 1.9 |  |  | 1.9 | 949 | ㎡ | 0.002 |  | 0%
1.12 | 4#海关卡口 | 264.41 |  |  | 264.41 | 521 | ㎡ | 0.508 |  | 0.05%
1.12.1 | 地基处理 | 1.82 |  |  | 1.82 | 521 | ㎡ | 0.004 |  | 0%
1.12.2 | 土建工程 | 250.08 |  |  | 250.08 | 521 | ㎡ | 0.48 |  | 0.05%
1.12.3 | 给排水工程 | 1.56 |  |  | 1.56 | 521 | ㎡ | 0.003 |  | 0%
1.12.4 | 暖通工程 | 2.08 |  |  | 2.08 | 521 | ㎡ | 0.004 |  | 0%
1.12.5 | 电气工程 | 4.69 |  |  | 4.69 | 521 | ㎡ | 0.009 |  | 0%
1.12.6 | 抗震支架 | 3.13 |  |  | 3.13 | 521 | ㎡ | 0.006 |  | 0%
1.12.7 | 标识标牌 | 1.04 |  |  | 1.04 | 521 | ㎡ | 0.002 |  | 0%
1.14 | 海关围网 | 463.8 |  |  | 463.8 | 7730 | 延米 | 0.06 |  | 0.09%
2 | 保税仓储和加工 | 90687.6 | 360 | 0 | 91047.6 |  |  |  |  | 17.74% |  |  |  | 88325.13
2.1 | 8#保税加工中心 | 19377.15 | 180 | 0 | 19557.15 | 39225 | ㎡ | 0.499 |  | 3.81%
2.1.1 | 地基处理 | 196.13 |  |  | 196.13 | 39225 | ㎡ | 0.005 |  | 0.04%
2.1.2 | 基础工程 | 235.35 |  |  | 235.35 | 39225 | ㎡ | 0.006 |  | 0.05%
2.1.3 | 土建工程 | 9414 |  |  | 9414 | 39225 | ㎡ | 0.24 |  | 1.83%
2.1.4 | 装饰装修工程 | 4707 |  |  | 4707 | 39225 | ㎡ | 0.12 |  | 0.92%
2.1.5 | 给排水工程 | 588.38 |  |  | 588.38 | 39225 | ㎡ | 0.015 |  | 0.11%
2.1.6 | 暖通工程 | 1176.75 |  |  | 1176.75 | 39225 | ㎡ | 0.03 |  | 0.23%
2.1.7 | 电气工程 | 2745.75 |  |  | 2745.75 | 39225 | ㎡ | 0.07 |  | 0.54%
2.1.8 | 电梯工程 |  | 180 |  | 180 | 4 | 部 | 45 |  | 0.04%
2.1.9 | 抗震支架 | 235.35 |  |  | 235.35 | 39225 | ㎡ | 0.006 |  | 0.05%
2.1.10 | 标识标牌 | 78.45 |  |  | 78.45 | 39225 | ㎡ | 0.002 |  | 0.02%
2.2 | 9#保税加工中心 | 11200.76 | 180 | 0 | 11380.76 | 20936 | ㎡ | 0.544 |  | 2.22%
2.2.1 | 地基处理 | 104.68 |  |  | 104.68 | 20936 | ㎡ | 0.005 |  | 0.02%
2.2.2 | 基础工程 | 146.55 |  |  | 146.55 | 20936 | ㎡ | 0.007 |  | 0.03%
2.2.3 | 土建工程 | 5443.36 |  |  | 5443.36 | 20936 | ㎡ | 0.26 |  | 1.06%
2.2.4 | 装饰装修工程 | 2931.04 |  |  | 2931.04 | 20936 | ㎡ | 0.14 |  | 0.57%
2.2.5 | 给排水工程 | 314.04 |  |  | 314.04 | 20936 | ㎡ | 0.015 |  | 0.06%
2.2.6 | 暖通工程 | 628.08 |  |  | 628.08 | 20936 | ㎡ | 0.03 |  | 0.12%
2.2.7 | 电气工程 | 1465.52 |  |  | 1465.52 | 20936 | ㎡ | 0.07 |  | 0.29%
2.2.8 | 电梯工程 |  | 180 |  | 180 | 4 | 部 | 45 |  | 0.04%
2.2.9 | 抗震支架 | 125.62 |  |  | 125.62 | 20936 | ㎡ | 0.006 |  | 0.02%
2.2.10 | 标识标牌 | 41.87 |  |  | 41.87 | 20936 | ㎡ | 0.002 |  | 0.01%
2.3 | 10#危险品库区 | 2722.5 | 0 | 0 | 2722.5 | 4500 | ㎡ | 0.605 |  | 0.53%
2.3.1 | 地基处理 | 22.5 |  |  | 22.5 | 4500 | ㎡ | 0.005 |  | 0%
2.3.2 | 基础工程 | 31.5 |  |  | 31.5 | 4500 | ㎡ | 0.007 |  | 0.01%
2.3.3 | 土建工程 | 1170 |  |  | 1170 | 4500 | ㎡ | 0.26 |  | 0.23%
2.3.4 | 装饰装修工程 | 810 |  |  | 810 | 4500 | ㎡ | 0.18 |  | 0.16%
2.3.5 | 给排水工程 | 67.5 |  |  | 67.5 | 4500 | ㎡ | 0.015 |  | 0.01%
2.3.6 | 暖通工程 | 225 |  |  | 225 | 4500 | ㎡ | 0.05 |  | 0.04%
2.3.7 | 电气工程 | 360 |  |  | 360 | 4500 | ㎡ | 0.08 |  | 0.07%
2.3.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.3.9 | 抗震支架 | 27 |  |  | 27 | 4500 | ㎡ | 0.006 |  | 0.01%
2.3.10 | 标识标牌 | 9 |  |  | 9 | 4500 | ㎡ | 0.002 |  | 0%
2.4 | 11#保税物流中心 | 9822.7 | 0 | 0 | 9822.7 | 19884 | ㎡ | 0.494 |  | 1.91%
2.4.1 | 地基处理 | 99.42 |  |  | 99.42 | 19884 | ㎡ | 0.005 |  | 0.02%
2.4.2 | 基础工程 | 119.3 |  |  | 119.3 | 19884 | ㎡ | 0.006 |  | 0.02%
2.4.3 | 土建工程 | 4772.16 |  |  | 4772.16 | 19884 | ㎡ | 0.24 |  | 0.93%
2.4.4 | 装饰装修工程 | 2386.08 |  |  | 2386.08 | 19884 | ㎡ | 0.12 |  | 0.46%
2.4.5 | 给排水工程 | 298.26 |  |  | 298.26 | 19884 | ㎡ | 0.015 |  | 0.06%
2.4.6 | 暖通工程 | 596.52 |  |  | 596.52 | 19884 | ㎡ | 0.03 |  | 0.12%
2.4.7 | 电气工程 | 1391.88 |  |  | 1391.88 | 19884 | ㎡ | 0.07 |  | 0.27%
2.4.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.4.9 | 抗震支架 | 119.3 |  |  | 119.3 | 19884 | ㎡ | 0.006 |  | 0.02%
2.4.10 | 标识标牌 | 39.77 |  |  | 39.77 | 19884 | ㎡ | 0.002 |  | 0.01%
2.5 | 12#保税物流中心 | 9822.7 | 0 | 0 | 9822.7 | 19884 | ㎡ | 0.494 |  | 1.91%
2.5.1 | 地基处理 | 99.42 |  |  | 99.42 | 19884 | ㎡ | 0.005 |  | 0.02%
2.5.2 | 基础工程 | 119.3 |  |  | 119.3 | 19884 | ㎡ | 0.006 |  | 0.02%
2.5.3 | 土建工程 | 4772.16 |  |  | 4772.16 | 19884 | ㎡ | 0.24 |  | 0.93%
2.5.4 | 装饰装修工程 | 2386.08 |  |  | 2386.08 | 19884 | ㎡ | 0.12 |  | 0.46%
2.5.5 | 给排水工程 | 298.26 |  |  | 298.26 | 19884 | ㎡ | 0.015 |  | 0.06%
2.5.6 | 暖通工程 | 596.52 |  |  | 596.52 | 19884 | ㎡ | 0.03 |  | 0.12%
2.5.7 | 电气工程 | 1391.88 |  |  | 1391.88 | 19884 | ㎡ | 0.07 |  | 0.27%
2.5.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.5.9 | 抗震支架 | 119.3 |  |  | 119.3 | 19884 | ㎡ | 0.006 |  | 0.02%
2.5.10 | 标识标牌 | 39.77 |  |  | 39.77 | 19884 | ㎡ | 0.002 |  | 0.01%
2.6 | 13#保税物流中心 | 6862.1 | 0 | 0 | 6862.1 | 12591 | ㎡ | 0.545 |  | 1.34%
2.6.1 | 地基处理 | 62.96 |  |  | 62.96 | 12591 | ㎡ | 0.005 |  | 0.01%
2.6.2 | 基础工程 | 88.14 |  |  | 88.14 | 12591 | ㎡ | 0.007 |  | 0.02%
2.6.3 | 土建工程 | 3147.75 |  |  | 3147.75 | 12591 | ㎡ | 0.25 |  | 0.61%
2.6.4 | 装饰装修工程 | 1888.65 |  |  | 1888.65 | 12591 | ㎡ | 0.15 |  | 0.37%
2.6.5 | 给排水工程 | 188.87 |  |  | 188.87 | 12591 | ㎡ | 0.015 |  | 0.04%
2.6.6 | 暖通工程 | 503.64 |  |  | 503.64 | 12591 | ㎡ | 0.04 |  | 0.1%
2.6.7 | 电气工程 | 881.37 |  |  | 881.37 | 12591 | ㎡ | 0.07 |  | 0.17%
2.6.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.6.9 | 抗震支架 | 75.55 |  |  | 75.55 | 12591 | ㎡ | 0.006 |  | 0.01%
2.6.10 | 标识标牌 | 25.18 |  |  | 25.18 | 12591 | ㎡ | 0.002 |  | 0%
2.7 | 14#保税物流中心 | 6862.1 | 0 | 0 | 6862.1 | 12591 | ㎡ | 0.545 |  | 1.34% | 8#-14#(minus 10#)保税物流中心 | 64307.51 | CW04 |  |  | 2024Q4 | 24
2.7.1 | 地基处理 | 62.96 |  |  | 62.96 | 12591 | ㎡ | 0.005 |  | 0.01%
2.7.2 | 基础工程 | 88.14 |  |  | 88.14 | 12591 | ㎡ | 0.007 |  | 0.02%
2.7.3 | 土建工程 | 3147.75 |  |  | 3147.75 | 12591 | ㎡ | 0.25 |  | 0.61%
2.7.4 | 装饰装修工程 | 1888.65 |  |  | 1888.65 | 12591 | ㎡ | 0.15 |  | 0.37%
2.7.5 | 给排水工程 | 188.87 |  |  | 188.87 | 12591 | ㎡ | 0.015 |  | 0.04%
2.7.6 | 暖通工程 | 503.64 |  |  | 503.64 | 12591 | ㎡ | 0.04 |  | 0.1%
2.7.7 | 电气工程 | 881.37 |  |  | 881.37 | 12591 | ㎡ | 0.07 |  | 0.17%
2.7.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.7.9 | 抗震支架 | 75.55 |  |  | 75.55 | 12591 | ㎡ | 0.006 |  | 0.01%
2.7.10 | 标识标牌 | 25.18 |  |  | 25.18 | 12591 | ㎡ | 0.002 |  | 0%
2.8 | 15#保税物流中心 | 5399.86 | 0 | 0 | 5399.86 | 9908 | ㎡ | 0.545 |  | 1.05%
2.8.1 | 地基处理 | 49.54 |  |  | 49.54 | 9908 | ㎡ | 0.005 |  | 0.01%
2.8.2 | 基础工程 | 69.36 |  |  | 69.36 | 9908 | ㎡ | 0.007 |  | 0.01%
2.8.3 | 土建工程 | 2477 |  |  | 2477 | 9908 | ㎡ | 0.25 |  | 0.48%
2.8.4 | 装饰装修工程 | 1486.2 |  |  | 1486.2 | 9908 | ㎡ | 0.15 |  | 0.29%
2.8.5 | 给排水工程 | 148.62 |  |  | 148.62 | 9908 | ㎡ | 0.015 |  | 0.03%
2.8.6 | 暖通工程 | 396.32 |  |  | 396.32 | 9908 | ㎡ | 0.04 |  | 0.08%
2.8.7 | 电气工程 | 693.56 |  |  | 693.56 | 9908 | ㎡ | 0.07 |  | 0.14%
2.8.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.8.9 | 抗震支架 | 59.45 |  |  | 59.45 | 9908 | ㎡ | 0.006 |  | 0.01%
2.8.10 | 标识标牌 | 19.82 |  |  | 19.82 | 9908 | ㎡ | 0.002 |  | 0%
2.9 | 16#保税物流中心 | 6205.92 | 0 | 0 | 6205.92 | 11387 | ㎡ | 0.545 |  | 1.21%
2.9.1 | 地基处理 | 56.94 |  |  | 56.94 | 11387 | ㎡ | 0.005 |  | 0.01%
2.9.2 | 基础工程 | 79.71 |  |  | 79.71 | 11387 | ㎡ | 0.007 |  | 0.02%
2.9.3 | 土建工程 | 2846.75 |  |  | 2846.75 | 11387 | ㎡ | 0.25 |  | 0.55%
2.9.4 | 装饰装修工程 | 1708.05 |  |  | 1708.05 | 11387 | ㎡ | 0.15 |  | 0.33%
2.9.5 | 给排水工程 | 170.81 |  |  | 170.81 | 11387 | ㎡ | 0.015 |  | 0.03%
2.9.6 | 暖通工程 | 455.48 |  |  | 455.48 | 11387 | ㎡ | 0.04 |  | 0.09%
2.9.7 | 电气工程 | 797.09 |  |  | 797.09 | 11387 | ㎡ | 0.07 |  | 0.16%
2.9.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.9.9 | 抗震支架 | 68.32 |  |  | 68.32 | 11387 | ㎡ | 0.006 |  | 0.01%
2.9.10 | 标识标牌 | 22.77 |  |  | 22.77 | 11387 | ㎡ | 0.002 |  | 0%
2.1 | 17#保税物流中心 | 6205.92 | 0 | 0 | 6205.92 | 11387 | ㎡ | 0.545 |  | 1.21%
2.10.1 | 地基处理 | 56.94 |  |  | 56.94 | 11387 | ㎡ | 0.005 |  | 0.01%
2.10.2 | 基础工程 | 79.71 |  |  | 79.71 | 11387 | ㎡ | 0.007 |  | 0.02%
2.10.3 | 土建工程 | 2846.75 |  |  | 2846.75 | 11387 | ㎡ | 0.25 |  | 0.55%
2.10.4 | 装饰装修工程 | 1708.05 |  |  | 1708.05 | 11387 | ㎡ | 0.15 |  | 0.33%
2.10.5 | 给排水工程 | 170.81 |  |  | 170.81 | 11387 | ㎡ | 0.015 |  | 0.03%
2.10.6 | 暖通工程 | 455.48 |  |  | 455.48 | 11387 | ㎡ | 0.04 |  | 0.09%
2.10.7 | 电气工程 | 797.09 |  |  | 797.09 | 11387 | ㎡ | 0.07 |  | 0.16%
2.10.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.10.9 | 抗震支架 | 68.32 |  |  | 68.32 | 11387 | ㎡ | 0.006 |  | 0.01%
2.10.10 | 标识标牌 | 22.77 |  |  | 22.77 | 11387 | ㎡ | 0.002 |  | 0%
2.11 | 18#保税物流中心 | 6205.92 | 0 | 0 | 6205.92 | 11387 | ㎡ | 0.545 |  | 1.21% | 15#+16#+17#+18#保税物流中心 | 24017.62 | CW05 |  |  | 2025Q4 | 24
2.11.1 | 地基处理 | 56.94 |  |  | 56.94 | 11387 | ㎡ | 0.005 |  | 0.01%
2.11.2 | 基础工程 | 79.71 |  |  | 79.71 | 11387 | ㎡ | 0.007 |  | 0.02%
2.11.3 | 土建工程 | 2846.75 |  |  | 2846.75 | 11387 | ㎡ | 0.25 |  | 0.55%
2.11.4 | 装饰装修工程 | 1708.05 |  |  | 1708.05 | 11387 | ㎡ | 0.15 |  | 0.33%
2.11.5 | 给排水工程 | 170.81 |  |  | 170.81 | 11387 | ㎡ | 0.015 |  | 0.03%
2.11.6 | 暖通工程 | 455.48 |  |  | 455.48 | 11387 | ㎡ | 0.04 |  | 0.09%
2.11.7 | 电气工程 | 797.09 |  |  | 797.09 | 11387 | ㎡ | 0.07 |  | 0.16%
2.11.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.11.9 | 抗震支架 | 68.32 |  |  | 68.32 | 11387 | ㎡ | 0.006 |  | 0.01%
2.11.10 | 标识标牌 | 22.77 |  |  | 22.77 | 11387 | ㎡ | 0.002 |  | 0%
3 | 贸易和货运服务设施 | 96421.65 | 810 | 0 | 97231.65 |  |  |  |  | 18.95% |  |  |  | 97231.65
3.1 | 19#综合配套中心 | 59191.65 | 360 | 0 | 59551.65 |  | ㎡ |  |  | 11.6% | 19#综合配套中心 | 59551.65 | CW06 |  |  | 2026Q2 | 30
3.1.1 | 地上 | 38311.65 | 360 | 0 | 38671.65 | 57525 | ㎡ | 0.672 |  | 7.54%
3.1.1.1 | 地基处理 | 287.63 |  |  | 287.63 | 57525 | ㎡ | 0.005 |  | 0.06%
3.1.1.2 | 基础工程 | 8053.5 |  |  | 8053.5 | 57525 | ㎡ | 0.14 |  | 1.57%
3.1.1.3 | 土建工程 | 14381.25 |  |  | 14381.25 | 57525 | ㎡ | 0.25 |  | 2.8%
3.1.1.4 | 装饰装修工程 | 8628.75 |  |  | 8628.75 | 57525 | ㎡ | 0.15 |  | 1.68%
3.1.1.5 | 给排水工程 | 747.83 |  |  | 747.83 | 57525 | ㎡ | 0.013 |  | 0.15%
3.1.1.6 | 暖通工程 | 2301 |  |  | 2301 | 57525 | ㎡ | 0.04 |  | 0.45%
3.1.1.7 | 电气工程 | 3451.5 |  |  | 3451.5 | 57525 | ㎡ | 0.06 |  | 0.67%
3.1.1.8 | 电梯工程 |  | 360 |  | 360 | 8 | 部 | 45 |  | 0.07%
3.1.1.9 | 抗震支架 | 345.15 |  |  | 345.15 | 57525 | ㎡ | 0.006 |  | 0.07%
3.1.1.10 | 标识标牌 | 115.05 |  |  | 115.05 | 57525 | ㎡ | 0.002 |  | 0.02%
3.1.2 | 地下 | 20880 | 0 | 0 | 20880 | 30000 | ㎡ | 0.696 |  | 4.07%
3.1.2.1 | 地基处理 | 150 |  |  | 150 | 30000 | ㎡ | 0.005 |  | 0.03%
3.1.2.2 | 基础工程 | 4200 |  |  | 4200 | 30000 | ㎡ | 0.14 |  | 0.82%
3.1.2.3 | 土建工程 | 7500 |  |  | 7500 | 30000 | ㎡ | 0.25 |  | 1.46%
3.1.2.4 | 装饰装修工程 | 4500 |  |  | 4500 | 30000 | ㎡ | 0.15 |  | 0.88%
3.1.2.5 | 给排水工程 | 390 |  |  | 390 | 30000 | ㎡ | 0.013 |  | 0.08%
3.1.2.6 | 暖通工程 | 1500 |  |  | 1500 | 30000 | ㎡ | 0.05 |  | 0.29%
3.1.2.7 | 电气工程 | 1800 |  |  | 1800 | 30000 | ㎡ | 0.06 |  | 0.35%
3.1.2.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
3.1.2.9 | 人防工程 | 600 |  |  |  | 15000 | ㎡ | 0.04
3.1.2.10 | 抗震支架 | 180 |  |  | 180 | 30000 | ㎡ | 0.006 |  | 0.04%
3.1.2.11 | 标识标牌 | 60 |  |  | 60 | 30000 | ㎡ | 0.002 |  | 0.01%
3.2 | 21#商贸物流大楼 | 37230 | 450 | 0 | 37680 |  | ㎡ |  |  | 7.34% | 20#商贸物流大楼 | 37680 | CW08 |  |  | 2025Q2 | 30 | 路南
3.2.1 | 地上 | 23310 | 450 | 0 | 23760 | 35000 | ㎡ | 0.679 |  | 4.63%
3.2.1.1 | 地基处理 | 175 |  |  | 175 | 35000 | ㎡ | 0.005 |  | 0.03%
3.2.1.2 | 基础工程 | 4900 |  |  | 4900 | 35000 | ㎡ | 0.14 |  | 0.95%
3.2.1.3 | 土建工程 | 8750 |  |  | 8750 | 35000 | ㎡ | 0.25 |  | 1.71%
3.2.1.4 | 装饰装修工程 | 5250 |  |  | 5250 | 35000 | ㎡ | 0.15 |  | 1.02%
3.2.1.5 | 给排水工程 | 455 |  |  | 455 | 35000 | ㎡ | 0.013 |  | 0.09%
3.2.1.6 | 暖通工程 | 1400 |  |  | 1400 | 35000 | ㎡ | 0.04 |  | 0.27%
3.2.1.7 | 电气工程 | 2100 |  |  | 2100 | 35000 | ㎡ | 0.06 |  | 0.41%
3.2.1.8 | 电梯工程 |  | 450 |  | 450 | 10 | 部 | 45 |  | 0.09%
3.2.1.9 | 抗震支架 | 210 |  |  | 210 | 35000 | ㎡ | 0.006 |  | 0.04%
3.2.1.10 | 标识标牌 | 70 |  |  | 70 | 35000 | ㎡ | 0.002 |  | 0.01%
3.2.2 | 地下 | 13920 | 0 | 0 | 13920 | 20000 | ㎡ | 0.696 |  | 2.71%
3.2.2.1 | 地基处理 | 100 |  |  | 100 | 20000 | ㎡ | 0.005 |  | 0.02%
3.2.2.2 | 基础工程 | 2800 |  |  | 2800 | 20000 | ㎡ | 0.14 |  | 0.55%
3.2.2.3 | 土建工程 | 5000 |  |  | 5000 | 20000 | ㎡ | 0.25 |  | 0.97%
3.2.2.4 | 装饰装修工程 | 3000 |  |  | 3000 | 20000 | ㎡ | 0.15 |  | 0.58%
3.2.2.5 | 给排水工程 | 260 |  |  | 260 | 20000 | ㎡ | 0.013 |  | 0.05%
3.2.2.6 | 暖通工程 | 1000 |  |  | 1000 | 20000 | ㎡ | 0.05 |  | 0.19%
3.2.2.7 | 电气工程 | 1200 |  |  | 1200 | 20000 | ㎡ | 0.06 |  | 0.23%
3.2.2.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
3.2.2.9 | 人防工程 | 400 |  |  |  | 10000 | ㎡ | 0.04 |  | 0%
3.2.2.10 | 抗震支架 | 120 |  |  | 120 | 20000 | ㎡ | 0.006 |  | 0.02%
3.2.2.11 | 标识标牌 | 40 |  |  | 40 | 20000 | ㎡ | 0.002 |  | 0.01%
4 | 信息化与相关设备 | 0 | 43141.88 | 0 | 43141.88 |  |  |  |  | 8.41% |  |  |  | 22038.98
4.1 | 弱电工程 |  | 21102.9 |  | 21102.9 |  |  |  |  | 4.11%
4.1.2 | 后期弱电工程 |  | 21102.9 |  | 21102.9 |  |  |  |  | 4.11%
4.1.2.1 | 2#国际货站 |  | 6371.89 |  | 6371.89 | 19474 | ㎡ | 0.327 |  | 1.24% | [5 empty] | 2026Q2 | 12
4.1.2.2 | 3#国际货站 |  | 6371.89 |  | 6371.89 | 19474 | ㎡ | 0.327 |  | 1.24% | [5 empty] | 2026Q2 | 12
4.1.2.3 | 4#国际快件中心 |  | 1634.33 |  | 1634.33 | 45398 | ㎡ | 0.036 |  | 0.32% | 纳入主体工程
4.1.2.4 | 2#海关卡口 |  | 13.48 |  | 13.48 | 949 | ㎡ | 0.014 |  | 0%
4.1.2.5 | 4#海关卡口 |  | 7.4 |  | 7.4 | 521 | ㎡ | 0.014 |  | 0%
4.1.2.7 | 8#保税加工中心 |  | 176.51 |  | 176.51 | 39225 | ㎡ | 0.005 |  | 0.03%
4.1.2.8 | 9#保税加工中心 |  | 94.21 |  | 94.21 | 20936 | ㎡ | 0.005 |  | 0.02%
4.1.2.9 | 10#危险品库区 |  | 20.25 |  | 20.25 | 4500 | ㎡ | 0.005 |  | 0%
4.1.2.10 | 11#保税物流中心 |  | 89.48 |  | 89.48 | 19884 | ㎡ | 0.005 |  | 0.02%
4.1.2.11 | 12#保税物流中心 |  | 89.48 |  | 89.48 | 19884 | ㎡ | 0.005 |  | 0.02%
4.1.2.12 | 13#保税物流中心 |  | 56.66 |  | 56.66 | 12591 | ㎡ | 0.005 |  | 0.01%
4.1.2.13 | 14#保税物流中心 |  | 56.66 |  | 56.66 | 12591 | ㎡ | 0.005 |  | 0.01%
4.1.2.14 | 15#保税物流中心 |  | 44.59 |  | 44.59 | 9908 | ㎡ | 0.005 |  | 0.01%
4.1.2.15 | 16#保税物流中心 |  | 51.24 |  | 51.24 | 11387 | ㎡ | 0.005 |  | 0.01%
4.1.2.16 | 17#保税物流中心 |  | 51.24 |  | 51.24 | 11387 | ㎡ | 0.005 |  | 0.01%
4.1.2.17 | 18#保税物流中心 |  | 51.24 |  | 51.24 | 11387 | ㎡ | 0.005 |  | 0.01%
4.1.2.19 | 19#综合配套中心 |  | 1050.3 |  | 1050.3 | 87525 | ㎡ | 0.012 |  | 0.2%
4.1.2.20 | 20#商贸物流大楼 |  | 660 |  | 660 | 55000 | ㎡ | 0.012 |  | 0.13% | [5 empty] | 2025Q2
4.1.2.21 | 室外工程 |  | 4212.05 |  | 4212.05 | 679362.9 | ㎡ | 0.006 |  | 0.82% | 监控 |  |  |  |  | 最新完工开始 | 48
4.2 | 工艺设备 |  | 22038.98 |  | 22038.98 |  |  |  |  | 4.29% | 工艺设备? | 22038.98 | GD02 |  |  |  |  | 未定
4.2.2 | 后期 |  | 22038.98 |  | 22038.98 |  |  |  |  | 4.29%
5 | 配套设施 | 83757.18 | 0 | 100 | 83857.18 |  |  |  |  | 16.34% |  |  |  | 85213.18
5.1 | 1#高架联络桥 | 8800 | 0 | 0 | 8800 | 11000 | ㎡ | 0.8 |  | 1.71%
5.1.1 | 路基工程 | 1650 |  |  | 1650 | 11000 | ㎡ | 0.15 |  | 0.32%
5.1.2 | 桥梁工程 | 6600 |  |  | 6600 | 11000 | ㎡ | 0.6 |  | 1.29%
5.1.2 | 照明工程 | 550 |  |  | 550 | 11000 | ㎡ | 0.05 |  | 0.11%
5.2 | 2#预留高架联络桥 | 8800 | 0 | 0 | 8800 | 11000 | ㎡ | 0.8 |  | 1.71%
5.2.2 | 路基工程 | 1650 |  |  | 1650 | 11000 | ㎡ | 0.15 |  | 0.32%
5.2.3 | 桥梁工程 | 6600 |  |  | 6600 | 11000 | ㎡ | 0.6 |  | 1.29%
5.2.4 | 照明工程 | 550 |  |  | 550 | 11000 | ㎡ | 0.05 |  | 0.11%
5.3 | 3#平交联络桥 | 4000 | 0 | 0 | 4000 | 5000 | ㎡ | 0.8 |  | 0.78%
5.3.1 | 路基工程 | 750 |  |  | 750 | 5000 | ㎡ | 0.15 |  | 0.15%
5.3.2 | 桥梁工程 | 3000 |  |  | 3000 | 5000 | ㎡ | 0.6 |  | 0.58%
5.3.3 | 照明工程 | 250 |  |  | 250 | 5000 | ㎡ | 0.05 |  | 0.05%
5.4 | 4#高架桥 | 3200 | 0 | 0 | 3200 | 4000 | ㎡ | 0.8 |  | 0.62% | 1#+4#
5.4.1 | 路基工程 | 600 |  |  | 600 | 4000 | ㎡ | 0.15 |  | 0.12%
5.4.2 | 桥梁工程 | 2400 |  |  | 2400 | 4000 | ㎡ | 0.6 |  | 0.47%
5.4.3 | 照明工程 | 200 |  |  | 200 | 4000 | ㎡ | 0.05 |  | 0.04%
5.5 | 21#道口 | 750 | 0 | 0 | 750 | 1500 | ㎡ | 0.5 |  | 0.15% | 1#+2#+3#+4#+21# | 25550 | CW09
5.5.1 | 路基工程 | 225 |  |  | 225 | 1500 | ㎡ | 0.15 |  | 0.04%
5.5.2 | 桥梁工程 | 450 |  |  | 450 | 1500 | ㎡ | 0.3 |  | 0.09%
5.5.3 | 照明工程 | 75 |  |  | 75 | 1500 | ㎡ | 0.05 |  | 0.01%
5.1 | 道路、场坪、绿化等 | 58207.18 | 0 | 0 | 58207.18 | 590935.81 | ㎡ | 0.1 |  | 11.34%
5.10.2 | 二期 | 58207.18 |  |  |  | 590935.81
5.10.2.1 | 道路工程 | 16546.2 |  |  | 16546.2 | 118187.162 | ㎡ |  |  | 3.22% | 多少条、名称、长度? | 16546.2 | CW10
5.10.2.1.1 | 地基处理 | 2363.74 |  |  | 2363.74 | 118187.162 | ㎡ | 0.02 |  | 0.46%
5.10.2.1.2 | 道路工程 | 14182.46 |  |  | 14182.46 | 118187.162 | ㎡ | 0.12 |  | 2.76%
5.10.2.2 | 场坪工程 | 30137.73 |  |  | 30137.73 | 177280.743 | ㎡ |  |  | 5.87% | ??? | 30137.73 | CW11
5.10.2.2.1 | 地基处理 | 3545.61 |  |  | 3545.61 | 177280.743 | ㎡ | 0.02 |  | 0.69%
5.10.2.2.2 | 场坪工程 | 26592.11 |  |  | 26592.11 | 177280.743 | ㎡ | 0.15 |  | 5.18%
5.10.2.3 | 绿化工程 | 6204.83 |  |  | 6204.83 | 206827.53 | ㎡ | 0.03 |  | 1.21% |  | 6204.83 | CW12
5.10.2.4 | 室外给排水工程 | 2363.74 |  |  | 2363.74 | 590935.81 | ㎡ | 0.004 |  | 0.46% |  | 2363.74
5.10.2.5 | 室外电气工程 | 2954.68 |  |  | 2954.68 | 590935.81 | ㎡ | 0.005 |  | 0.58% |  | 2954.68
5.11 | 建筑工人实名制 |  |  | 50 | 50 |  |  |  |  | 0.01% | ?? | 50
5.12 | 智慧工地管理费 |  |  | 50 | 50 |  |  |  |  | 0.01% | ?? | 50
6 | 能力建设 |  |  | 678 | 678 |  |  |  |  | 0.13% | ?? | 678
7 | 专题研究 |  |  | 678 | 678 |  |  |  |  | 0.13% | ?? | 678
628353.32
二 | 工程建设其他费 |  |  | 88080.8 | 88080.8 |  |  |  |  | 17.16%
1 | 土地费用 |  |  | 50951.96 | 50951.96 |  |  |  |  | 9.93%
2 | 建设单位管理费 |  |  | 2582.37 | 2582.37 |  |  |  | 参照财建[2016]504号 | 0.5%
3 | 工程建设监理费 |  |  | 3611.35 | 3611.35 |  |  |  | 参照发改价格[2007]670号 | 0.7%
4 | 建设项目前期咨询费用 |  |  | 290 | 290 |  |  |  |  | 0.06%
4.1 | 可研报告及资金申请报告编制 |  |  | 290 | 290 |  |  |  | 参照计价格[1999]1283号 | 0.06%
5 | 水土保持相关费用 |  |  | 1016 | 1016 |  |  |  | 参照水利部保监[2005]22号 | 0.2%
5.1 | 水土保持方案编制费 |  |  | 280 | 280 |  |  |  | 参照水利部保监[2005]22号 | 0.05%
5.2 | 水土保持监测费 |  |  | 608 | 608 |  |  |  | 参照水利部保监[2005]22号 | 0.12%
5.3 | 水土保持设施竣工验收技术评估报告编制费 |  |  | 128 | 128 |  |  |  | 参照水利部保监[2005]22号 | 0.02%
6 | 水土保持补偿费 |  |  | 101.9 | 101.9 | 679362.9 | ㎡ |  | 鄂价环资[2017]93号 | 0.02%
7 | 勘察设计费 |  |  | 9268.28 | 9268.28 |  |  |  |  | 1.81%
7.1 | 工程勘察费 |  |  | 2318.54 | 2318.54 |  |  |  | 参照计价格[2002]10号 | 0.45%
7.2 | 工程设计费 |  |  | 6074.94 | 6074.94 |  |  |  | 参照计价格[2002]10号 | 1.18%
7.3 | 施工图预算编制费 |  |  | 486 | 486 |  |  |  | 参照计价格[2002]10号 | 0.09%
7.4 | 竣工图编制费 |  |  | 388.8 | 388.8 |  |  |  |  | 0.08%
8 | 建设工程造价咨询服务费 |  |  | 3348.93 | 3348.93 |  |  |  | 参照鄂价工服规[2012]149号 | 0.65%
8.1 | 工程量清单编制 |  |  | 199.44 | 199.44 |  |  |  | 参照鄂价工服规[2012]149号 | 0.04%
8.2 | 控制价编制 |  |  | 125.88 | 125.88 |  |  |  | 参照鄂价工服规[2012]149号 | 0.02%
8.3 | 施工阶段全过程造价控制 |  |  | 1484.09 | 1484.09 |  |  |  | 参照鄂价工服规[2012]149号 | 0.29%
8.4 | 竣工决算审核 |  |  | 1539.52 | 1539.52 |  |  |  | 参照鄂价工服规[2012]149号 | 0.3%
9 | 场地准备及临时设施费 |  |  | 3622.72 | 3622.72 |  |  |  | 工程费用1% | 0.71%
10 | 工程保险费 |  |  | 1811.36 | 1811.36 |  |  |  | 工程费用0.5% | 0.35%
11 | 招标代理服务费 |  |  | 143.53 | 143.53 |  |  |  | 参照计价格[2002]1980号 | 0.03%
11.1 | 工程招标 |  |  | 101.78 | 101.78 |  |  |  |  | 0.02%
11.2 | 服务招标 |  |  | 41.75 | 41.75 |  |  |  |  | 0.01%
11.2.1 | 设计招标 |  |  | 18.02 | 18.02 |  |  |  |  | 0%
11.2.2 | 勘察招标 |  |  | 10.25 | 10.25 |  |  |  |  | 0%
11.2.3 | 监理招标 |  |  | 13.48 | 13.48 |  |  |  |  | 0%
12 | 环境影响咨询服务费 |  |  | 76.32 | 76.32 |  |  |  |  | 0.01%
13 | 社会稳定性风险评估 |  |  | 121.98 | 121.98 |  |  |  |  | 0.02%
14 | 节能报告评估 |  |  | 40 | 40 |  |  |  |  | 0.01%
15 | 建筑垃圾服务费 |  |  | 8368.19 | 8368.19 |  |  |  |  | 1.63%
16 | 地质灾害危害性评估 |  |  | 40 | 40 |  |  |  |  | 0.01%
17 | 交通影响评价费 |  |  | 50 | 50 |  |  |  |  | 0.01%
18 | 高可靠性供电费 |  |  | 100 | 100 |  |  |  |  | 0.02%
19 | 第三方检测费 |  |  | 2535.91 | 2535.91 |  |  |  |  | 0.49%
三 | 预备费 |  |  |  | 36028.26 |  |  |  | (1+2)×8% | 7.02%
四 | 专项费用 |  |  |  | 2300 |  |  |  |  | 0.45%
1 | 外电报装 |  |  |  | 1000 |  |  |  |  | 0.19%
2 | 外水报装 |  |  |  | 600 |  |  |  |  | 0.12%
3 | 燃气报装 |  |  |  | 700 |  |  |  |  | 0.14%
五 | 建设投资 |  |  |  | 488681.49 |  |  |  | （一+二+三） | 95.23%
六 | 建设期利息及贷款费用 |  |  |  | 22374 |  |  |  |  | 4.36%
1 | 建设期利息 |  |  |  | 20340 |  |  |  |  | 3.96%
2 | 先征费（0.25%） |  |  |  | 678 |  |  |  |  | 0.13%
3 | 承诺费（0.25%） |  |  |  | 1356 |  |  |  |  | 0.26%
七 | 流动资金 |  |  |  | 2118.39 |  |  |  |  | 0.41%
八 | 总投资 |  |  |  | 513173.89 |  |  |  | （四+五+六+七） | 100%

## 1205V2(FSR) (hidden)
附表 1 总投资估算表（单位：万元）
|  | 估算价值(万元) |  |  |  | 技术经济指标
序号 | 工程和费用名称 | 建筑工程 | 设备及安装 | 其他费用 | 合 计 | 室内面积或数 |  | （万 | 备 注 | 比例
|  |  | 工程费 |  |  | 量 |  | 元）
（1+2+3）
1 | 海关业务基础设施 | 45278.13 | 360 | 0 | 45638.13 |  |  |  |  | 8.89%
1.2 | 2#国际货站 | 10593.86 | 90 | 0 | 10683.86 | 19474 | ㎡ | 0.549 |  | 2.08%
1.2.1 | 地基处理 | 97.37 |  |  | 97.37 | 19474 | ㎡ | 0.005 |  | 0.02%
1.2.2 | 基础工程 | 116.84 |  |  | 116.84 | 19474 | ㎡ | 0.006 |  | 0.02%
1.2.3 | 土建工程 | 4868.5 |  |  | 4868.5 | 19474 | ㎡ | 0.25 |  | 0.95%
1.2.4 | 装饰装修工程 | 2921.1 |  |  | 2921.1 | 19474 | ㎡ | 0.15 |  | 0.57%
1.2.5 | 给排水工程 | 292.11 |  |  | 292.11 | 19474 | ㎡ | 0.015 |  | 0.06%
1.2.6 | 暖通工程 | 778.96 |  |  | 778.96 | 19474 | ㎡ | 0.04 |  | 0.15%
1.2.7 | 电气工程 | 1363.18 |  |  | 1363.18 | 19474 | ㎡ | 0.07 |  | 0.27%
1.2.8 | 电梯工程 |  | 90 |  | 90 | 2 | 部 | 45 |  | 0.02%
1.2.9 | 抗震支架 | 116.84 |  |  | 116.84 | 19474 | ㎡ | 0.006 |  | 0.02%
1.2.10 | 标识标牌 | 38.95 |  |  | 38.95 | 19474 | ㎡ | 0.002 |  | 0.01%
1.3 | 3#国际货站 | 10593.86 | 90 | 0 | 10683.86 | 19474 | ㎡ | 0.549 | 2.08%
1.3.1 | 地基处理 | 97.37 |  |  | 97.37 | 19474 | ㎡ | 0.005 |  | 0.02%
1.3.2 | 基础工程 | 116.84 |  |  | 116.84 | 19474 | ㎡ | 0.006 |  | 0.02%
1.3.3 | 土建工程 | 4868.5 |  |  | 4868.5 | 19474 | ㎡ | 0.25 |  | 0.95%
1.3.4 | 装饰装修工程 | 2921.1 |  |  | 2921.1 | 19474 | ㎡ | 0.15 |  | 0.57%
1.3.5 | 给排水工程 | 292.11 |  |  | 292.11 | 19474 | ㎡ | 0.015 |  | 0.06%
1.3.6 | 暖通工程 | 778.96 |  |  | 778.96 | 19474 | ㎡ | 0.04 |  | 0.15%
1.3.7 | 电气工程 | 1363.18 |  |  | 1363.18 | 19474 | ㎡ | 0.07 |  | 0.27%
1.3.8 | 电梯工程 |  | 90 |  | 90 | 2 | 部 | 45 |  | 0.02%
1.3.9 | 抗震支架 | 116.84 |  |  | 116.84 | 19474 | ㎡ | 0.006 |  | 0.02%
1.3.10 | 标识标牌 | 38.95 |  |  | 38.95 | 19474 | ㎡ | 0.002 |  | 0.01%
1.4 | 4#国际快件中心 | 22880.59 | 180 | 0 | 23060.59 | 45398 | ㎡ | 0.508 | 4.49%
1.4.1 | 地基处理 | 226.99 |  |  | 226.99 | 45398 | ㎡ | 0.005 |  | 0.04%
1.4.2 | 基础工程 | 272.39 |  |  | 272.39 | 45398 | ㎡ | 0.006 |  | 0.05%
1.4.3 | 土建工程 | 10441.54 |  |  | 10441.54 | 45398 | ㎡ | 0.23 |  | 2.03%
1.4.4 | 装饰装修工程 | 5901.74 |  |  | 5901.74 | 45398 | ㎡ | 0.13 |  | 1.15%
1.4.5 | 给排水工程 | 680.97 |  |  | 680.97 | 45398 | ㎡ | 0.015 |  | 0.13%
1.4.6 | 暖通工程 | 1815.92 |  |  | 1815.92 | 45398 | ㎡ | 0.04 |  | 0.35%
1.4.7 | 电气工程 | 3177.86 |  |  | 3177.86 | 45398 | ㎡ | 0.07 |  | 0.62%
1.4.8 | 电梯工程 |  | 180 |  | 180 | 4 | 部 | 45 |  | 0.04%
1.4.9 | 抗震支架 | 272.39 |  |  | 272.39 | 45398 | ㎡ | 0.006 |  | 0.05%
1.4.10 | 标识标牌 | 90.8 |  |  | 90.8 | 45398 | ㎡ | 0.002 |  | 0.02%
1.5 | 2#海关卡口 | 481.62 |  |  | 481.62 | 949 | ㎡ | 0.508 | 0.09%
1.5.1 | 地基处理 | 3.32 |  |  | 3.32 | 949 | ㎡ | 0.004 |  | 0%
1.5.2 | 土建工程 | 455.52 |  |  | 455.52 | 949 | ㎡ | 0.48 |  | 0.09%
1.5.3 | 给排水工程 | 2.85 |  |  | 2.85 | 949 | ㎡ | 0.003 |  | 0%
1.5.4 | 暖通工程 | 3.8 |  |  | 3.8 | 949 | ㎡ | 0.004 |  | 0%
1.5.5 | 电气工程 | 8.54 |  |  | 8.54 | 949 | ㎡ | 0.009 |  | 0%
1.5.6 | 抗震支架 | 5.69 |  |  | 5.69 | 949 | ㎡ | 0.006 |  | 0%
1.5.7 | 标识标牌 | 1.9 |  |  | 1.9 | 949 | ㎡ | 0.002 |  | 0%
1.6 | 4#海关卡口 | 264.41 |  |  | 264.41 | 521 | ㎡ | 0.508 | 0.05%
1.6.1 | 地基处理 | 1.82 |  |  | 1.82 | 521 | ㎡ | 0.004 |  | 0%
1.6.2 | 土建工程 | 250.08 |  |  | 250.08 | 521 | ㎡ | 0.48 |  | 0.05%
1.6.3 | 给排水工程 | 1.56 |  |  | 1.56 | 521 | ㎡ | 0.003 |  | 0%
1.6.4 | 暖通工程 | 2.08 |  |  | 2.08 | 521 | ㎡ | 0.004 |  | 0%
1.6.5 | 电气工程 | 4.69 |  |  | 4.69 | 521 | ㎡ | 0.009 |  | 0%
1.6.6 | 抗震支架 | 3.13 |  |  | 3.13 | 521 | ㎡ | 0.006 |  | 0%
1.6.7 | 标识标牌 | 1.04 |  |  | 1.04 | 521 | ㎡ | 0.002 |  | 0%
1.7 | 海关围网 | 463.8 |  |  | 463.8 | 7730 | 延米 | 0.06 | 0.09%
2 | 保税仓储和加工 | 90687.6 | 360 | 0 | 91047.6 |  |  |  |  | 17.74%
2.1 | 8#保税加工中心 | 19377.15 | 180 | 0 | 19557.15 | 39225 | ㎡ | 0.499 | 3.81%
2.1.1 | 地基处理 | 196.13 |  |  | 196.13 | 39225 | ㎡ | 0.005 |  | 0.04%
2.1.2 | 基础工程 | 235.35 |  |  | 235.35 | 39225 | ㎡ | 0.006 |  | 0.05%
2.1.3 | 土建工程 | 9414 |  |  | 9414 | 39225 | ㎡ | 0.24 |  | 1.83%
2.1.4 | 装饰装修工程 | 4707 |  |  | 4707 | 39225 | ㎡ | 0.12 |  | 0.92%
2.1.5 | 给排水工程 | 588.38 |  |  | 588.38 | 39225 | ㎡ | 0.015 |  | 0.11%
2.1.6 | 暖通工程 | 1176.75 |  |  | 1176.75 | 39225 | ㎡ | 0.03 |  | 0.23%
2.1.7 | 电气工程 | 2745.75 |  |  | 2745.75 | 39225 | ㎡ | 0.07 |  | 0.54%
2.1.8 | 电梯工程 |  | 180 |  | 180 | 4 | 部 | 45 |  | 0.04%
2.1.9 | 抗震支架 | 235.35 |  |  | 235.35 | 39225 | ㎡ | 0.006 |  | 0.05%
2.1.10 | 标识标牌 | 78.45 |  |  | 78.45 | 39225 | ㎡ | 0.002 |  | 0.02%
2.2 | 9#保税加工中心 | 11200.76 | 180 | 0 | 11380.76 | 20936 | ㎡ | 0.544 |  | 2.22%
2.2.1 | 地基处理 | 104.68 |  |  | 104.68 | 20936 | ㎡ | 0.005 |  | 0.02%
2.2.2 | 基础工程 | 146.55 |  |  | 146.55 | 20936 | ㎡ | 0.007 |  | 0.03%
2.2.3 | 土建工程 | 5443.36 |  |  | 5443.36 | 20936 | ㎡ | 0.26 |  | 1.06%
2.2.4 | 装饰装修工程 | 2931.04 |  |  | 2931.04 | 20936 | ㎡ | 0.14 |  | 0.57%
2.2.5 | 给排水工程 | 314.04 |  |  | 314.04 | 20936 | ㎡ | 0.015 |  | 0.06%
2.2.6 | 暖通工程 | 628.08 |  |  | 628.08 | 20936 | ㎡ | 0.03 |  | 0.12%
2.2.7 | 电气工程 | 1465.52 |  |  | 1465.52 | 20936 | ㎡ | 0.07 |  | 0.29%
2.2.8 | 电梯工程 |  | 180 |  | 180 | 4 | 部 | 45 |  | 0.04%
2.2.9 | 抗震支架 | 125.62 |  |  | 125.62 | 20936 | ㎡ | 0.006 |  | 0.02%
2.2.10 | 标识标牌 | 41.87 |  |  | 41.87 | 20936 | ㎡ | 0.002 |  | 0.01%
2.3 | 10#危险品库区 | 2722.5 | 0 | 0 | 2722.5 | 4500 | ㎡ | 0.605 | 0.53%
2.3.1 | 地基处理 | 22.5 |  |  | 22.5 | 4500 | ㎡ | 0.005 |  | 0%
2.3.2 | 基础工程 | 31.5 |  |  | 31.5 | 4500 | ㎡ | 0.007 |  | 0.01%
2.3.3 | 土建工程 | 1170 |  |  | 1170 | 4500 | ㎡ | 0.26 |  | 0.23%
2.3.4 | 装饰装修工程 | 810 |  |  | 810 | 4500 | ㎡ | 0.18 |  | 0.16%
2.3.5 | 给排水工程 | 67.5 |  |  | 67.5 | 4500 | ㎡ | 0.015 |  | 0.01%
2.3.6 | 暖通工程 | 225 |  |  | 225 | 4500 | ㎡ | 0.05 |  | 0.04%
2.3.7 | 电气工程 | 360 |  |  | 360 | 4500 | ㎡ | 0.08 |  | 0.07%
2.3.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.3.9 | 抗震支架 | 27 |  |  | 27 | 4500 | ㎡ | 0.006 |  | 0.01%
2.3.10 | 标识标牌 | 9 |  |  | 9 | 4500 | ㎡ | 0.002 |  | 0%
2.4 | 11#保税物流中心 | 9822.7 | 0 | 0 | 9822.7 | 19884 | ㎡ | 0.494 | 1.91%
2.4.1 | 地基处理 | 99.42 |  |  | 99.42 | 19884 | ㎡ | 0.005 |  | 0.02%
2.4.2 | 基础工程 | 119.3 |  |  | 119.3 | 19884 | ㎡ | 0.006 |  | 0.02%
|  | 估算价值(万元) |  |  |  | 技术经济指标
序号 | 工程和费用名称 | 建筑工程 | 设备及安装 | 其他费用 | 合 计 | 室内面积或数 |  | （万 | 备 注 | 比例
|  |  | 工程费 |  |  | 量 |  | 元）
2.4.3 | 土建工程 | 4772.16 |  |  | 4772.16 | 19884 | ㎡ | 0.24 |  | 0.93%
2.4.4 | 装饰装修工程 | 2386.08 |  |  | 2386.08 | 19884 | ㎡ | 0.12 |  | 0.46%
2.4.5 | 给排水工程 | 298.26 |  |  | 298.26 | 19884 | ㎡ | 0.015 |  | 0.06%
2.4.6 | 暖通工程 | 596.52 |  |  | 596.52 | 19884 | ㎡ | 0.03 |  | 0.12%
2.4.7 | 电气工程 | 1391.88 |  |  | 1391.88 | 19884 | ㎡ | 0.07 |  | 0.27%
2.4.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.4.9 | 抗震支架 | 119.3 |  |  | 119.3 | 19884 | ㎡ | 0.006 |  | 0.02%
2.4.10 | 标识标牌 | 39.77 |  |  | 39.77 | 19884 | ㎡ | 0.002 |  | 0.01%
2.5 | 12#保税物流中心 | 9822.7 | 0 | 0 | 9822.7 | 19884 | ㎡ | 0.494 | 1.91%
2.5.1 | 地基处理 | 99.42 |  |  | 99.42 | 19884 | ㎡ | 0.005 |  | 0.02%
2.5.2 | 基础工程 | 119.3 |  |  | 119.3 | 19884 | ㎡ | 0.006 |  | 0.02%
2.5.3 | 土建工程 | 4772.16 |  |  | 4772.16 | 19884 | ㎡ | 0.24 |  | 0.93%
2.5.4 | 装饰装修工程 | 2386.08 |  |  | 2386.08 | 19884 | ㎡ | 0.12 |  | 0.46%
2.5.5 | 给排水工程 | 298.26 |  |  | 298.26 | 19884 | ㎡ | 0.015 |  | 0.06%
2.5.6 | 暖通工程 | 596.52 |  |  | 596.52 | 19884 | ㎡ | 0.03 |  | 0.12%
2.5.7 | 电气工程 | 1391.88 |  |  | 1391.88 | 19884 | ㎡ | 0.07 |  | 0.27%
2.5.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.5.9 | 抗震支架 | 119.3 |  |  | 119.3 | 19884 | ㎡ | 0.006 |  | 0.02%
|  | 估算价值(万元) |  |  |  | 技术经济指标
序号 | 工程和费用名称 | 建筑工程 | 设备及安装 | 其他费用 | 合 计 | 室内面积或数 |  | （万 | 备 注 | 比例
|  |  | 工程费 |  |  | 量 |  | 元）
2.5.10 | 标识标牌 | 39.77 |  |  | 39.77 | 19884 | ㎡ | 0.002 |  | 0.01%
2.6 | 13#保税物流中心 | 6862.1 | 0 | 0 | 6862.1 | 12591 | ㎡ | 0.545 | 1.34%
2.6.1 | 地基处理 | 62.96 |  |  | 62.96 | 12591 | ㎡ | 0.005 |  | 0.01%
2.6.2 | 基础工程 | 88.14 |  |  | 88.14 | 12591 | ㎡ | 0.007 |  | 0.02%
2.6.3 | 土建工程 | 3147.75 |  |  | 3147.75 | 12591 | ㎡ | 0.25 |  | 0.61%
2.6.4 | 装饰装修工程 | 1888.65 |  |  | 1888.65 | 12591 | ㎡ | 0.15 |  | 0.37%
2.6.5 | 给排水工程 | 188.87 |  |  | 188.87 | 12591 | ㎡ | 0.015 |  | 0.04%
2.6.6 | 暖通工程 | 503.64 |  |  | 503.64 | 12591 | ㎡ | 0.04 |  | 0.1%
2.6.7 | 电气工程 | 881.37 |  |  | 881.37 | 12591 | ㎡ | 0.07 |  | 0.17%
2.6.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.6.9 | 抗震支架 | 75.55 |  |  | 75.55 | 12591 | ㎡ | 0.006 |  | 0.01%
2.6.10 | 标识标牌 | 25.18 |  |  | 25.18 | 12591 | ㎡ | 0.002 |  | 0%
2.7 | 14#保税物流中心 | 6862.1 | 0 | 0 | 6862.1 | 12591 | ㎡ | 0.545 | 1.34%
2.7.1 | 地基处理 | 62.96 |  |  | 62.96 | 12591 | ㎡ | 0.005 |  | 0.01%
2.7.2 | 基础工程 | 88.14 |  |  | 88.14 | 12591 | ㎡ | 0.007 |  | 0.02%
2.7.3 | 土建工程 | 3147.75 |  |  | 3147.75 | 12591 | ㎡ | 0.25 |  | 0.61%
2.7.4 | 装饰装修工程 | 1888.65 |  |  | 1888.65 | 12591 | ㎡ | 0.15 |  | 0.37%
2.7.5 | 给排水工程 | 188.87 |  |  | 188.87 | 12591 | ㎡ | 0.015 |  | 0.04%
2.7.6 | 暖通工程 | 503.64 |  |  | 503.64 | 12591 | ㎡ | 0.04 |  | 0.1%
|  | 估算价值(万元) |  |  |  | 技术经济指标
序号 | 工程和费用名称 | 建筑工程 | 设备及安装 | 其他费用 | 合 计 | 室内面积或数 |  | （万 | 备 注 | 比例
|  |  | 工程费 |  |  | 量 |  | 元）
2.7.7 | 电气工程 | 881.37 |  |  | 881.37 | 12591 | ㎡ | 0.07 |  | 0.17%
2.7.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.7.9 | 抗震支架 | 75.55 |  |  | 75.55 | 12591 | ㎡ | 0.006 |  | 0.01%
2.7.10 | 标识标牌 | 25.18 |  |  | 25.18 | 12591 | ㎡ | 0.002 |  | 0%
2.8 | 15#保税物流中心 | 5399.86 | 0 | 0 | 5399.86 | 9908 | ㎡ | 0.545 | 1.05%
2.8.1 | 地基处理 | 49.54 |  |  | 49.54 | 9908 | ㎡ | 0.005 |  | 0.01%
2.8.2 | 基础工程 | 69.36 |  |  | 69.36 | 9908 | ㎡ | 0.007 |  | 0.01%
2.8.3 | 土建工程 | 2477 |  |  | 2477 | 9908 | ㎡ | 0.25 |  | 0.48%
2.8.4 | 装饰装修工程 | 1486.2 |  |  | 1486.2 | 9908 | ㎡ | 0.15 |  | 0.29%
2.8.5 | 给排水工程 | 148.62 |  |  | 148.62 | 9908 | ㎡ | 0.015 |  | 0.03%
2.8.6 | 暖通工程 | 396.32 |  |  | 396.32 | 9908 | ㎡ | 0.04 |  | 0.08%
2.8.7 | 电气工程 | 693.56 |  |  | 693.56 | 9908 | ㎡ | 0.07 |  | 0.14%
2.8.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.8.9 | 抗震支架 | 59.45 |  |  | 59.45 | 9908 | ㎡ | 0.006 |  | 0.01%
2.8.10 | 标识标牌 | 19.82 |  |  | 19.82 | 9908 | ㎡ | 0.002 |  | 0%
2.9 | 16#保税物流中心 | 6205.92 | 0 | 0 | 6205.92 | 11387 | ㎡ | 0.545 | 1.21%
2.9.1 | 地基处理 | 56.94 |  |  | 56.94 | 11387 | ㎡ | 0.005 |  | 0.01%
2.9.2 | 基础工程 | 79.71 |  |  | 79.71 | 11387 | ㎡ | 0.007 |  | 0.02%
2.9.3 | 土建工程 | 2846.75 |  |  | 2846.75 | 11387 | ㎡ | 0.25 |  | 0.55%
|  | 估算价值(万元) |  |  |  | 技术经济指标
序号 | 工程和费用名称 | 建筑工程 | 设备及安装 | 其他费用 | 合 计 | 室内面积或数 |  | （万 | 备 注 | 比例
|  |  | 工程费 |  |  | 量 |  | 元）
2.9.4 | 装饰装修工程 | 1708.05 |  |  | 1708.05 | 11387 | ㎡ | 0.15 |  | 0.33%
2.9.5 | 给排水工程 | 170.81 |  |  | 170.81 | 11387 | ㎡ | 0.015 |  | 0.03%
2.9.6 | 暖通工程 | 455.48 |  |  | 455.48 | 11387 | ㎡ | 0.04 |  | 0.09%
2.9.7 | 电气工程 | 797.09 |  |  | 797.09 | 11387 | ㎡ | 0.07 |  | 0.16%
2.9.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.9.9 | 抗震支架 | 68.32 |  |  | 68.32 | 11387 | ㎡ | 0.006 |  | 0.01%
2.9.10 | 标识标牌 | 22.77 |  |  | 22.77 | 11387 | ㎡ | 0.002 |  | 0%
2.1 | 17#保税物流中心 | 6205.92 | 0 | 0 | 6205.92 | 11387 | ㎡ | 0.545 | 1.21%
2.10.1 | 地基处理 | 56.94 |  |  | 56.94 | 11387 | ㎡ | 0.005 |  | 0.01%
2.10.2 | 基础工程 | 79.71 |  |  | 79.71 | 11387 | ㎡ | 0.007 |  | 0.02%
2.10.3 | 土建工程 | 2846.75 |  |  | 2846.75 | 11387 | ㎡ | 0.25 |  | 0.55%
2.10.4 | 装饰装修工程 | 1708.05 |  |  | 1708.05 | 11387 | ㎡ | 0.15 |  | 0.33%
2.10.5 | 给排水工程 | 170.81 |  |  | 170.81 | 11387 | ㎡ | 0.015 |  | 0.03%
2.10.6 | 暖通工程 | 455.48 |  |  | 455.48 | 11387 | ㎡ | 0.04 |  | 0.09%
2.10.7 | 电气工程 | 797.09 |  |  | 797.09 | 11387 | ㎡ | 0.07 |  | 0.16%
2.10.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.10.9 | 抗震支架 | 68.32 |  |  | 68.32 | 11387 | ㎡ | 0.006 |  | 0.01%
2.10.1 | 标识标牌 | 22.77 |  |  | 22.77 | 11387 | ㎡ | 0.002 |  | 0%
0
|  | 估算价值(万元) |  |  |  | 技术经济指标
序号 | 工程和费用名称 | 建筑工程 | 设备及安装 | 其他费用 | 合 计 | 室内面积或数 |  | （万 | 备 注 | 比例
|  |  | 工程费 |  |  | 量 |  | 元）
2.11 | 18#保税物流中心 | 6205.92 | 0 | 0 | 6205.92 | 11387 | ㎡ | 0.545 | 1.21%
2.11.1 | 地基处理 | 56.94 |  |  | 56.94 | 11387 | ㎡ | 0.005 |  | 0.01%
2.11.2 | 基础工程 | 79.71 |  |  | 79.71 | 11387 | ㎡ | 0.007 |  | 0.02%
2.11.3 | 土建工程 | 2846.75 |  |  | 2846.75 | 11387 | ㎡ | 0.25 |  | 0.55%
2.11.4 | 装饰装修工程 | 1708.05 |  |  | 1708.05 | 11387 | ㎡ | 0.15 |  | 0.33%
2.11.5 | 给排水工程 | 170.81 |  |  | 170.81 | 11387 | ㎡ | 0.015 |  | 0.03%
2.11.6 | 暖通工程 | 455.48 |  |  | 455.48 | 11387 | ㎡ | 0.04 |  | 0.09%
2.11.7 | 电气工程 | 797.09 |  |  | 797.09 | 11387 | ㎡ | 0.07 |  | 0.16%
2.11.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
2.11.9 | 抗震支架 | 68.32 |  |  | 68.32 | 11387 | ㎡ | 0.006 |  | 0.01%
2.11.1 | 标识标牌 | 22.77 |  |  | 22.77 | 11387 | ㎡ | 0.002 |  | 0%
0
3 | 贸易和货运服务设施 | 96421.65 | 810 | 0 | 97231.65 |  |  |  | 18.95
%
3.1 | 19#综合配套中心 | 59191.65 | 360 | 0 | 59551.65 |  | ㎡ |  | 11.6
%
3.1.1 | 地上 | 38311.65 | 360 | 0 | 38671.65 | 57525 | ㎡ | 0.672 | 7.54%
3.1.1.1 | 地基处理 | 287.63 |  |  | 287.63 | 57525 | ㎡ | 0.005 |  | 0.06%
3.1.1.2 | 基础工程 | 8053.5 |  |  | 8053.5 | 57525 | ㎡ | 0.14 |  | 1.57%
3.1.1.3 | 土建工程 | 14381.25 |  |  | 14381.25 | 57525 | ㎡ | 0.25 |  | 2.8%
|  | 估算价值(万元) |  |  |  | 技术经济指标
序号 | 工程和费用名称 | 建筑工程 | 设备及安装 | 其他费用 | 合 计 | 室内面积或数 |  | （万 | 备 注 | 比例
|  |  | 工程费 |  |  | 量 |  | 元）
3.1.1.4 | 装饰装修工程 | 8628.75 |  |  | 8628.75 | 57525 | ㎡ | 0.15 |  | 1.68%
3.1.1.5 | 给排水工程 | 747.83 |  |  | 747.83 | 57525 | ㎡ | 0.013 |  | 0.15%
3.1.1.6 | 暖通工程 | 2301 |  |  | 2301 | 57525 | ㎡ | 0.04 |  | 0.45%
3.1.1.7 | 电气工程 | 3451.5 |  |  | 3451.5 | 57525 | ㎡ | 0.06 |  | 0.67%
3.1.1.8 | 电梯工程 |  | 360 |  | 360 | 8 | 部 | 45 |  | 0.07%
3.1.1.9 | 抗震支架 | 345.15 |  |  | 345.15 | 57525 | ㎡ | 0.006 |  | 0.07%
3.1.1.1 | 标识标牌 | 115.05 |  |  | 115.05 | 57525 | ㎡ | 0.002 |  | 0.02%
0
3.1.2 | 地下 | 20880 | 0 | 0 | 20880 | 30000 | ㎡ | 0.696 | 4.07%
3.1.2.1 | 地基处理 | 150 |  |  | 150 | 30000 | ㎡ | 0.005 |  | 0.03%
3.1.2.2 | 基础工程 | 4200 |  |  | 4200 | 30000 | ㎡ | 0.14 |  | 0.82%
3.1.2.3 | 土建工程 | 7500 |  |  | 7500 | 30000 | ㎡ | 0.25 |  | 1.46%
3.1.2.4 | 装饰装修工程 | 4500 |  |  | 4500 | 30000 | ㎡ | 0.15 |  | 0.88%
3.1.2.5 | 给排水工程 | 390 |  |  | 390 | 30000 | ㎡ | 0.013 |  | 0.08%
3.1.2.6 | 暖通工程 | 1500 |  |  | 1500 | 30000 | ㎡ | 0.05 |  | 0.29%
3.1.2.7 | 电气工程 | 1800 |  |  | 1800 | 30000 | ㎡ | 0.06 |  | 0.35%
3.1.2.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
3.1.2.9 | 人防工程 | 600 |  |  |  | 15000 | ㎡ | 0.04
3.1.2.1 | 抗震支架 | 180 |  |  | 180 | 30000 | ㎡ | 0.006 |  | 0.04%
|  | 估算价值(万元) |  |  |  | 技术经济指标
序号 | 工程和费用名称 | 建筑工程 | 设备及安装 | 其他费用 | 合 计 | 室内面积或数 |  | （万 | 备 注 | 比例
|  |  | 工程费 |  |  | 量 |  | 元）
0
3.1.2.1 | 标识标牌 | 60 |  |  | 60 | 30000 | ㎡ | 0.002 |  | 0.01%
1
3.2 | 20#商贸物流大楼 | 37230 | 450 | 0 | 37680 |  | ㎡ |  | 7.34%
3.2.1 | 地上 | 23310 | 450 | 0 | 23760 | 35000 | ㎡ | 0.679 | 4.63%
3.2.1.1 | 地基处理 | 175 |  |  | 175 | 35000 | ㎡ | 0.005 |  | 0.03%
3.2.1.2 | 基础工程 | 4900 |  |  | 4900 | 35000 | ㎡ | 0.14 |  | 0.95%
3.2.1.3 | 土建工程 | 8750 |  |  | 8750 | 35000 | ㎡ | 0.25 |  | 1.71%
3.2.1.4 | 装饰装修工程 | 5250 |  |  | 5250 | 35000 | ㎡ | 0.15 |  | 1.02%
3.2.1.5 | 给排水工程 | 455 |  |  | 455 | 35000 | ㎡ | 0.013 |  | 0.09%
3.2.1.6 | 暖通工程 | 1400 |  |  | 1400 | 35000 | ㎡ | 0.04 |  | 0.27%
3.2.1.7 | 电气工程 | 2100 |  |  | 2100 | 35000 | ㎡ | 0.06 |  | 0.41%
3.2.1.8 | 电梯工程 |  | 450 |  | 450 | 10 | 部 | 45 |  | 0.09%
3.2.1.9 | 抗震支架 | 210 |  |  | 210 | 35000 | ㎡ | 0.006 |  | 0.04%
3.2.1.1 | 标识标牌 | 70 |  |  | 70 | 35000 | ㎡ | 0.002 |  | 0.01%
0
3.2.2 | 地下 | 13920 | 0 | 0 | 13920 | 20000 | ㎡ | 0.696 | 2.71%
3.2.2.1 | 地基处理 | 100 |  |  | 100 | 20000 | ㎡ | 0.005 |  | 0.02%
3.2.2.2 | 基础工程 | 2800 |  |  | 2800 | 20000 | ㎡ | 0.14 |  | 0.55%
|  | 估算价值(万元) |  |  |  | 技术经济指标
序号 | 工程和费用名称 | 建筑工程 | 设备及安装 | 其他费用 | 合 计 | 室内面积或数 |  | （万 | 备 注 | 比例
|  |  | 工程费 |  |  | 量 |  | 元）
3.2.2.3 | 土建工程 | 5000 |  |  | 5000 | 20000 | ㎡ | 0.25 |  | 0.97%
3.2.2.4 | 装饰装修工程 | 3000 |  |  | 3000 | 20000 | ㎡ | 0.15 |  | 0.58%
3.2.2.5 | 给排水工程 | 260 |  |  | 260 | 20000 | ㎡ | 0.013 |  | 0.05%
3.2.2.6 | 暖通工程 | 1000 |  |  | 1000 | 20000 | ㎡ | 0.05 |  | 0.19%
3.2.2.7 | 电气工程 | 1200 |  |  | 1200 | 20000 | ㎡ | 0.06 |  | 0.23%
3.2.2.8 | 电梯工程 |  | 0 |  | 0 | 0 | 部 | 45 |  | 0%
3.2.2.9 | 人防工程 | 400 |  |  |  | 10000 | ㎡ | 0.04 |  | 0%
3.2.2.1 | 抗震支架 | 120 |  |  | 120 | 20000 | ㎡ | 0.006 |  | 0.02%
0
3.2.2.1 | 标识标牌 | 40 |  |  | 40 | 20000 | ㎡ | 0.002 |  | 0.01%
1
4 | 信息化与相关设备 | 0 | 43141.88 | 0 | 43141.88 |  |  |  | 8.41%
4.1 | 弱电工程 |  | 21102.9 |  | 21102.9 |  |  |  | 4.11%
4.1.2 | 二弱电工程 |  | 21102.9 |  | 21102.9 |  |  |  | 4.11%
4.1.2.1 | 2#国际货站 |  | 6371.89 |  | 6371.89 | 19474 | ㎡ | 0.327 | 1.24%
4.1.2.2 | 3#国际货站 |  | 6371.89 |  | 6371.89 | 19474 | ㎡ | 0.327 | 1.24%
4.1.2.3 | 4#国际快件中心 |  | 1634.33 |  | 1634.33 | 45398 | ㎡ | 0.036 | 0.32%
4.1.2.4 | 2#海关卡口 |  | 13.48 |  | 13.48 | 949 | ㎡ | 0.014 | 0%
4.1.2.5 | 4#海关卡口 |  | 7.4 |  | 7.4 | 521 | ㎡ | 0.014 | 0%
|  | 估算价值(万元) |  |  |  | 技术经济指标
序号 | 工程和费用名称 | 建筑工程 | 设备及安装 | 其他费用 | 合 计 | 室内面积或数 |  | （万 | 备 注 | 比例
|  |  | 工程费 |  |  | 量 |  | 元）
4.1.2.7 | 8#保税加工中心 |  | 176.51 |  | 176.51 | 39225 | ㎡ | 0.005 | 0.03%
4.1.2.8 | 9#保税加工中心 |  | 94.21 |  | 94.21 | 20936 | ㎡ | 0.005 | 0.02%
4.1.2.9 | 10#危险品库区 |  | 20.25 |  | 20.25 | 4500 | ㎡ | 0.005 | 0%
4.1.2.1 | 11#保税物流中心 |  | 89.48 |  | 89.48 | 19884 | ㎡ | 0.005 | 0.02%
0
4.1.2.1 | 12#保税物流中心 |  | 89.48 |  | 89.48 | 19884 | ㎡ | 0.005 | 0.02%
1
4.1.2.1 | 13#保税物流中心 |  | 56.66 |  | 56.66 | 12591 | ㎡ | 0.005 | 0.01%
2
4.1.2.1 | 14#保税物流中心 |  | 56.66 |  | 56.66 | 12591 | ㎡ | 0.005 | 0.01%
3
4.1.2.1 | 15#保税物流中心 |  | 44.59 |  | 44.59 | 9908 | ㎡ | 0.005 | 0.01%
4
4.1.2.1 | 16#保税物流中心 |  | 51.24 |  | 51.24 | 11387 | ㎡ | 0.005 | 0.01%
5
4.1.2.1 | 17#保税物流中心 |  | 51.24 |  | 51.24 | 11387 | ㎡ | 0.005 | 0.01%
6
4.1.2.1 | 18#保税物流中心 |  | 51.24 |  | 51.24 | 11387 | ㎡ | 0.005 | 0.01%
7
4.1.2.1 | 19#综合配套中心 |  | 1050.3 |  | 1050.3 | 87525 | ㎡ | 0.012 | 0.2%
9
4.1.2.2 | 20#商贸物流大楼 |  | 660 |  | 660 | 55000 | ㎡ | 0.012 | 0.13%
|  | 估算价值(万元) |  |  |  | 技术经济指标
序号 | 工程和费用名称 | 建筑工程 | 设备及安装 | 其他费用 | 合 计 | 室内面积或数 |  | （万 | 备 注 | 比例
|  |  | 工程费 |  |  | 量 |  | 元）
0
4.1.2.2 | 室外工程 |  | 4212.05 |  | 4212.05 | 679362.9 | ㎡ | 0.006 | 0.82%
1 | [5 empty] | 0
4.2 | 工艺设备 |  | 22038.98 |  | 22038.98 |  |  |  | 4.29%
5 | 配套设施 | 83757.18 | 0 | 100 | 83857.18 |  |  |  | 16.34
%
5.1 | 1#高架联络桥 | 8800 | 0 | 0 | 8800 | 11000 | ㎡ | 0.8 | 1.71%
5.1.1 | 路基工程 | 1650 |  |  | 1650 | 11000 | ㎡ | 0.15 | 0.32%
5.1.2 | 桥梁工程 | 6600 |  |  | 6600 | 11000 | ㎡ | 0.6 | 1.29%
5.1.2 | 照明工程 | 550 |  |  | 550 | 11000 | ㎡ | 0.05 | 0.11%
5.2 | 2#预留高架联络桥 | 8800 | 0 | 0 | 8800 | 11000 | ㎡ | 0.8 | 1.71%
5.2.2 | 路基工程 | 1650 |  |  | 1650 | 11000 | ㎡ | 0.15 | 0.32%
5.2.3 | 桥梁工程 | 6600 |  |  | 6600 | 11000 | ㎡ | 0.6 | 1.29%
5.2.4 | 照明工程 | 550 |  |  | 550 | 11000 | ㎡ | 0.05 | 0.11%
5.3 | 3#平交联络桥 | 4000 | 0 | 0 | 4000 | 5000 | ㎡ | 0.8 | 0.78%
5.3.1 | 路基工程 | 750 |  |  | 750 | 5000 | ㎡ | 0.15 | 0.15%
5.3.2 | 桥梁工程 | 3000 |  |  | 3000 | 5000 | ㎡ | 0.6 | 0.58%
5.3.3 | 照明工程 | 250 |  |  | 250 | 5000 | ㎡ | 0.05 | 0.05%
5.4 | 4#高架桥 | 3200 | 0 | 0 | 3200 | 4000 | ㎡ | 0.8 | 0.62%
5.4.1 | 路基工程 | 600 |  |  | 600 | 4000 | ㎡ | 0.15 | 0.12%
|  | 估算价值(万元) |  |  |  | 技术经济指标
序号 | 工程和费用名称 | 建筑工程 | 设备及安装 | 其他费用 | 合 计 | 室内面积或数 |  | （万 | 备 注 | 比例
|  |  | 工程费 |  |  | 量 |  | 元）
5.4.2 | 桥梁工程 | 2400 |  |  | 2400 | 4000 | ㎡ | 0.6 | 0.47%
5.4.3 | 照明工程 | 200 |  |  | 200 | 4000 | ㎡ | 0.05 | 0.04%
5.5 | 21#道口 | 750 | 0 | 0 | 750 | 1500 | ㎡ | 0.5 | 0.15%
5.5.1 | 路基工程 | 225 |  |  | 225 | 1500 | ㎡ | 0.15 | 0.04%
5.5.2 | 桥梁工程 | 450 |  |  | 450 | 1500 | ㎡ | 0.3 | 0.09%
5.5.3 | 照明工程 | 75 |  |  | 75 | 1500 | ㎡ | 0.05 | 0.01%
5.6 | 道路、场坪、绿化等 | 58207.18 | 0 | 0 | 58207.18 | 590935.8 | ㎡ | 0.1 | 11.34
[6 empty] | 1 |  |  | %
5.6.1 | 二期 | 58207.18 |  |  | 58207.18 | 590935.8
1
5.6.1.1 | 道路工程 | 16546.2 |  |  | 16546.2 | 118187.1 | ㎡ |  | 3.22%
62
5.6.2.1 | 地基处理 | 2363.74 |  |  | 2363.74 | 118187.1 | ㎡ | 0.02 | 0.46%
0.1 | [5 empty] | 62
5.6.2.1 | 道路工程 | 14182.46 |  |  | 14182.46 | 118187.1 | ㎡ | 0.12 | 2.76%
0.2 | [5 empty] | 62
5.6.2.2 | 场坪工程 | 30137.73 |  |  | 30137.73 | 177280.7 | ㎡ |  | 5.87%
43
5.6.2.2 | 地基处理 | 3545.61 |  |  | 3545.61 | 177280.7 | ㎡ | 0.02 | 0.69%
0.1 | [5 empty] | 43
5.6.2.2 | 场坪工程 | 26592.11 |  |  | 26592.11 | 177280.7 | ㎡ | 0.15 | 5.18%
0.2 | [5 empty] | 43
|  | 估算价值(万元) |  |  |  | 技术经济指标
序号 | 工程和费用名称 | 建筑工程 | 设备及安装 | 其他费用 | 合 计 | 室内面积或数 |  | （万 | 备 注 | 比例
|  |  | 工程费 |  |  | 量 |  | 元）
5.6.2.3 | 绿化工程 | 6204.83 |  |  | 6204.83 | 206827.5 | ㎡ | 0.03 | 1.21%
3
5.6.2.4 | 室外给排水工程 | 2363.74 |  |  | 2363.74 | 590935.8 | ㎡ | 0.004 | 0.46%
1
5.6.2.5 | 室外电气工程 | 2954.68 |  |  | 2954.68 | 590935.8 | ㎡ | 0.005 | 0.58%
1
5.7 | 建筑工人实名制 |  |  | 50 | 50 |  |  |  | 0.01%
5.8 | 智慧工地管理费 |  |  | 50 | 50 |  |  |  | 0.01%
6 | 能力建设 |  |  | 678 | 678 |  |  |  | 0.13%
7 | 专题研究 |  |  | 678 | 678 |  |  |  | 0.13%
二 | 工程建设其他费 |  |  | 88080.8 | 88080.8 |  |  |  | 17.16
%
1 | 土地费用 |  |  | 50951.96 | 50951.96 |  |  |  | 9.93%
2 | 建设单位管理费 |  |  | 2582.37 | 2582.37 |  |  |  | 参照财建[2016]504 号 0.50%
3 | 工程建设监理费 |  |  | 3611.35 | 3611.35 |  |  |  | 参照发改价格
0.7%
[2007]670 号
4 | 建设项目前期咨询费用 |  |  | 290 | 290 |  |  |  | 0.06%
4.1 | 可研报告及资金申请报告编制 |  |  | 290 | 290 |  |  |  | 参照计价格[1999]1283
0.06%
号
5 | 水土保持相关费用 |  |  | 1016 | 1016 |  |  |  | 参照水利部保监
0.2%
[2005]22 号
|  | 估算价值(万元) |  |  |  | 技术经济指标
序号 | 工程和费用名称 | 建筑工程 | 设备及安装 | 其他费用 | 合 计 | 室内面积或数 |  | （万 | 备 注 | 比例
|  |  | 工程费 |  |  | 量 |  | 元）
5.1 | 水土保持方案编制费 |  |  | 280 | 280 |  |  |  | 参照水利部保监
0.05%
[2005]22 号
5.2 | 水土保持监测费 |  |  | 608 | 608 |  |  |  | 参照水利部保监
0.12%
[2005]22 号
5.3 | 水土保持设施竣工验收技术评 |  |  | 128 | 128 |  |  |  | 参照水利部保监
| 估报告编制费 | [7 empty] | 0.02%
[2005]22 号
6 | 水土保持补偿费 |  |  | 101.9 | 101.9 | 679362.9 | ㎡ |  | 鄂价环资[2017]93 号 0.02%
0
7 | 勘察设计费 |  |  | 9268.28 | 9268.28 |  |  |  | 1.81%
7.1 | 工程勘察费 |  |  | 2318.54 | 2318.54 |  |  |  | 参照计价格[2002]10 号 0.45%
7.2 | 工程设计费 |  |  | 6074.94 | 6074.94 |  |  |  | 参照计价格[2002]10 号 1.18%
7.3 | 施工图预算编制费 |  |  | 486 | 486 |  |  |  | 参照计价格[2002]10 号 0.09%
7.4 | 竣工图编制费 |  |  | 388.8 | 388.8 |  |  |  | 0.08%
8 | 建设工程造价咨询服务费 |  |  | 3348.93 | 3348.93 |  |  |  | 参照鄂价工服规
0.65%
[2012]149 号
8.1 | 工程量清单编制 |  |  | 199.44 | 199.44 |  |  |  | 参照鄂价工服规
0.04%
[2012]149 号
8.2 | 控制价编制 |  |  | 125.88 | 125.88 |  |  |  | 参照鄂价工服规
0.02%
[2012]149 号
8.3 | 施工阶段全过程造价控制 |  |  | 1484.09 | 1484.09 |  |  |  | 参照鄂价工服规
0.29%
[2012]149 号
8.4 | 竣工决算审核 |  |  | 1539.52 | 1539.52 |  |  |  | 参照鄂价工服规 0.30%
|  | 估算价值(万元) |  |  |  | 技术经济指标
序号 | 工程和费用名称 | 建筑工程 | 设备及安装 | 其他费用 | 合 计 | 室内面积或数 |  | （万 | 备 注 | 比例
|  |  | 工程费 |  |  | 量 |  | 元）
[2012]149 号
9 | 场地准备及临时设施费 |  |  | 3622.72 | 3622.72 |  |  |  | 工程费用 1% 0.71%
10 | 工程保险费 |  |  | 1811.36 | 1811.36 |  |  |  | 工程费用 0.5% 0.35%
11 | 招标代理服务费 |  |  | 143.53 | 143.53 |  |  |  | 参照计价格[2002]1980
0.03%
号
11.1 | 工程招标 |  |  | 101.78 | 101.78 |  |  |  | 0.02%
11.2 | 服务招标 |  |  | 41.75 | 41.75 |  |  |  | 0.01%
11.2.1 | 设计招标 |  |  | 18.02 | 18.02 |  |  |  | 0%
11.2.2 | 勘察招标 |  |  | 10.25 | 10.25 |  |  |  | 0%
11.2.3 | 监理招标 |  |  | 13.48 | 13.48 |  |  |  | 0%
12 | 环境影响咨询服务费 |  |  | 76.32 | 76.32 |  |  |  | 0.01%
13 | 社会稳定性风险评估 |  |  | 121.98 | 121.98 |  |  |  | 0.02%
14 | 节能报告评估 |  |  | 40 | 40 |  |  |  | 0.01%
15 | 建筑垃圾服务费 |  |  | 8368.19 | 8368.19 |  |  |  | 1.63%
16 | 地质灾害危害性评估 |  |  | 40 | 40 |  |  |  | 0.01%
17 | 交通影响评价费 |  |  | 50 | 50 |  |  |  | 0.01%
18 | 高可靠性供电费 |  |  | 100 | 100 |  |  |  | 0.02%
19 | 第三方检测费 |  |  | 2535.91 | 2535.91 |  |  |  | 0.49%
三 | 预备费 |  |  |  | 36028.26 |  |  |  | (1+2)×8% | 7.02%
四 | 专项费用 |  |  |  | 2300 |  |  |  | 0.45%
1 | 外电报装 |  |  |  | 1000 |  |  |  | 0.19%
|  | 估算价值(万元) |  |  |  | 技术经济指标
序号 | 工程和费用名称 | 建筑工程 | 设备及安装 | 其他费用 | 合 计 | 室内面积或数 |  | （万 | 备 注 | 比例
|  |  | 工程费 |  |  | 量 |  | 元）
2 | 外水报装 |  |  |  | 600 |  |  |  | 0.12%
3 | 燃气报装 |  |  |  | 700 |  |  |  | 0.14%
五 | 建设投资 |  |  |  | 488681.49 |  |  |  | 95.23
（一+二+三）
%
六 | 建设期利息及贷款费用 |  |  |  | 22374 |  |  |  |  | 4.36%
1 | 建设期利息 |  |  |  | 20340 |  |  |  | 3.96%
2 | 先征费（0.25%） |  |  |  | 678 |  |  |  | 0.13%
3 | 承诺费（0.25%） |  |  |  | 1356 |  |  |  | 0.26%
七 | 流动资金 |  |  |  | 2118.39 |  |  |  | 0.41%
八 | 总投资 |  |  |  | 513173.89 |  |  |  | （四+五+六+七） | 100
%

## 20231019可研预算 (hidden)
序号 | 工程和费用名称 | 估算价值(万元) |  |  |  | 技术经济指标 |  |  | 备 注
|  | 建筑工程 | 设备及安装工程费 | 其他费用 | 合 计 | 室内面积或数量 |  | （万元）
一 | 工程费用 | 301279.78 | 65920.71 | 100 | 367300.49 |  |  |  | （1+2+3）
1 | 海关业务基础设施 | 46384.2 | 0 | 0 | 46384.2
1.1 | 2#国际货站 | 10710.7 |  |  | 10710.7 | 19474 | ㎡ | 0.55
1.2 | 3#国际货站 | 10710.7 |  |  | 10710.7 | 19474 | ㎡ | 0.55
1.3 | 4#国际快件中心 | 22699 |  |  | 22699 | 45398 | ㎡ | 0.5
1.4 | 2#海关卡口 | 1200 |  |  | 1200 | 8 | 车道 | 150
1.5 | 4#海关卡口 | 600 |  |  | 600 | 4 | 车道 | 150
1.6 | 海关围网 | 463.8 |  |  | 463.8 | 7730 | 延米 | 0.06
2 | 保税仓储和加工 | 91799.35 | 0 | 0 | 91799.35
2.1 | 8#保税加工中心 | 19612.5 |  |  | 19612.5 | 39225 | ㎡ | 0.5
2.2 | 9#保税加工中心 | 11514.8 |  |  | 11514.8 | 20936 | ㎡ | 0.55
2.3 | 10#危险品库区 | 2700 |  |  | 2700 | 4500 | ㎡ | 0.6
2.4 | 11#保税物流中心 | 9942 |  |  | 9942 | 19884 | ㎡ | 0.5
2.5 | 12#保税物流中心 | 9942 |  |  | 9942 | 19884 | ㎡ | 0.5
2.6 | 13#保税物流中心 | 6925.05 |  |  | 6925.05 | 12591 | ㎡ | 0.55
2.7 | 14#保税物流中心 | 6925.05 |  |  | 6925.05 | 12591 | ㎡ | 0.55
2.8 | 15#保税物流中心 | 5449.4 |  |  | 5449.4 | 9908 | ㎡ | 0.55
2.9 | 16#保税物流中心 | 6262.85 |  |  | 6262.85 | 11387 | ㎡ | 0.55
2.1 | 17#保税物流中心 | 6262.85 |  |  | 6262.85 | 11387 | ㎡ | 0.55
2.11 | 18#保税物流中心 | 6262.85 |  |  | 6262.85 | 11387 | ㎡ | 0.55
3 | 贸易和货运服务设施 | 95141.25 | 0 | 0 | 95141.25
3.1 | 19#综合配套中心 | 58391.25 |  |  | 58391.25 |  | ㎡
3.1.1 | 地上 | 37391.25 |  |  | 37391.25 | 57525 | ㎡ | 0.65
3.1.2 | 地下 | 21000 |  |  | 21000 | 30000 | ㎡ | 0.7
3.2 | 20#商贸物流大楼 | 36750 |  |  | 36750 |  | ㎡
3.2.1 | 地上 | 22750 |  |  | 22750 | 35000 | ㎡ | 0.65
3.2.2 | 地下 | 14000 |  |  | 14000 | 20000 | ㎡ | 0.7
4 | 信息化与相关设备 | 0 | 65920.71 | 0 | 65920.71
4.1 | 海关监管设备及综保区信息化 |  | 20815.71 |  | 20815.71
4.2 | 民航货检设备设施 |  | 25105 |  | 25105
4.3 | 园区弱电智能化及无人驾驶 |  | 20000 |  | 20000
5 | 配套设施 | 67954.98 | 0 | 100 | 68054.98
5.1 | 1#高架桥 | 8800 |  |  | 8800 | 11000 | ㎡ | 0.8
5.2 | 2#高架桥 | 8800 |  |  | 8800 | 11000 | ㎡ | 0.8
5.3 | 3#高架桥 | 4000 |  |  | 4000 | 5000 | ㎡ | 0.8
5.4 | 4#高架桥 | 3200 |  |  | 3200 | 4000 | ㎡ | 0.8
5.5 | 21#道口 | 750 |  |  | 750 | 1500 | ㎡ | 0.5
5.6 | 道路、场坪、绿化等 | 42404.98 |  |  | 42404.98 | 424049.81 | ㎡ | 0.1
5.7 | 建筑工人实名制 |  |  | 50 | 50
5.8 | 智慧工地管理费 |  |  | 50 | 50
二 | 工程建设其他费 |  |  | 61955.37 | 61955.37
1 | 土地费用 |  |  | 31492.52 | 31492.52
2 | 建设单位管理费 |  |  | 2488.97 | 2488.97 |  |  |  | 参照财建[2016]504号
3 | 工程建设监理费 |  |  | 3650.63 | 3650.63 |  |  |  | 参照发改价格[2007]670号
4 | 建设项目前期咨询费用 |  |  | 290 | 290
4.1 | 可研报告及资金申请报告编制 |  |  | 290 | 290 |  |  |  | 参照计价格[1999]1283号
5 | 水土保持相关费用 |  |  | 1016 | 1016 |  |  |  | 参照水利部保监[2005]22号
5.1 | 水土保持方案编制费 |  |  | 280 | 280 |  |  |  | 参照水利部保监[2005]22号
5.2 | 水土保持监测费 |  |  | 608 | 608 |  |  |  | 参照水利部保监[2005]22号
5.3 | 水土保持设施竣工验收技术评估报告编制费 |  |  | 128 | 128 |  |  |  | 参照水利部保监[2005]22号
6 | 水土保持补偿费 |  |  | 140.64 | 140.64 | 937600 | ㎡ |  | 鄂价环资[2017]93号
7 | 勘察设计费 |  |  | 9383.77 | 9383.77
7.1 | 工程勘察费 |  |  | 2350.72 | 2350.72 |  |  |  | 参照计价格[2002]10号
7.2 | 工程设计费 |  |  | 6147.77 | 6147.77 |  |  |  | 参照计价格[2002]10号
7.3 | 施工图预算编制费 |  |  | 491.82 | 491.82 |  |  |  | 参照计价格[2002]10号
7.4 | 竣工图编制费 |  |  | 393.46 | 393.46
8 | 建设工程造价咨询服务费 |  |  | 3302.74 | 3302.74 |  |  |  | 参照鄂价工服规[2012]149号
8.1 | 工程量清单编制 |  |  | 201.95 | 201.95 |  |  |  | 参照鄂价工服规[2012]149号
8.2 | 控制价编制 |  |  | 127.39 | 127.39 |  |  |  | 参照鄂价工服规[2012]149号
8.3 | 施工阶段全过程造价控制 |  |  | 1504.2 | 1504.2 |  |  |  | 参照鄂价工服规[2012]149号
8.4 | 竣工决算审核 |  |  | 1469.19 | 1469.19 |  |  |  | 参照鄂价工服规[2012]149号
9 | 场地准备及临时设施费 |  |  | 3673 | 3673 |  |  |  | 工程费用1%
10 | 工程保险费 |  |  | 1836.5 | 1836.5 |  |  |  | 工程费用0.5%
11 | 招标代理服务费 |  |  | 144.28 | 144.28 |  |  |  | 参照计价格[2002]1980号
11.1 | 工程招标 |  |  | 102.28 | 102.28
11.2 | 服务招标 |  |  | 42 | 42
11.2.1 | 设计招标 |  |  | 18.1 | 18.1
11.2.2 | 勘察招标 |  |  | 10.33 | 10.33
11.2.3 | 监理招标 |  |  | 13.58 | 13.58
12 | 环境影响咨询服务费 |  |  | 73.97 | 73.97
13 | 社会稳定性风险评估 |  |  | 118.46 | 118.46
14 | 节能报告评估 |  |  | 40 | 40
15 | 建筑垃圾服务费 |  |  | 1542.78 | 1542.78
16 | 地质灾害危害性评估 |  |  | 40 | 40
17 | 交通影响评价费 |  |  | 50 | 50
18 | 高可靠性供电费 |  |  | 100 | 100
19 | 第三方检测费 |  |  | 2571.1 | 2571.1
三 | 预备费 |  |  |  | 34340.47 |  |  |  | (1+2)×8%
四 | 专项费用 |  |  |  | 2300
1 | 外电报装 |  |  |  | 1000
2 | 外水报装 |  |  |  | 600
3 | 燃气报装 |  |  |  | 700
五 | 建设投资 |  |  |  | 465896.33 |  |  |  | （一+二+三）
六 | 建设期利息及贷款费用 |  |  |  | 22374
1 | 建设期利息 |  |  |  | 20340
2 | 先征费（0.25%） |  |  |  | 678
3 | 承诺费（0.25%） |  |  |  | 1356
七 | 流动资金 |  |  |  | 1461.28
八 | 总投资 |  |  |  | 489731.62 |  |  |  | （四+五+六+七）
一 | 工程费用 | 367300.49
1 | 海关业务基础设施 | 46384.2 |  | 0.12628 | 7823.9749 | 54208.1749
2 | 保税仓储和加工 | 91799.35 |  | 0.24993 | 15484.4928 | 107283.8428
3 | 贸易和货运服务设施 | 95141.25 |  | 0.25903 | 16048.1964 | 111189.4464
4 | 信息化与相关设备 | 65920.71 |  | 0.17947 | 11119.3462 | 77040.0562
5 | 配套设施 | 68054.98 |  | 0.18528 | 11479.3497 | 79534.3297
|  | 367300.49 |  |  | 61955.36 | 429255.85
|  |  |  | 技术支持服务 | 实施期建设相关费用 |  | 土地
二 | 工程建设其他费 | 61955.37
1 | 土地费用 | 31492.52 |  |  |  |  | 31492.52
2 | 建设单位管理费 | 2488.97 |  |  | 2488.97
3 | 工程建设监理费 | 3650.63 |  | 3650.63
4 | 建设项目前期咨询费用
4.1 | 可研报告及资金申请报告编制 | 290 | 290 | 290
5 | 水土保持相关费用 | 1016
5.1 | 水土保持方案编制费 |  | 280 | 280
5.2 | 水土保持监测费 |  |  |  | 608
5.3 | 水土保持设施竣工验收技术评估报告编制费 |  | 128 | 128
6 | 水土保持补偿费 | 140.64 |  |  | 140.64
7 | 勘察设计费 | 9383.77
7.1 | 工程勘察费 |  | 2350.72 | 2350.72
7.2 | 工程设计费 |  | 6147.77 | 6147.77
7.3 | 施工图预算编制费 |  | 491.82 | 491.82
7.4 | 竣工图编制费 |  | 393.46 | 393.46
8 | 建设工程造价咨询服务费 | 3302.74
8.1 | 工程量清单编制 |  | 201.95 | 201.95
8.2 | 控制价编制 |  | 127.39 | 127.39
8.3 | 施工阶段全过程造价控制 |  | 1504.2 | 1504.2
8.4 | 竣工决算审核 |  | 1469.19 | 1469.19
9 | 场地准备及临时设施费 | 3673 |  |  | 3673
10 | 工程保险费 | 1836.5 |  |  | 1836.5
11 | 招标代理服务费 | 144.28 |  | 144.28
11.1 | 工程招标 |  | 102.28
11.2 | 服务招标 |  | 42
11.2.1 | 设计招标
11.2.2 | 勘察招标
11.2.3 | 监理招标
12 | 环境影响咨询服务费 | 73.97 |  | 73.97
13 | 社会稳定性风险评估 | 118.46 |  | 118.46
14 | 节能报告评估 | 40 |  | 40
15 | 建筑垃圾服务费 | 1542.78 |  |  | 1542.78
16 | 地质灾害危害性评估 | 40 |  | 40
17 | 交通影响评价费 | 50 |  | 50
18 | 高可靠性供电费 | 100 |  |  | 100
19 | 第三方检测费 | 2571.1 |  |  | 2571.1
20 | 项目管理与能力建设
四 | 专项费用 | 2300
1 | 外电报装 | [5 empty] | 1500
2 | 外水报装 | [5 empty] | 600
3 | 燃气报装 | [5 empty] | 700
|  | 61955.36 |  | 17501.84 | 12960.99 |  | 31492.52 |  | 61955.35
五 | 建设投资 | 465896.33
六 | 建设期利息及贷款费用 | 22374
1 | 建设期利息 | 20340
2 | 先征费（0.25%） | 678
3 | 承诺费（0.25%） | 1356
七 | 流动资金 | 1461.28
八 | 总投资 | 489731.62

## 投融资计划 (hidden)
总计
项目 | 人民币(万元) | 美元(万元)
A. 基本费用
1. 海关业务基础设施 | 54208.1749 | 7613.5077
2. 保税仓储和加工 | 107283.8428 | 15067.9554
3. 贸易和货运服务设施 | 111189.4464 | 15616.4953
4. 信息化与相关设备 | 77040.0562 | 10820.2326
5. 配套基础设施 | 79534.3297 | 11170.5519
6. 项目与能力建设咨询服务 | 2000 | 280.8989
合计 (A) | 431255.85 | 60569.6419
B. 不可预见费 | 34500.468 | 4845.5713
C. 实施期财务费用 | 22374 | 3142.4157
总计 (A+B+C) | 488130.318 | 68557.6289
金额
资金来源 | 人民币 (万元) | 美元 (万元) | %
亚投行贷款 | 284800 | 40000 | 58.35%
配套资金 | 203330.318 | 28557.6289 | 41.65%
总计 | 488130.318 | 68557.6289 | 100%