## IIIA-Goods-upto 19.04.24 (hidden)
Project Name: Mumbai Urban Transport Project IIIA-Station Improvement
Procurement Plan: Goods
|  | Project Implementation Entity: Mumbai Railway Vikas Corporation Ltd., Mumbai, India | [12 empty] | Revision No: 16 |  | Revision Date: | 21.03.24 |  |  |  | Approval Date: .......
[23 empty] | Evaluation Criteria (Rated Criteria/ Lowest evaluated Cost) | DATES WITH LINKS TO DOCUMENTS
Specific Procurement Arrangements | [12 empty] | Scheduled Dates |  | Contract Award Details | [5 empty] | Contract Implementation Status | Remarks/Status of Work |  | Draft Tender Documents / Specific Procurement Notice | Amendments to Tender Documents / Pre-Tender Meeting | Tender Submission / Opening of Technical Tenders/ Minutes | Tender Validity Extension | Technical Tender Evaluation Report | Opening of Financial Tender / Minutes | Financial Tender Evaluation / Combined Evaluation Report & Recommendation of Award | Standstill Period | Contract Award | Contract Commencement | Contract Amendments | Contract Completion | Contract Termination
Serial No. | HOD incharge | Contract No. | Description of Contract | Cost Estimate in Local Currency (In INR crore) | Cost Estimate in USD (In million) | Funding* Source by AIIB (%) | Funding* Source by Others (%) | Procurement Category | Procurement Method | Review by Bank (Prior or Post) | Pre-qualification (Yes/No) | Advance Contracting (Yes/No) | Tender Invitation (MM/YY) | Contract Signing (MM/YY) | Contract Price in Local Currency (In INR crore) | Contract Price Equivalence in USD (In million) | Contractor’s Name | Origin of Country | Contract Signing Date | Contract Period (Months)
Goods
Station Improvement (Component A)
1 | GM-Elec. | MRVC/G/201 | LOT- I ,PROCUREMENT OF ESCALATORS (Design, Manufacturing, Supply, Multiple loading/ unloading, Installation, Testing, Commissioning and maintenance during warranty period) at Mira Road and Kandivali of Western Railway and Neral and Kasara of Central Railway. | 11.11 | 1.3887 | 80 | 20 | 2.5 | NOCT | Post | Yes | Yes | 3/23 | 10/23 | 11.63 | 1.6614 | M/s Johnson Pvt Ltd, Chennai | India | 06.10.2023 | 18 Months | Under implementation | Work in progress
| GM-Elec. |  | LOT- II ,PROCUREMENT OF ELEVATORS (Design, Manufacturing, Supply, Multiple loading/ unloading, Installation, Testing, Commissioning and maintenance during warranty period) at Mira Road and Kandivali of Western Railway and Neral and Kasara of Central Railway. | 2.39 | 0.29875 | 80 | 20 |  | NOCT | Post | Yes | Yes | 3/23 | 11/23 | 2.49 | 0.35571 | M/s Omega Ahemedabad | India | 06.11.2023 | 18 Months | Under implementation | Work in progress Material for 01 Elevator at Mira Road received, Installation and commissioning work in progress.
2 | GM-Elec. | MRVC/G/202 | LOT- I-Procurement of Escalators - Supply, Installation, Testing, Commissioning of Escalators at BNDP, MLND, VK, GC, DI, GTBN, CMBR, GV, MNKRD, of CR and Santacruz, NSP, BSR, BHY of WR under Station Improvement work | 42.9 | 5.3625 | 80 | 20 |  | IOCT | Prior | Yes | Yes | 05/24 | 09/24 | [7 empty] | Tender will be invited with the progress of civil works contract
| GM-Elec. |  | LOT- II-Procurement of Elevators - Supply, Installation, Testing, Commissioning of Elevators at BNDP, MLND, VK, GC, DI, GTBN, CMBR, GV, MNKRD, of CR and Santacruz, NSP, BSR, BHY of WR under Station Improvement work | 6.79 | 0.84875 | 80 | 20 |  | IOCT | Prior | Yes | Yes | 05/24 | 09/24
3
4
5
|  |  | Sub Total | 63.19 | 7.8987 | [9 empty] | 14.12 | 2.0171
CBTC
7
8
|  |  | Sub Total | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
|  |  | Total of Goods and Plants | 63.19 | 7.8987 | [9 empty] | 14.12 | 2.0171
Notes: 1) *80% of total value (including taxes) will be funded by the bank for Works, Goods, consulting and non-consulting services under Component A (Stn. Imp) and 100% (including taxes) for Goods, consulting and non-consulting services under Component B (TA Studies)
Notes: 2) Exchange rate (USD 1: INR 80)

## Sheet4 (hidden)
Project Name: Mumbai Urban Transport Project IIIA-Station Improvement | [22 empty] | Completed
Procurement Plan: Consultancies | [22 empty] | Counterpart Funding
|  | Project Implementation Entity: Mumbai Railway Vikas Corporation Ltd., Mumbai, India | [12 empty] | Revision No: 16 |  | Revision Date: | 21.03.24 |  |  |  | Approval Date: .......
Specific Procurement Arrangements | [12 empty] | Scheduled Dates |  | Contract Award Details | [5 empty] | Contract Implementation Status | Remarks | Type of Consultant (Firm/ Individual) | Particular selection method (QCBS/ FBS/ QBS/ LCS/ CQS) | Contract Type (Time Based/ Lump sum) | DATES WITH LINKS TO DOCUMENTS
Serial No. | HOD incharge | Package/ Contract No. | Description of Contract | Cost Estimate in local currency (INR in crore) | Cost Estimate in USD million | Funding* Source by AIIB (%) | Funding* Source by Others (%) | Procurement Category | Procurement Method | Review by Bank (Prior or Post) | Pre-qualification (Yes/No) | Advance Contracting (Yes/No) | Tender Invitation (MM/YY) | Contract Signing (MM/YY) | Contract Price in Local Currency | Contract Price Equivalence in USD | Contractor’s Name | Origin of Country | Contract Signing Date | Contract Period (Months) | [5 empty] | Terms of Reference / Request for Expressions of Interest | Extension to Expressions of Interest Submission | Shortlist Evaluation Report & Shortlisted Consultants | Draft Request for Proposals | Amendment to Request for Proposals | Technical Proposal Opening Minutes | Proposal Validity Extension | Technical Evaluation Report | Contract Negotiations and Draft Final Contract | Standstill Period | Contract Award | Contract Commencement | Contract Amendments | Contract Completion | Contract Termination
(A) | Station Improvement (Component A) i.e. Consultancy Services chargeable to Project
1 | GM-P | MRVC/Cons/223 | Station Improvement-Consultancy for Detail Designing Engineering including Structural & Architectural design of Station Improvement | 8 | 1 | 80 | 20 | Consultancy | QCBS | Post |  | Yes | 2024-01-21 | 2024-11-21 | 9.1 | 1.3 | M/s. Ayesa Ingenieria y Arquitectura S.A.U -UP(India) in JV with M/s. Amiand Consulting Pvt. Ltd. Vakola, Santacruz East - Mumbai | India | 2022-01-29 | Part A 12 Months, Part B 36 Months after part A. | Under Implementation | Work in progress.
2 | GM/C-II & CSTE | (MRVC/Cons/224) | ESIA for CBTC and Station Improvements | 1 | 0.14 | 0 | 100 | Consultancy | Limited tender | NA |  |  | 04/20 | 10/20 | 1.16 | 0.17 | RITES Gurgaon | India | 2020-10-01 | 6 | Under Implementation. | Not Eligible for Bank's funding. Funded from counterpart funds. ESIA & RAP report for SI uploaded on MRVC website on 09/Feb/22 and link shared with AIIB. Revised report, approved by AIIB uploaded in Aug, 2023. Draft ESIA report for CBTC received from consultant and is under scrutiny.
3 | GM-P | MRVC/Cons/OHS/225 | Occupational Health and Safety (OHS) audit and monitoring implementation of OHS plan at worksites of various projects on Central and Western Railway in MMR area of Mumbai by MRVC as per Term of Reference | 1.89 | 0.24 | 80 | 20 | Consultancy | QCBS | Post | Yes | Yes | 08/23 | 12/23 | 3.88 | 0.49 | M/s. URS Scott Wilson India Pvt. Ltd. in JV with AECOM India Pvt. Ltd | India |  | 36 |  | LoA issued on 26.12.2023.Acceptance of firm against LoA, received on 10.02.2024. Contract not yet signed.
|  |  | Sub Total of Consultancy (A) | 9.89 | 1.24 | [9 empty] | 12.98 | 1.79
(B) | TA Studies (Component B) Other Studies / Institutional strengthening Consultancies
1 | GM/C-II | MRVC/TA/131 | TA study for Improving Universal Access for PWDs (Persons with Disability) | 3.6 | 0.45 | 100 | 0 | Consultancy | Direct Selection | Post | No | Yes | 10/21 | 12/12 | 3.6 | 0.51 | Indian Institute of Technology (IIT), Roorkee | India | 2022-12-12 | 12 | Under Implementation | LOA issued to IIT Roorkee on dated 12.12.2022. Inception Report submitted by IIT. on 24.03.2023. Accessiblility Improvement Drawings for Mira Road submiited. work in progress. Extension upto June, 2024 under process.
2 | FA&CAO | MRVC/TA/201 | Technical assistance study under MUTP 3A for examining costing of Mumbai suburban rail services with the purpose of improving processes involved therein and assessing the overall viability of suburban railway operations in Mumbai. | 5 | 0.625 | 100 | 0 | Consultancy | Direct Selection | Post | [11 empty] | AIIB hasapproved direct selection of IIT/Bombay on 16.03.2024.
3 | COM/GM-El |  | Technical Assistance Study for Network Expansion and Other improvement works/projects needed for Mumbai suburban services to improve quality of service, capacity augmentation, safety and comfort to the commuters using suburban services and making detailed proposals for MUTP Phase-IV based on the study recommendations | 6 | 0.75 | 100 | 0 | Consultancy | NOCT | Post | [11 empty] | Under process in MRVC. TOR under preparation.
4 | GM/RS |  | Study of existing station lighting system and suggest smart lighting solutions by simulating the lighting profile using latest software techniques as per international standards along with utilization of energy conservation measures such as natural light including green energy solutions like Solar power etc | [18 empty] | TOR to be prepared & rough cost assessed
5 | GM/RS |  | Feasibility Study of existing 110kV Transmission lines in North-Eastern and South-Eastern sections of Central Railway for monetization by exploring various possible options and suggesting the best solution in the interest of Indian Railways | [18 empty] | TOR to be prepared & rough cost assessed
6 | COM/GM-El |  | Operation research on requirement of stabling sidings on WR for operational needs of present and future suburban corridors. | [18 empty] | TOR to be prepared and shared with Division for approval. Letter sent to PCOM/WR on 21.03.2024
7 | COM/GM-El |  | Feasibility study of automation of train operation by making most suitable changes in the train running schedule during the period of disruption in train operations in Mumbai suburban system utilizing online monitoring tools and innovative AI technologies. | [18 empty] | To be further discussed with Division by COM regarding its requirement and obtain TOR from Division. Letter sent to PCOM/WR on 21.03.2024.
|  |  | Sub Total of TA Studies (B) | 14.6 | 1.825 | [9 empty] | 3.6 | 0.51
|  |  | Gand Total of Consultancies/TA Studies (A+B) | 24.49 | 3.065 | [9 empty] | 16.58 | 2.3
Notes: 1) *80% of total value (including taxes) will be funded by the bank for Works, Goods, consulting and non-consulting services under Component A (Stn. Imp) and 100% (including taxes) for Goods, consulting and non-consulting services under Component B (TA Studies)
Notes: 2) Exchange rate (USD 1: INR 80)

## IIIA-Works
Project Name: Mumbai Urban Transport Project IIIA-Station Improvement
Procurement Plan: Works
| Project Implementation Entity: Mumbai Railway Vikas Corporation Ltd., Mumbai, India | [12 empty] | Revision No: 05 |  | Revision Date: | 07.04.2025
Specific Procurement Arrangements | [11 empty] | Scheduled Dates |  | Contract Award Details | [5 empty] | Contract Implementation Status | Remarks/Status of Work
Serial No. | Package/Contract No. | Description of Contract | Cost Estimate in local currency (INR in crore) | Cost Estimate in USD million | Funding* Source by AIIB in USD (Millions) (including taxes) | Funding* Source by Others in USD MIllions (including taxes) | Procurement Category | Procurement Method | Review by Bank (Prior or Post) | Pre-qualification (Yes/No) | Advance Contracting (Yes/No) | Tender Invitation (MM/YY) | Contract Signing (MM/YY) | Contract Price in INR Local Currency (IC GST) | Contract Price Equivalence in USD | Contractor’s Name | Origin of Country | Contract Signing Date | Contract Period (Months)
I |  | Works
Station Improvement (Component A)
| (i) | Civil Works
1 | MRVC/W/201 | Lot III: Station Improvements works for Neral, Kasara (Civil and S&T) | 112.11 | 14.01 | 80 | 20 | Works | IOCT | Prior | No | Yes | 01/22 | 08/22 | 129 | 16.12 | M/s. Miral Infrastructure | India | 10/22 | 36 | Under implementation | Application for variation sent to AIIB for NOC on 05.04.2025
|  | Lot VI: Station Improvements works for Kandivali, Mira Road (Civil & S&T works) | 123.57 | 15.44 | [5 empty] | No | Yes | 01/22 | 08/22 | 148.19 | 18.5237 | M/s. Sai Projects (Mumbai) Pvt. Ltd. | India | 10/22 | 36 | Under implementation | Work is in progress.
|  | Lot I: Station Improvements works for Ghatkopar, Bhandup (Civil works) | 128.7852 | 16.1 | [7 empty] | 04/23 | 09/23 | [5 empty] | 36 |  | Out of 7 lots , two lots (LoT No. III and Lot No. VI) awarded. Balance lots were retendered. Considering poor response for composite works, separate tenders were invited for civil works, Electrical works and S&T works for balance lots. BOQ & tender Documents approved & NOC received from AIIB. Dates given for LOT I, II, IV, V & VII are subject to availability of funds. As contract for LOT I ,II, IV, V & VII could not be decided, bid has been restructured as new packages for CR- MRVC/W/209/Lot I to Lot III and WR- MRVC/W/210/Lot I & Lot II
|  | Lot II: Station Improvements work for Mulund, Dombivali (Civil works) | 128.5256 | 16.07 | [14 empty] | 36
|  | Lot IV: Station Improvements works for GTB Nagar, Chembur, Govandi, Mankhurd | 133.4934 | 16.7 | [7 empty] | 04/23 | 09/23
|  | Lot V: Station Improvements works for Mumbai Central, Santacruz | 76.4404 | 9.56
|  | Lot VII: Station Improvements works for Bhayander, Vasai Road, Nallasopara | 141.3994 | 17.68 | [7 empty] | 04/23 | 09/23 | [5 empty] | 36
2 | MRVC/W/209 | Lot I: Station Improvements works for Ghatkopar, Bhandup (Civil works) | 141.482 | 17.6852 | 80 | 20 | Works | IOCT | Prior | No | Yes | 2023-05-23 | 2023-10-23 | 155.32 | 19.415 | M/s. Sai Projects (Mumbai) Pvt. Ltd | India | 23.02.2024 | 36 | Under implementation | Work is in progress.
|  | Lot II: Station Improvements work for Mulund, Dombivali (Civil works) | 128.53 | 16.0663 | [5 empty] | No | Yes | 2023-05-23 | 2023-10-23 | 143.34 | 17.9175 | M/s Sai Projects - Sai Dutt (JV) | India | 24.04.2024 | 36 |  | Work is in progress.
|  | Lot III: Station Improvements works for GTB Nagar, Chembur, Govandi, Mankhurd (Civil works) | 133.5 | 16.6875 | [5 empty] | No | Yes | 2023-05-23 | 2023-10-23 | 149.26 | 18.6575 | M/s Kailashchandra Dilipkumar Construction Pvt. Ltd. | India | 23/02/2024 | 36 | Under implementation | Work is in progress.
3 | MRVC/W/210 | Lot I: Station Improvements works for Santacruz & Bhayandar (Civil works) | 137.706 | 17.2132 | 80 | 20 | Works | NOCT | Prior | No | Yes | 2023-06-07 | 2023-10-23 | 148.52 | 18.565 | M/s. Sai Projects (Mumbai) Pvt. Ltd | India | 29.04.2024 | 36 | Under implementation | Work is in progress.
|  | Lot II: Station Improvements works for Vasai Road & Nallasopara (Civil works) | 93.6212 | 11.7027 | [5 empty] | No | Yes | 2023-06-08 | 2023-10-23 | 102.33 | 12.7912 | M/s Sai Dutt - Sai Projects (JV) | India |  | 36 | Under implementation | Work is in progress.
|  | Sub Total I | 870.5192 | 108.8049 | [9 empty] | 975.96 | 121.99
| (ii) | Electrical General Service Works
4 | MRVC/W/202-R2 | Lot I: General Electrification Works related to Station Improvement works at Ghatkopar, Bhandup,stations of Central Railway. | 10.59 | 1.3237 | 80 | 20 | Works | NOCT | Post | No | Yes | 2024-09-24 |  | 12.1531 | 1.5191 | M/s Daanish Electricals and Sales Pvt Ltd., | India |  | 30 | Under implementation | LOA issued to all the firms on 22.02.2025.
|  | Lot II: General Electrification Works related to Station Improvement works at Mulund, Dombivali stations of Central Railway. | 11.25 | 1.4062 | [9 empty] | 13.3798 | 1.6725 | M/s Pronet Technologies Pvt LTd. | India
|  | Lot IV: General Electrification Works related to Station Improvement works at GTB Nagar, Chembur, Govandi and Mankhurd stations of Central Railway. | 14.76 | 1.845 | [9 empty] | 16.7446 | 2.0931 | M/s Sagar Sai Enterprises JV with M/s Jagdish Engineering services | India
5 | MRVC/W/202 | Lot III: General Electrification Works related to Station Improvement works at Neral, Kasara, stations of Central Railway. | 7.36 | 0.92 | 80 | 20 | Works | NOCT | POST | NO | YES | 11/22 | 2024-05-23 | 6.71 | 0.83875 | M/s. Jagdish Engineering Service | India | 04.05.2023 | 36 | Under implementation | work is under progress
6 | MRVC/W/202(GS) | General Electrification Works related to Station Improvement works at Kandivali, Mira Road, stations of Western Railway. | 9.36 | 1.17 | 80 | 20 | Works | NOCT | Post | No | Yes | 11/22 | 03/23 | 8.98 | 1.1225 | M/s Sankalp Industial services, Palghar | India | 29.03.23 | 36 | Under implementation | MIRA & KILE stations work in progress.65% work completed
7 | MRVC/EL/STN. Imp) | RFB-MRVC/EL/STN. Imp)/Sifting of Esalator at Kandivali , Mira Road & Virar Stn. | 0.74 | 0.0925 | 80 | 20 | Works | NOCT | Post | No | Yes | 2023-01-23 | 2024-06-23 | 0.74 | 0.0925 | M/s. Johnson IndiaPvt. Ltd. | India | 13.06.2023 | 12 Extended upto 31.08.2025 | Under implementation | Work in progress. One Escalator Shifted from MIRA & Commissioned at MM Second Escalators shifted from South End to Middle FOB of PF No 1 of MIRA. 01 Esc of VR dismantled and shifted to BSR. For Bal 01 esc of NSP is planned to be shifted in April-2025.
8 | MRVC/W/202 | RFB-MRVC/W/202(GS)/Lot-II Station improvement: General Electrification Works related to Station Improvement works at , Santacruz, Bhayandar, Vasai Road and Nallasopara stations of Western Railway | 15.07 | 1.8838 | 80 | 20 | Works | NOCT | post | NO | Yes | 2023-10-23 | 2023-12-23 | 11.29 | 1.4112 | M/s. Daanish Electricals | India | 28.03.2024 | 36 | Under implementation | Work in progress at Bhayender, Vasai Road and Nalasopara.10% work completed.
|  | Sub Total II | 69.13 | 8.6412 | [9 empty] | 69.9975 | 8.7497
| (iii) | Electrical OHE Works
9 | MRVC/W/204/CR | Lot-I: OHE Works related to Station Improvement works at Bhandup,Ghatkopar stations of Central Railway. | 10.56 | 1.32 | 80 | 20 | Works | NOCT | Post | No | Yes | 05/23 | 08/23 | 11.1 | 1.3875 | M/. Umesh & Bros Const. | India | 19.12.2023 | 36 | Under implementation | Work is in under progress.
Lot-II: OHE Works related to Station Improvement works at Mulund, Dombivali, stations of Central Railway.
Lot-IV: OHE Works related to Station Improvement works at GTB Nagar, Chembur, Govandi and Mankhurd stations of Central Railway.
10 | MRVC/W/204 | Lot-III-OHE Works related to Station Improvement works at Neral, Kasara, stations of Central Railway. | 2.05 | 0.25625 | 80 | 20 | Works | NOCT | Post | NO | YES | 01/23 | 05/23 | 1.99 | 0.24875 | M/s. Texmaco Rail & Engineering | India | 19.07.2023 | 24 | Under implementation | Work is in under progress.
11 | MRVC/W/203 | MRVC/W/203/Lot-II (OHE) (Lot-I AT MIRA & KILE) : OHE Works related to Station Improvement works at Kandivali, Mira Road, of Western Railway. | 4.3 | 0.5375 | 80 | 20 | Works | NOCT | Post | No | Yes | 2022-10-22 | 2023-01-23 | 4.26 | 0.5325 | M/S Saroj Engineering Virar(W) | India | 31.03.23 | 36 | Under implementation | Work in progress.
12 | MRVC/W/206 | MRVC/W/206/Lot-II (OHE) (Lot-II ) : OHE Works related to Station Improvement works at Santacruz, Bhayandar, Vasai Road and Nallasopara stations of Western Railway | 8.7 | 1.0875 | 80 | 20 | Works | NOCT | Post | no | yes | 2023-10-23 | 2023-12-23 | 6.23 | 0.77875 | M/s. Texmaco Rail & Engineering | India | 21.03.2024 | 36 | Under implementation | Work in progress.
|  | Sub Total III | 25.61 | 3.2012 | [9 empty] | 23.58 | 2.9475
| (iv) | Signalling & Telecom Works
13 | MRVC/W/211 | Signalling & Telecom Works related to Station Improvement works at Ghatkopar, Bhandup, Mulund, Dombivali, GTB Nagar, Chembur, Govandi and Mankhurd stations of Central Railway. | 32.46 | 4.06 | 80 | 20 | Works | NOCT | Post | No | No | 2024-02-16 | 2024-05-24 | 8.97 | 1.1213 | M/s Teletech Services | India | 09.09.2024 | 36 | Under implementation | Work in progress.
14 | MRVC/W/208 | Balance Signalling & Telecom Works related to Station Improvement works at Santacruz, Bhayandar, Vasai Road and Nallasopara stations of Western Railway. | 23.71 | 2.96 | 80 | 20 | Works | NOCT | Post | No | No | 2024-12-24 | 2025-03-01 | [5 empty] | 24 |  | Technical design are under preparation.Mumbai central work has been dropped as the similar work has been assigned to RLDA.
|  | Total Signal & Telecom Works | 56.17 | 7.02 | [9 empty] | 8.97 | 1.1213
|  | Total of Station Improvement | 1021.4292 | 127.6674 | [9 empty] | 1078.5075 | 134.8084
II | B | Augmentation of Carrying Capacity and Safety enhancement using Communication Based Train Control (CBTC)
2 |  | Augmentation of Carrying Capacity and Safety enhancement using Communication Based Train Control (CBTC) CBTC on (i) CSMT - Panvel harbour Line (ii) CSMT -Kalyan on Central Railway (iii) CCG-VR on Western Railway | 4500 | 642.86 | 80 | 20 | Work | IOCT | Prior | [9 empty] | 72 |  | Ministry of Railway (MoR) has taken this project for indigenous development under its innovation policy. Further action will as per the advise from MoR.
0 |  | Sub Total II | 4500 | 642.86 | [9 empty] | 0 | 0
|  | Total of Works (I+II) | 5521.4292 | 770.5274 |  |  |  | ` | [5 empty] | 1078.5075 | 134.8084
Notes: 1) *80% of total value (including taxes) will be funded by the bank for Works, Goods, consulting and non-consulting services under Component A (Stn. Imp) and 100% (including taxes) for Goods, consulting and non-consulting services under Component B (TA Studies)
Notes: 2) Exchange rate (USD 1: INR 80)

## IIIA-Goods
Project Name: Mumbai Urban Transport Project IIIA-Station Improvement
Procurement Plan: Goods
| Project Implementation Entity: Mumbai Railway Vikas Corporation Ltd., Mumbai, India | [12 empty] | Revision No: 05 |  | Revision Date: | 07.04.2025
[22 empty] | Evaluation Criteria (Rated Criteria/ Lowest evaluated Cost) | DATES WITH LINKS TO DOCUMENTS
Specific Procurement Arrangements | [11 empty] | Scheduled Dates |  | Contract Award Details | [5 empty] | Contract Implementation Status | Remarks/Status of Work |  | Draft Tender Documents / Specific Procurement Notice | Amendments to Tender Documents / Pre-Tender Meeting | Tender Submission / Opening of Technical Tenders/ Minutes | Tender Validity Extension | Technical Tender Evaluation Report | Opening of Financial Tender / Minutes | Financial Tender Evaluation / Combined Evaluation Report & Recommendation of Award | Standstill Period | Contract Award | Contract Commencement | Contract Amendments | Contract Completion | Contract Termination
Serial No. | Contract No. | Description of Contract | Cost Estimate in Local Currency (In INR crore) | Cost Estimate in USD (In million) | Funding* Source by AIIB in USD (Millions) (including taxes) | Funding* Source by Others in USD MIllions (including taxes) | Procurement Category | Procurement Method | Review by Bank (Prior or Post) | Pre-qualification (Yes/No) | Advance Contracting (Yes/No) | Tender Invitation (MM/YY) | Contract Signing (MM/YY) | Contract Price in Local Currency (In INR crore) | Contract Price Equivalence in USD (In million) | Contractor’s Name | Origin of Country | Contract Signing Date | Contract Period (Months)
Goods
Station Improvement (Component A)
1 | MRVC/G/201 | LOT- I, PROCUREMENT OF 22 Nos (CR-18, WR-10) Total - 28 Nos of ESCALATORS (Design, Manufacturing, Supply, Multiple loading/ unloading, Installation, Testing, Commissioning and maintenance during warranty period) at Mira Road and Kandivali of Western Railway and Neral and Kasara of Central Railway (Ph-I). | 11.11 | 1.3887 | 80 | 20 | Goods | NOCT | Post | Yes | Yes | 3/23 | 10/23 | 14.8 | 2.1143 | M/s Johnson Pvt Ltd, Chennai | India | 06.10.2023 | 18 Months i.e. upto 23.02.2025 Extended upto 23.02.2026 | Under implementation | Work in progress, MIRA: Out of 06 at MIRA, material for 02 nos recived and 01 commissioned and 01 under commissioning. KILE: Out of 04 nos at KILE, 01 commissioned. Out of 05 nos at NRL and 07 nos at KSRA, GAD for 08 nos, 04 of NRL and 04 of KSRA approved.
|  | LOT- II, PROCUREMENT OF 15 Nos (CE-9, WR-6) of ELEVATORS (Design, Manufacturing, Supply, Multiple loading/ unloading, Installation, Testing, Commissioning and maintenance during warranty period) at Mira Road and Kandivali of Western Railway and Neral and Kasara of Central Railway (Ph-I). | 2.39 | 0.29875 | [5 empty] | Yes | Yes | 3/23 | 11/23 | 2.49 | 0.35571 | M/s Omega Ahemedabad | India | 06.11.2023 | 18 Months i.e. upto 11.03.2025 Extended upto 11.03.2026 | Under implementation | Work in progress MIRA: Out of 3 Nos at MIRA, two commissioned at PF-1. and at PF-2&3. one under commissioning at PF-4, KILE: Out of 3 nos at KILE, One commissioned in Jan-25. Out of 06 nos at NRL and 03 Nos at KSRA, GAD for 01 No at KSRA and 02 Nos at NRL approved.
2 | MRVC/G/202 | LOT- I-Procurement of 50 nos (CR-39, WR-11) of Escalators - Supply, Installation, Testing, Commissioning of Escalators at BNDP, MLND, VK, GC, DI, GTBN, CMBR, GV, MNKRD, of CR and Santacruz, NSP, BSR, BHY of WR under Station Improvement work | 26.44 | 3.305 | 80 | 20 | Goods | IOCT | Prior | Yes | Yes | 08/24 | 11/24 | 27.43 | 3.9186 | M/s. Johnson Lifts Pvt. Ltd.(Chennai) | India | LOA date 28.12.2024 | 18 Months | Under implementation | LOA issued on 28.12.2024.
|  | LOT- II-Procurement of 27 Nos (CR-21, WR-6) of Elevators - Supply, Installation, Testing, Commissioning of Elevators at BNDP, MLND, VK, GC, DI, GTBN, CMBR, GV, MNKRD, of CR and Santacruz, NSP, BSR, BHY of WR under Station Improvement work | 4.49 | 0.56125 | [5 empty] | Yes | Yes | 08/24 | 11/24 | [7 empty] | Tender opened TEC under discussion
3
4
5
|  | Sub Total | 44.43 | 5.5537 | [9 empty] | 44.72 | 6.3886
CBTC
7
8
|  | Sub Total | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
|  | Total of Goods and Plants | 44.43 | 5.5537 | [9 empty] | 44.72 | 6.3886
Notes: 1) *80% of total value (including taxes) will be funded by the bank for Works, Goods, consulting and non-consulting services under Component A (Stn. Imp) and 100% (including taxes) for Goods, consulting and non-consulting services under Component B (TA Studies)
Notes: 2) Exchange rate (USD 1: INR 80)

## IIIA-Project Consultancies & TA
Project Name: Mumbai Urban Transport Project IIIA-Station Improvement
Procurement Plan: Consultancies
| Project Implementation Entity: Mumbai Railway Vikas Corporation Ltd., Mumbai, India | [12 empty] | Revision No: 05 |  | Revision Date: | 07.04.2025
Specific Procurement Arrangements | [11 empty] | Scheduled Dates |  | Contract Award Details | [5 empty] | Contract Implementation Status
Serial No. | Package/ Contract No. | Description of Contract | Cost Estimate in local currency (INR in crore) | Cost Estimate in USD million | Funding* Source by AIIB in USD (Millions) (including taxes) | Funding* Source by Others in USD MIllions (including taxes) | Procurement Category | Procurement Method | Review by Bank (Prior or Post) | Pre-qualification (Yes/No) | Advance Contracting (Yes/No) | Tender Invitation (MM/YY) | Contract Signing (MM/YY) | Contract Price in Local Currency | Contract Price Equivalence in USD | Contractor’s Name | Origin of Country | Contract Signing Date | Contract Period (Months)
(A)
1 | MRVC/Cons/223 | Station Improvement-Consultancy for Detail Designing Engineering including Structural & Architectural design of Station Improvement | 8 | 1 | 80 | 20 | Consultancy | QCBS | Post |  | Yes | 2024-01-21 | 2024-11-21 | 9.1 | 1.3 | M/s. Ayesa Ingenieria y Arquitectura S.A.U -UP(India) in JV with M/s. Amiand Consulting Pvt. Ltd. Vakola, Santacruz East - Mumbai | India | 2022-01-29 | Part A 12 Months, Part B 36 Months after part A. | Under Implementation
2 | MRVC/Cons/OHS/225 | Occupational Health and Safety (OHS) audit and monitoring implementation of OHS plan at worksites of various projects on Central and Western Railway in MMR area of Mumbai by MRVC as per Term of Reference | 1.89 | 0.24 | 80 | 20 | Consultancy | QCBS | Post | Yes | Yes | 08/23 | 12/23 | 3.88 | 0.49 | M/s. URS Scott Wilson India Pvt. Ltd. in JV with AECOM India Pvt. Ltd | India | 24/04/2024 | 36 | Under Implementation
|  | Sub Total of Consultancy (A) | 9.89 | 1.24 | [9 empty] | 12.98 | 1.79
(B)
1 | MRVC/TA/131 | TA study for Improving Universal Access for PWDs (Persons with Disability) | 3.6 | 0.45 | 100 | 0 | Consultancy | Direct Selection | Post | No | Yes | 10/21 | 12/12 | 3.6 | 0.51 | Indian Institute of Technology (IIT), Roorkee | India | 2022-12-12 | 12 | Under Implementation
2 | MRVC/Costing and Financial Consultancy/MUTP-3A/RFP/2024 | Development of a framework for Financial & Economic Sustainability of Suburban Railway system in MMR | 5 | 0.625 | 100 | 0 | Consultancy | Direct Selection SSS | Prior | No | Yes | - | 01/25 | 5.89 | 0.73625 | Indian Institute of Technology (IIT) Bombay, Mumbai | India | 28.01.2025 | 30 | Under Implementation
3 |  | Technical Assistance Study for Network Expansion and Other improvement works/projects needed for Mumbai suburban services to improve quality of service, capacity augmentation, safety and comfort to the commuters using suburban services and making detailed proposals for MUTP Phase-IV based on the study recommendations | 10.54 | 1.3175 | 100 | 0 | Consultancy | QCBS | Post
4 | MRVC/TA/226 | Flood Vulnerability and Mitigation Assessment for Mumbai suburban system of Western and Central Railway | 7.93 | 0.99125 | 100 | 0 | Consultancy | QCBS | Post
5 |  | TA study for detailed proposal for underground suburban corridor between Mumbai Central to Churchgate on WR and Parel to CSMT on CR.
Study of existing station lighting system and suggest smart lighting solutions by simulating the lighting profile using latest software techniques as per international standards along with utilization of energy conservation measures such as natural light including green energy solutions like Solar power etc
Feasibility Study of existing 110kV Transmission lines in North-Eastern and South-Eastern sections of Central Railway for monetization by exploring various possible options and suggesting the best solution in the interest of Indian Railways
Operation research on requirement of stabling sidings on WR for operational needs of present and future suburban corridors.
Feasibility study of automation of train operation by making most suitable changes in the train running schedule during the period of disruption in train operations in Mumbai suburban system utilizing online monitoring tools and innovative AI technologies.