## Publication - PP Template
P001023 Reconstruction of A-27 Highway Atyrau-Dossor Section Project
Project Country: Kazakhstan |  | Bank's Approval Date of the Initial Procurement Plan: October 22, 2025
Project Sector: Transport |  | Approved PP Update No.: 1
AIIB Loan Amount (USD Million): 272.0 |  | Bank's Approval Date of the PP Update: N/A
PROJECT PROCUREMENT PLAN
Project Implementing Agency | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration
JSC NC QazAvtoJol | CS-02 | Project Management Consulting Services | 3400000 | 88 | Consulting Services | IOCS-QCBS | Prior Review | Not Applicable | 2025-11-01 | 2026-06-01 | 4 years
JSC NC QazAvtoJol | CS-01 | Construction Supervision of Design, Build and Maintenance Works | 3700000 | 88 | Consulting Services | IOCS-QCBS | Prior Review | Not Applicable | 2025-11-01 | 2026-06-01 | 4 years
JSC NC QazAvtoJol | IOCT-1 | Design and Build for reconstruction and upgrading (from 2- to 4-lanes) of 86 km road section (K512-K598) of the A-27 Highway between the city of Atyrau and Town of Dossor in the Atyrau Region of Kazakhstan. Output and Performance-based Road Maintenance | 253600000 | 88 | Works | IOCT1S2E | Prior Review | No | 2025-11-01 | 2026-06-01 | 4 years