## Sheet1
Sri Lanka: Sampur-Kappalthurai Transmission Infrastructure Development Project
Loan Number: L0921A
PP of June 2025
Contract Number 1 | Description | Procurement Category 2 | A | Selection Method / Procurement Method | Particular Selection Method for Firms / Basis of Qualification | Evaluation Criteria | Bank's Review | Sheduled Date of Publication of REOI / SPN | Scheduled Contract Award Date
A. Consulting Services
Not Applicable
Sub-total A
B. Goods, Works and non-Consulting Services
CEB/AGM(P)/2024/IOCT/SKTDP-Lot A | Construction of Sampur – Kappalthurai 220 kV Transmission Line | Procurement of Plant (Design, Supply and Installation) | 17.3592 | IOCT | Post Qualification | Lowest Evaluated Cost | Prior Review | 2025.07.10 | 2026.01.08
CEB/AGM(P)/2024/IOCT/SKTDP-Lot B | Costruction of Sampur Collector 220(132)/33kV Grid Substation and Augmentation of Kappalthurai 220(132)/33kV Grid Substation | Procurement of Plant (Design, Supply and Installation) | 16.1627 | IOCT | Post Qualification | Lowest Evaluated Cost | Prior Review | 2025.07.31 | 2026.01.29