## Publication - PP Template
P000969 Baku Metro Expansion Project – Phase I
Project Country: | Azerbaijan | Bank's Approval Date of the Initial Procurement Plan: | 03-20-2025
Project Sector: | Transport | Approved PP Update No.: | Version 5
AIIB Loan (USD Million): | 180.00 | Bank's Approval Date of the PP Update: | 08-18-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
“Baku Metropolitan” Closed Joint-Stock Company | BMEP/P1/CW-01 | Construction Completion and Supply and Installation of Equipment for the Darnagul Electrical Depot | 114,929,335.36 | 85.00 | Works | IOCT (International Open Competitive Tendering) |  | Rated Criteria | Prior | No | 08-18-2026 | 01-24-2027 | 720 | Cleared