## Publication - PP Template
P000969 Baku Metro Expansion Project – Phase I
Project Country: | Azerbaijan | Bank's Approval Date of the Initial Procurement Plan: | 03-20-2025
Project Sector: | Transport | Approved PP Update No.: | Version 4
AIIB Loan (USD Million): | 180.00 | Bank's Approval Date of the PP Update: | 08-11-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
“Baku Metropolitan” Closed Joint-Stock Company | BMEP/P1/CS-04/03 | Senior Contract and Claim Management Specialist | 130,000.00 | 85.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 08-10-2026 | 09-25-2026 | 365 | Cleared
“Baku Metropolitan” Closed Joint-Stock Company | BMEP/P1/CS-04/01 | Senior Contract and Procurement Specialist | 180,000.00 | 85.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 08-10-2026 | 09-25-2026 | 365 | Cleared
“Baku Metropolitan” Closed Joint-Stock Company | BMEP/P1/CS-03/08 | Project Delivery Manager | 71,000.00 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 08-10-2026 | 09-25-2026 | 365 | Cleared
“Baku Metropolitan” Closed Joint-Stock Company | BMEP/P1/CW-04 | Renovation and Furnishing of the Project Implementation Unit (PIU) Office | 120,000.00 | 85.00 | Works | RFQ (Request for Quotations) |  | Lowest Evaluated Cost | Post |  |  | 09-23-2026 | 60 | Cleared
“Baku Metropolitan” Closed Joint-Stock Company | BMEP/P1/CS-02 | Consulting Services for Design Review and Supervision of Completion of Construction of Darnagul and Khojasan Electric Depots and Installation of Equipment | 6,327,160.00 | 85.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 04-06-2026 | 08-31-2026 | 14 | Cleared
“Baku Metropolitan” Closed Joint-Stock Company | BMEP/P1/CS-03/03 | Lead Environmental and Social Safeguards Specialist | 42,353.00 |  | Consulting Services | LCSIC (Limited Competitive Selection of Individual Consultants) |  |  | Prior |  | 09-01-2025 | 10-09-2025 | 366 | Cleared
“Baku Metropolitan” Closed Joint-Stock Company | BMEP/P1/CS-03/02 | Local Financial Management Specialist | 42,353.00 |  | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Prior |  |  | 08-16-2025 | 366 | Cleared
“Baku Metropolitan” Closed Joint-Stock Company | BMEP/P1/CS-03/01 | Local Procurement and Contract Administration Specialist | 42,353.00 |  | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Prior |  |  | 08-16-2025 | 366 | Cleared
“Baku Metropolitan” Closed Joint-Stock Company | BMEP/P1/CS-01 | Environmental and Social Consulting Services for the Baku Metro Expansion Project (Phase 1) | 198,116.10 | 100.00 | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) |  | Prior |  | 03-26-2025 | 05-24-2025 | 98 | Cleared
|  | Total: | 7153335.1