## Publication - PP
P001180 Baku Absheron Circular Railway Project
Project Country: | Azerbaijan | Bank's Approval Date of the Initial Procurement Plan: | 09-25-2026
Project Sector: | Transport | Approved PP Update No.: | Version 1
AIIB Loan (USD Million): |  | Bank's Approval Date of the PP Update: | 09-25-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
Azerbaijan Railways Closed Joint Stock Company | BACRP/AIIB-CS-CQS-01 | Environmental and Social Consulting Services for the Baku Absheron Circular Rail | 290,400.00 | 100.00 | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) |  | Post |  | 10-08-2026 | 12-07-2026 | 126 | Cleared
Azerbaijan Railways Closed Joint Stock Company | BACRP/AIIB-CS-IC-03 | PIU Senior Financial Specialist | 193,600.00 | 100.00 | Consulting Services | LCSIC (Limited Competitive Selection of Individual Consultants) |  |  | Post |  | 12-21-2026 | 01-21-2027 | 1441 | Cleared
Azerbaijan Railways Closed Joint Stock Company | BACRP/AIIB-CS-IC-02 | PIU Environmental and Social Specialist | 204,250.00 | 100.00 | Consulting Services | LCSIC (Limited Competitive Selection of Individual Consultants) |  |  | Post |  | 10-01-2026 | 10-25-2026 | 1529 | Cleared
Azerbaijan Railways Closed Joint Stock Company | BACRP/AIIB-CS-IC-01 | PIU Senior Procurement and Contract Administration Specialist | 204,250.00 | 100.00 | Consulting Services | LCSIC (Limited Competitive Selection of Individual Consultants) |  |  | Post |  | 09-28-2026 | 10-15-2026 | 1539 | Cleared
|  | Total: | 892,500.00