## Publication - PP
S000656 Urban Sustainable Water Supply Development
Project Country: | Cambodia | Bank's Approval Date of the Initial Procurement Plan: | 07-24-2024
Project Sector: | Water | Approved PP Update No.: | Version 3
Grant Amount (USD Million): | 3.6 | Bank's Approval Date of the PP Update: | 10-23-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
Ministry of Industry, Science, Technology & Innovation | MISTI-USWSDP-IC-03A | National Environmental and Social Safeguard Consultant | 11340 | 100 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Prior |  |  | 11-01-2026 | 180 | Cleared
Ministry of Industry, Science, Technology & Innovation | MISTI-USWSDP-IC-03 | National Environmental and Social Safeguard Consultant | 11340 | 100 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 05-04-2026 | 06-11-2026 | 14 | Cleared
Ministry of Industry, Science, Technology & Innovation | MISTI-USWSDP-CS-01 | Feasibility Study and Detailed Engineering Design Consulting Firm | 3153627.22 | 100 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 08-28-2024 | 04-05-2025 | 622 | Cleared
Ministry of Industry, Science, Technology & Innovation | MISTI-USWSDP-IC-02 | National Procurement Consultant (Intermittent) | 10465.12 | 100 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 07-15-2024 | 09-11-2024 | 271 | Cleared
Ministry of Industry, Science, Technology & Innovation | MISTI-USWSDP-IC-01 | National Water Supply Consultant | 29438.79 | 100 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 07-15-2024 | 09-11-2024 | 271 | Cleared
|  | Total: | 3216211.13