## Publication - PP Template
P000452 Climate Adaptive Irrigation and Sustainable Agriculture for Resilience Project (CAISAR)
Project Country: | Cambodia | Bank's Approval Date of the Initial Procurement Plan: | 09-08-2025
Project Sector: | Water | Approved PP Update No.: | Version 2
AIIB Loan (USD Million): | 100.00 | Bank's Approval Date of the PP Update: | 08-28-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
Ministry of Water Resources and Meteorology | AIIB-CAISAR-G-07 | Supply and Installation of Accounting Software (Sage 50) | 24,500.00 | 100.00 | Goods | RFQ (Request for Quotations) |  | Lowest Evaluated Cost | Post | No |  | 09-25-2026 | 90 | Cleared
Ministry of Water Resources and Meteorology | AIIB-CAISAR-IC-05 | National Procurement Specialist | 36,000.00 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 08-20-2026 | 10-03-2026 | 365 | Cleared
Ministry of Water Resources and Meteorology | AIIB-CAISAR-IC-04 | National Accounting Asistance | 20,400.00 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 08-20-2026 | 10-13-2026 | 365 | Cleared
Ministry of Water Resources and Meteorology | AIIB-CAISAR-IC-03 | National Financial Management Specialist | 36,000.00 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 08-20-2026 | 10-13-2026 | 365 | Cleared
Ministry of Water Resources and Meteorology | AIIB-CAISAR-IC-02 | National Environemental Specialist | 18,000.00 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 09-22-2026 | 11-15-2026 | 365 | Cleared
Ministry of Water Resources and Meteorology | AIIB-CAISAR-IC-01 | National Social Specialist | 18,000.00 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 09-22-2026 | 11-15-2026 | 365 | Cleared
Ministry of Water Resources and Meteorology | AIIB-CAISAR-G-06 | Supply and Delivery of Office Furniture | 40,000.00 | 100.00 | Goods | RFQ (Request for Quotations) |  | Lowest Evaluated Cost | Post | No |  | 10-15-2026 | 90 | Cleared
Ministry of Water Resources and Meteorology | AIIB-CAISAR-G-05 | Supply and Delivery of Office Equipment | 90,000.00 | 100.00 | Goods | RFQ (Request for Quotations) |  | Lowest Evaluated Cost | Post | No |  | 10-25-2026 | 90 | Cleared
Ministry of Water Resources and Meteorology | AIIB-CAISAR-G-03 | Supply and Delivery of 6 units of motorcycles (for PMU) | 15,000.00 | 100.00 | Goods | RFQ (Request for Quotations) |  | Lowest Evaluated Cost | Post | No |  | 10-24-2026 | 90 | Cleared
Ministry of Water Resources and Meteorology | AIIB-CAISAR-G-01 | Supply and Delivery of 4 Vehicles (3 Pick-up truck, and 1 SUV with high safety) | 225,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 08-25-2026 | 10-24-2026 | 90 | Cleared
Ministry of Water Resources and Meteorology | AIIB-CAISAR-W01 | Modernization of main canal and distribution system of Krepeu Trom irrigation scheme under the CAISAR | 5,072,431.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 08-22-2025 | 12-23-2025 | 28 | Cleared
|  | Total: | 5,595,331.00