## Publication - PP Template
P000770 Hubei Global Air Cargo Logistics Project
Project Country: | China | Bank's Approval Date of the Initial Procurement Plan: | 02-14-2025
Project Sector: | Transport | Approved PP Update No.: | Version 9
AIIB Loan (USD Million): | 400.00 | Bank's Approval Date of the PP Update: | 01-28-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
Ezhou Linkong Group Co., Ltd. | HGAC-CS05 | Three-Star Green Building Certification for New Domestic Buildings | 160,600.00 | 100% | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) |  | Post |  | 01-26-2026 | 03-26-2026 | 730 | Cleared
Ezhou Linkong Group Co., Ltd. | HGAC-CS04 | Certification for New Buildings Related to International Green Building | 1,053,300.00 | 100% | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 01-26-2026 | 04-24-2026 | 730 | Cleared
Ezhou Linkong Group Co., Ltd. | HGAC-CS01 | Technical Support for Project Management, Training, Study Tours, Development and Promotion of Knowledge Products, etc. | 1,384,000.00 | 100% | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 12-01-2025 | 02-27-2026 | 730 | Cleared
Ezhou Linkong Group Co., Ltd. | HGAC-GD01 | Procurement and Installation of Rooftop Photovoltaic Equipment for the Customs Inspection Center and Bonded Warehouses 1#-5# in Phase I (Starter Zone), with a total photovoltaic panel area of 26,163 m². | 3,191,400.00 | 100% | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-14-2025 | 12-31-2025 | 360 | Cleared
Ezhou Linkong Group Co., Ltd. | HGAC-CW13 | Other works, including landscape greenery, landscape water features, landscape electrical systems, outdoor signs and plaques, etc. | 8,510,100.00 | 100% | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 10-24-2025 | 12-10-2025 | 180 | Cleared
Ezhou Linkong Group Co., Ltd. | HGAC-CW12 | Total construction area: 33,597.02㎡, including 19,903.88㎡ for W01-A comprehensive office building and 13,693.14㎡ for W01-B comprehensive office building. | 24,500,000.00 | 100% | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 07-18-2025 | 10-19-2025 | 180 | Cleared
Ezhou Linkong Group Co., Ltd. | HGAC-CW11 | Total construction area: 13,346.71㎡, including 13,110.89㎡ for S01 Duty-free Center and 235.82㎡ for S01-2 Pump Room. | 15,500,000.00 | 100% | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 07-18-2025 | 10-19-2025 | 180 | Cleared
Ezhou Linkong Group Co., Ltd. | HGAC-CW09 | North District Municipal Road, (1) Overpass Connecting Road 1# (Roadbed area 2667㎡), Overpass Connect Road 2# (Roadbed area 2375㎡)； (2) 4 North District roads (Planning Second Road 581.6m, Third Road 990m, Planning Fourth Road 1075m, Planning Fifth Road 354m) Comprehensive Bonded Road and related infrastructure；(3) 2# checkpoint. | 23,500,000.00 | 100% | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 05-30-2025 | 08-31-2025 | 180 | Cleared
Ezhou Linkong Group Co., Ltd. | HGAC-CW02 | Total construction area: 58279.64 ㎡, including M01-A logistics warehouse 21862.29 ㎡, M01-B logistics warehouse 21910.62㎡, T01 inspection site construction area of 13499.33 ㎡, and supporting buildings of 1007.4 ㎡. | 38,000,000.00 | 100% | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 05-07-2025 | 08-08-2025 | 180 | Cleared
Ezhou Linkong Group Co., Ltd. | HGAC-CW01 | J01/K01 logistics warehouse, with a total construction area of 49513.88㎡ | 27,500,000.00 | 100% | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 04-30-2025 | 08-31-2025 | 180 | Cleared
Ezhou Linkong Group Co., Ltd. | HGAC-CW10 | Earth Works | 34,967,000.00 | 100% | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | Yes | 03-24-2025 | 10-20-2025 | 120 | Cleared
Ezhou Linkong Group Co., Ltd. | HGAC-CS03 | External Resettlement and Social Monitoring and Assessment Services | 166,000.00 | 100% | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) |  | Post |  | 02-13-2025 | 04-13-2025 | 1650 | Cleared
Ezhou Linkong Group Co., Ltd. | HGAC-CS02 | External Environmental Monitoring Services | 166,000.00 | 100% | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) |  | Prior |  | 02-13-2025 | 04-13-2025 | 1650 | Cleared
|  | Total: | 178,598,400.00