## Publication - PP Template
P000406 Liaoning Green Smart Public Transport Demonstration Project
Project Country: | China | Bank's Approval Date of the Initial Procurement Plan: | 05-08-2024
Project Sector: | Transport | Approved PP Update No.: | Version 9
AIIB Loan (USD Million): | 150.00 | Bank's Approval Date of the PP Update: | 08-21-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | HLD-G03 | Procurement of electric buses: nineteen 8-m-long buses (excluding on-board smart devices) | 1,620,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 08-28-2026 | 09-22-2026 | 60 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | HLD-G09 | Procurement of 50 sets of supporting charging devices for Jianshangzi charging station | 270,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 08-28-2026 | 09-22-2026 | 60 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | FX-G06 | Procurement of 50 sets of supporting charging devices for 5 charging stations | 2,440,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 08-28-2026 | 09-22-2026 | 60 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | PJ-G04 | Procurement of twenty 6-m-long electric buses, ninty-two 8-m-long electric buses， twenty 10.5-m-long passenger transport electric buses (132 buses in total, all vehicles equipped with on-board smart devices) | 13,800,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 02-11-2026 | 03-22-2026 | 180 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | YK-G07 | Procurement of Thirty-five 10.5-m-long pure electric buses | 4,830,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 09-15-2025 | 10-24-2025 | 180 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | YK-G02(Re) | Procurement and installation of 504 sets of on-board end device,public transport dispatch command center,software for smart public transport system, and upgrading of modular machine room | 3,680,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Rated Criteria | Prior | No | 06-03-2025 | 08-06-2025 | 210 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | JZ-G05 | Procurement of 10 eclectric buses：5 of 10.5-m-long low-entry pure electric buses and 5 of 7-m-long pure electric passenger transport buses (including board smart devices) | 1,090,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 10-16-2024 | 11-10-2024 | 30 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | HLD-G05A(Re) | Procurement and installation of on-board smart devices. | 1,630,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 06-27-2024 | 09-17-2024 | 150 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | FX-G05A(Re) | Procurement and installation of on-board smart devices. | 1,630,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 06-26-2024 | 09-16-2024 | 150 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | YK-G04(Re) | Procurement of twenty 8.5-m-long pure electric buses and thirty 12-m-long pure electric buses. | 6,510,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 04-22-2024 | 07-16-2024 | 180 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | FX/HLD-G04 | Intelligent upgrading of hardware and software in the dispatch command center. Purcurement and installation of smart public transport platform.(Joint procurement by Fuxin and Huludao) | 1,640,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 06-01-2023 | 08-01-2023 | 28 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | YK-G04-archived | Procurement of twenty 8.5-m-long pure electric buses and thirty 12-m-long pure electric buses. | 6,510,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 10-01-2023 | 12-01-2023 | 28 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | YK-G03 | Procurement of 110 sets of supporting charging devices (charging pile equipment, charging pile installation, power substation electrical installation, high and low voltage distribution equipment, etc.) | 5,190,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 02-01-2024 | 04-02-2024 | 28 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | YK-G02-archived | Procurement and installation of 504 sets of on-board end device,public transport dispatch command center,software for smart public transport system, and upgrading of modular machine room | 3,680,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 11-01-2023 | 01-01-2024 | 28 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | PJ-G04 | Procurement of seventy-three 8-m-long electric buses，forty 12-m-long electric buses， ten 8-m-long passenger transport electric buses， ten 11-m-long passenger transport electric buses，(133 buses in total, all vehicles equipped with on-board smart devices) | 13,400,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 10-01-2023 | 12-01-2023 | 28 | Cancel-Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | PJ-G03 | Procurement of smart public transport system and equipments, upgrading of smart dispatch command center (replacing the orginal vehicle devices) | 4,600,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 06-01-2023 | 08-01-2023 | 28 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | PJ-G02 | Procurement and installtion 132 charging piles (excluding high-voltage connection) for 6 parking lots, including Railway station and Liulihe etc. | 1,580,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 10-01-2023 | 02-01-2024 | 28 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | JZ-G02 | Procurement of smart public transport system and equipments, upgrading of data room,and replacing the original vehicle devices | 1,930,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 09-01-2023 | 11-01-2023 | 28 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | HLD-G05B | Procurement and installation of on-board smart devices. | 40,000.00 | 100.00 | Goods | RFQ (Request for Quotations) |  | Lowest Evaluated Cost | Post | No |  | 01-01-2024 | 7 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | HLD-G05A-archived | Procurement and installation of on-board smart devices. | 1,630,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 06-01-2023 | 10-02-2023 | 28 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | HLD-G03 | Procurement of electric buses: forty 11-m-long buses(excluding on-board smart devices) | 4,030,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 11-01-2023 | 03-03-2024 | 28 | Cancel-Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | HLD-G02 | Procurement of electric buses: sixty-three 10.5-m-long buses and thirty 11-m-long buses(excluding on-board smart devices) | 8,830,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 10-01-2022 | 02-01-2023 | 28 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | FX-G05B | Procurement and installation of on-board smart devices. | 30,000.00 | 100.00 | Goods | RFQ (Request for Quotations) |  | Lowest Evaluated Cost | Post | No |  | 01-01-2024 | 7 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | FX-G05A-archived | Procurement and installation of on-board smart devices. | 1,630,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 06-01-2023 | 08-01-2023 | 28 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | CS03 | Retroactive contracts bidding document review and contract management consulting service（ICS) | 40,000.00 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  | Lowest Evaluated Cost | Post | No | 01-01-2021 | 02-08-2021 | 14 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | CS02 | Project performance monitoring and achievement summary（CQS) | 200,000.00 | 100.00 | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) | Lowest Evaluated Cost | Prior | No | 06-14-2022 | 08-12-2022 | 1 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | CS01 | Project Management and Technical Support（QCBS） | 570,000.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) | Lowest Evaluated Cost | Prior | No | 06-15-2022 | 11-09-2022 | 14 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | YK-G01 | Procurement of ninety-seven 10.5-m-long pure electric buses. | 13,380,000.00 | 100.00 | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 09-30-2022 | 01-31-2023 | 28 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | PJ-G01 | Procurement of forty 6.5-m-long electric buses， seventy 8-m-long electric buses，fifty-one 10.5-m-long new energy buses(totally 161 buses with on-board smart devices). | 14,100,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-10-2022 | 03-13-2023 | 28 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | JZ-G01 | Procurement of electric buses: seventy-eight 10.5-m-long low-entry pure electric buses,a hundred 10.5-m-long two-step pure electric buses, twenty 11-m-long pure electric buses,ten 7-m-long pure electric passenger transport bus(208 vehicles in total, including 208 sets of on-board smart devices) | 24,260,000.00 | 100.00 | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-26-2022 | 03-29-2023 | 28 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | HLD-G01 | Procurement of electric buses: seventy-five 10.5-m-long buses and thirty 8-m-long buses(excluding on-board smart devices) | 9,110,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 09-26-2022 | 01-27-2023 | 28 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | FX-G03 | Procurement of electric buses: thirty-five 11-m-long buses(excluding on-board smart devices) | 3,530,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 05-01-2024 | 07-01-2024 | 28 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | FX-G02 | Procurement of electric buses: thirty 8-m-long buses, fifty-eight 10.5-m-long buses and ten 11-m-long buses(excluding on-board smart devices). | 8,820,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 10-01-2022 | 12-01-2022 | 28 | Cleared
Liaoning Provincial Government/Liaoning Urban and Rural Construction Project Management Company | FX-G01 | Procurement of electric buses: forty 10.5-m-long buses and fifty 11-m-long buses | 8,730,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 09-26-2022 | 11-12-2022 | 28 | Cleared
|  | Total: | 174,960,000.00