## Publication - PP Template
S000658 China-ASEAN Sea-Rail Multimodal Logistics Project
Project Country: | China | Bank's Approval Date of the Initial Procurement Plan: | 06-29-2024
Project Sector: | Transport | Approved PP Update No.: | Version 1
AIIB Loan (USD Million): | 1.58 | Bank's Approval Date of the PP Update: | 03-23-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
Qinzhou Huangma Assets Management Group Co., Ltd. | CS-04-2 | Project Preparation Coordinator-2 | 40000 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 03-30-2026 | 05-07-2026 | 720 | Cleared
Qinzhou Huangma Assets Management Group Co., Ltd. | CS-05-2 | Partnership Selection and Promotion Consulting Services-2 | 150000 | 100.00 | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) |  | Post |  | 02-18-2026 | 05-06-2026 | 720 | Cleared
Qinzhou Huangma Assets Management Group Co., Ltd. | CS-04-1 | Project Preparation Coordinator-1 | 40000 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  |  | 02-16-2026 | 720 | Cleared
Qinzhou Huangma Assets Management Group Co., Ltd. | CS-05-1 | Partnership Selection and Promotion Consulting Services-1 | 150000 | 100.00 | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) |  | Post |  | 02-18-2026 | 05-06-2026 | 720 | Cleared
Qinzhou Huangma Assets Management Group Co., Ltd. | CS-03 | Senior Project Preparation Specialist | 40000 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 03-30-2026 | 05-23-2026 | 720 | Cleared
Qinzhou Huangma Assets Management Group Co., Ltd. | Services-02 | Climate Assessment and Green and Smart Logistics Park Planning and Design | 1330000 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) |  |  | Prior |  | 04-25-2024 | 10-31-2024 | 720 | Cleared
Qinzhou Huangma Assets Management Group Co., Ltd. | Services-01 | Demand and Economic Analysis | 250000 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) |  |  | Post |  | 05-10-2024 | 09-05-2024 | 720 | Cleared
|  | Total: | 2000000