## Publication - PP Template
S000700 El Salvador transmission grid expansion for climate transition Project
Project Country: | El Salvador | Bank's Approval Date of the Initial Procurement Plan: | 10-08-2026
Project Sector: | Energy | Approved PP Update No.: | Version 1
AIIB Loan (USD Million): |  | Bank's Approval Date of the PP Update: | 10-08-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
Empresa Transmisora de El Salvador, S.A. de C.V. | E-002-Grant | CONSULTING SERVICES FOR THE ENVIRONMENTAL, SOCIAL, LEGAL STUDY AND BASIC ENGINEERING OF THE PROJECTS: 230 kV GUAJOYO – SANTA ANA TRANSMISSION LINE, 115 kV TECOLUCA – EL PEDREGAL TRANSMISSION LINE, AND CAPACITY EXPANSION AT NEJAPA 230/115 kV SUBSTATION | 950,000.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 08-31-2026 | 03-01-2027 | 211 | Cleared
|  | Total: | 950,000.00