## Sheet1
AIIB FRA SCRIP PROJECT
Procurement Plan
| Serial No. | Contract Number | Contract Description | Procurement Category | Procurement Method | Bank's Review | Sheduled Date of Publication of REOI | Contract Duration (Months)
| CS-01 | SCRIP-CS-01 | Consultancy Services for Feasibility Study – AIIB Funded Projects | Consulting Services (Firm) | IOCS (QCBS) | Prior Review | Q2 2026 | 15
| CS-02 | SCRIP-CS-02 | Procurement Consultant | Consulting Services (Individual) | OCSIC-LCBS | Prior Review | Q2 2026 | 6
| CS-03 | SCRIP-CS-03 | OHS Consultant | Consulting Services (Individual) | OCSIC-LCBS | Prior Review | Q3 2026 | 6