## Publication
P000889 Tbilisi Metro Modernization Project
Project Country: | Georgia | Bank's Approval Date of the Initial Procurement Plan: | 09-30-2024
Project Sector: | Transport | Approved PP Update No.: | Version 4
AIIB Loan (USD Million): | 140 | Bank's Approval Date of the PP Update: | 09-29-2025
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Activity Status
Tbilisi Transport Company LLC | TTC-IC-01 | IC for supervision and design review | 58156 | 100 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Prior |  |  | 2025-10-18 | Cleared
Tbilisi Transport Company LLC | TTC-C01 | Supervision Consultant | 2300000 | 100 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 2026-05-06 | 2026-11-30 | Cleared
Tbilisi Transport Company LLC | TTC-G01 | Supply of electric metro cars | 230000000 | 58 | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 2024-09-30 | 2025-01-15 | Cleared
|  | Total: | 232358156