## Publication - PP Template
P000862 Assam Intra State Transmission System Enhancement Phase II
Project Country: | India | Bank's Approval Date of the Initial Procurement Plan: | 09-25-2024
Project Sector: | Energy | Approved PP Update No.: | Version 3
AIIB Loan (USD Million): | 140.61 | Bank's Approval Date of the PP Update: | 01-13-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
Assam Electricity Grid Corporation Ltd (AEGCL) | AEGCL/MD/AIIB/Phase-II/PKG:P-II-E/2026/P-II-E | Construction of 220/132KV, 2X160 MVA AIS Substation at Morigaon along with associated transmission lines | 25,448,704.00 | 82.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 01-13-2026 | 05-17-2026 | 1095 | Cleared
Assam Electricity Grid Corporation Ltd (AEGCL) | P-II-B | Construction of 132/33KV Titabor GIS and 132/33KV Chabua AIS along with associated transmission lines | 42,888,161.00 | 82.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 03-02-2024 | 09-16-2024 | 1295 | Cleared
Assam Electricity Grid Corporation Ltd (AEGCL) | P-II-A | Construction of 220/132KV ROWTA GIS along with associated transmission lines | 49,493,173.00 | 82.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 03-02-2024 | 09-01-2024 | 1295 | Cleared
Assam Electricity Grid Corporation Ltd (AEGCL) | Package P-II-D | Construction of 132/33KV, 2X50 MVA AIS at Serfanguri and Dhing along with associated Transmission Lines | 27,222,716.00 | 82.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 03-12-2024 | 08-18-2024 | 1295 | Cleared
Assam Electricity Grid Corporation Ltd (AEGCL) | AEGCL/MD/AIIB/PMC(Phase-II)/2024/07 dtd 29.0.2024 | Selection of Project Management Consultant for the Project "Assam Intra State Transmission System Enhancement Project (Phase-II_ | 6,573,494.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 02-29-2024 | 12-13-2024 | 1800 | Cleared
|  | Total: | 151,626,248.00