## Publication - PP
P000440 Assam Secondary Road Network Improvement Project
Project Country: | India | Bank's Approval Date of the Initial Procurement Plan: | 08-04-2025
Project Sector: | Transport | Approved PP Update No.: | Version 6
AIIB Loan (USD Million): | 320.00 | Bank's Approval Date of the PP Update: | 09-14-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
Public Works Roads Department, Assam, India | ASRIP/C/NCS-1 | Safe Guwahati: AI-Based Driver and Road Monitoring System for Safer Public Transport |  | Non-consulting Services | DC (Direct Contracting) |  |  | Post |  |  | 09-02-2026 | 365 | Cancel-Cleared
Public Works Roads Department, Assam, India | ASRIP/B/ICT-1B | Providing laptops to APWRD engineers under ASRIP | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 05-11-2026 | 08-25-2026 | 90 | Cleared
Public Works Roads Department, Assam, India | ASRIP/C/CS-1-A | Balance Employer’s Representative Services for improvement and upgradation of road from Balichapori, Majuli to Bongalmara, Lakhimpur, including construction of two major bridges over Luit and Subansiri rivers on EPC mode |  | Consulting Services | DS(Direct Selection) |  |  | Post |  |  | 01-16-2026 | 660 | Cleared
Public Works Roads Department, Assam, India | ASRIP/A/RI-8C | Improvement and upgradation of Dhodor Ali (Hulang Katoni to Balighat Tiniali Ch. 40+000 to 44+937 km) under ASRIP | 80.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 04-11-2025 | 07-25-2025 | 28 | Cleared
Public Works Roads Department, Assam, India | ASRIP/A/RI-8A | Improvement and upgradation of Dhodor Ali (Nakachari to Khanikor Ch. 0+000 to 20+000 km) under ASRIP | 80.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 10-29-2024 | 06-17-2025 | 541 | Cleared
Public Works Roads Department, Assam, India | ASRIP/A/RI-8B | Improvement and upgradation of Dhodor Ali (Khanikor to Hulang Katoni Ch. 20+000 to 40+000 km) under ASRIP | 80.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 10-29-2024 | 06-17-2025 | 541 | Cleared
Public Works Roads Department, Assam, India | ASRIP/C/L-1 | Legal Consulting Service under ASRIP | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 11-14-2024 | 01-30-2025 | 180 | Cleared
Public Works Roads Department, Assam, India | ASRIP/C/M-1 | Consultancy Services for Social Media management services for citizen engagement for ASRIP and projects under Asom Mala | 100.00 | Non-consulting Services | RFQ (Request for Quotations) |  | Lowest Evaluated Cost | Post |  |  | 06-01-2025 | 1 | Cleared
Public Works Roads Department, Assam, India | ASRIP/C/FM-2 | Consultancy Services for Financial Management Support services for ASRIP | 100.00 | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) |  | Post |  | 04-10-2023 | 09-21-2023 | 1096 | Cleared
Public Works Roads Department, Assam, India | ASRIP/C/FM-1 | Consultancy services for Internal Audit Services for ASRIP | 100.00 | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) |  | Post |  | 04-19-2023 | 12-29-2023 | 1096 | Cleared
Public Works Roads Department, Assam, India | ASRIP/C/TP-4 | Development Plan for Digital Infrastructure | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 07-14-2025 | 08-21-2025 | 14 | Cancel-Cleared
Public Works Roads Department, Assam, India | ASRIP/C/CS-4B | Individual consultants for road safety audit during construction, component 2 and 3 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Post |  | 07-12-2022 | 08-19-2022 | 14 | Cancel-Cleared
Public Works Roads Department, Assam, India | ASRIP/C/CS-6 | Consultancy services for Environmental & Social (E&S) External Monitoring for ASRIP | 100.00 | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) |  | Post |  | 02-20-2023 | 11-11-2023 | 1097 | Cleared
Public Works Roads Department, Assam, India | ASRIP/B/ICT-3 | Networking and petty IT goods | 100.00 | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 02-26-2021 | 07-10-2021 | 28 | Cleared
Public Works Roads Department, Assam, India | ASRIP/B/ICT-2 | Multipurpose photocopiers for PWRD Offices | 100.00 | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 02-26-2021 | 07-10-2021 | 28 | Cleared
Public Works Roads Department, Assam, India | ASRIP/B/ICT-1B | Procurement of laptops | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 02-26-2021 | 07-10-2021 | 28 | Cancel-Cleared
Public Works Roads Department, Assam, India | ASRIP/B/ICT-1A | Procurement of Desktop computers & peripherals | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 02-26-2021 | 07-10-2021 | 28 | Cleared
Public Works Roads Department, Assam, India | ASRIP/B/AM-1D | Disaster Recovery services | 100.00 | Consulting Services | DS(Direct Selection) |  |  | Prior |  |  | 03-10-2021 | 14 | Cleared
Public Works Roads Department, Assam, India | ASRIP/B/AM-1B | Upgradation of RAMS and Data Updation | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 06-11-2024 | 05-14-2025 | 1081 | Cleared
Public Works Roads Department, Assam, India | ASRIP/B/AM-1A | Consultancy Services for enhancement and management of upgraded APWRD e-portal under ASRIP | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Post |  | 02-26-2021 |  | 0 | Cleared
Public Works Roads Department, Assam, India | ASRIP/A/RS-6 | Road safety works in Tinsukia district | 80.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 02-26-2021 | 07-10-2021 | 0 | Cancel-Cleared
Public Works Roads Department, Assam, India | ASRIP/A/RS-5 | Road safety works in Sivasagar district | 80.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 02-26-2021 | 07-10-2021 | 0 | Cancel-Cleared
Public Works Roads Department, Assam, India | ASRIP/A/RS-4 | Road safety works in Jorhat district | 80.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 02-26-2021 | 07-10-2021 | 28 | Cancel-Cleared
Public Works Roads Department, Assam, India | ASRIP/A/RS-3 | Road safety works in Golaghat district | 80.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 02-26-2021 | 07-10-2021 | 28 | Cancel-Cleared
Public Works Roads Department, Assam, India | ASRIP/A/RS-2 | Road safety works in Dibrugarh district | 80.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 02-26-2021 | 07-10-2021 | 28 | Cancel-Cleared
Public Works Roads Department, Assam, India | ASRIP/A/RS-1-Cancelled | Road safety works in Lakhimpur & Dhemaji district | 80.00 | Consulting Services | NCS (National Competitive Selection) | QCBS (Quality Cost Based Selection) | Lowest Evaluated Cost | Post | No | 06-03-2023 | 06-26-2024 | 1081 | Cleared
Public Works Roads Department, Assam, India | ASRIP/C/TP-3 | Consultancy Services for Technical Assistance for Development of Multimodal and Logistics Master Plan for Assam under ASRIP | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QBS (Quality Based Selection) |  | Post |  | 02-26-2021 |  | 0 | Cleared
Public Works Roads Department, Assam, India | ASRIP/C/CB/3 | Trainings at IIT, Guwahati | 100.00 | Consulting Services | DS(Direct Selection) |  |  | Prior |  |  | 03-10-2021 | 14 | Cleared
Public Works Roads Department, Assam, India | ASRIP/C/CS-5 | Program Coordination and Management Consultancy (PCMC) services for implementation of ASRIP | 100.00 | Consulting Services | DS(Direct Selection) |  |  | Prior |  |  | 05-25-2023 | 1081 | Cleared
Public Works Roads Department, Assam, India | ASRIP/C/CS-4A | Proof checking of major bridges through institutions like IIT, NIT etc | 100.00 | Consulting Services | DS(Direct Selection) |  |  | Post |  |  | 03-10-2021 | 14 | Cancel-Cleared
Public Works Roads Department, Assam, India | ASRIP/C/RS-1 | Consultancy Services for Road Safety Improvement on SH and MDRs in project area of ASRIP | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Post |  | 06-03-2023 | 06-26-2024 | 1081 | Cleared
Public Works Roads Department, Assam, India | ASRIP/C/CB-1 | Consultancy Services for ARR&TI Technical Support for Trainings, development of e-learning modules, study tours and workshops of PWRD staff | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Post |  | 02-26-2021 | 07-10-2021 | 0 | Cleared
Public Works Roads Department, Assam, India | ASRIP/C/CS-3 | Consultancy Services for support for implementation of Resettlement Plans (RP) for ASRIP | 100.00 | Consulting Services | NCS (National Competitive Selection) | QBS (Quality Based Selection) |  | Post |  | 11-29-2021 | 08-12-2022 | 14 | Cleared
Public Works Roads Department, Assam, India | ASRIP/C/CS-2 | Construction Supervision Consultancy for improvement and upgradation of roads under ASRIP | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 02-26-2021 | 03-08-2022 | 1278 | Cleared
Public Works Roads Department, Assam, India | ASRIP/C/CS-1 | Employer's Representative for Improvement and upgradation of road from Balichapori, Majuli to Bongalmara, Lakhimpur, including construction of two major bridges over Luit and Subansiri rivers on EPC mode | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 02-26-2021 | 07-15-2022 | 1096 | Cleared
Public Works Roads Department, Assam, India | ASRIP/A/RI-1 | Improvement and Upgradation of road from Balichapori, Majuli to Bongalmara, Lakhimpur (including 2 RCC bridges over Subansiri and Luit river) in EPC mode under ASRIP | 80.00 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 12-01-2021 | 04-14-2022 | 28 | Cleared
Public Works Roads Department, Assam, India | ASRIP/A/RI-8 | Improvement and Upgradation of Dhodor Ali from Nakachari to Balighat tiniali under ASRIP | 80.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 12-01-2021 | 04-14-2022 | 28 | Cancel-Cleared
Public Works Roads Department, Assam, India | ASRIP/A/RI-7 | Improvement and Upgradation of road from Sivasagar to Chumoni under ASRIP | 80.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 07-01-2021 | 11-12-2021 | 28 | Cleared
Public Works Roads Department, Assam, India | ASRIP/A/RI-6 | Improvement and Upgradation of Moran Naharkatia road (Deesang Kinar Bangali to Kathalguri) under ASRIP | 80.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 07-01-2021 | 11-12-2021 | 28 | Cleared
Public Works Roads Department, Assam, India | ASRIP/A/RI-5 | Improvement and Upgradation of Moran Naharkatia road (Moran to Deesang Kinar Bangali) under ASRIP | 80.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 07-01-2021 | 01-29-2022 | 28 | Cleared
Public Works Roads Department, Assam, India | ASRIP/A/RI-4 | Improvement and Upgradation of Sarthebari Pathshala road under ASRIP | 80.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 06-01-2021 | 10-13-2021 | 36 | Cleared
Public Works Roads Department, Assam, India | ASRIP/A/RI-3 | Improvement and Upgradation of Dhodar Ali from Kamargaon to Kamarbandha under ASRIP | 80.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-01-2021 | 10-13-2021 | 36 | Cleared
Public Works Roads Department, Assam, India | ASRIP/A/RI-2 | Improvement and Upgradation of Dhakuakhana Butikur Telijan road under ASRIP | 80.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-06-2021 | 10-18-2021 | 106 | Cleared