## Publication - PP Template
P000353 Mumbai Urban Transport Project 3A - Station Improvement
Project Country: | India | Bank's Approval Date of the Initial Procurement Plan: | 08-11-2025
Project Sector: | Transport | Approved PP Update No.: | Version 2
AIIB Loan (USD Million): | 100.00 | Bank's Approval Date of the PP Update: | 07-17-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
Mumbai Railway Vikas Corporation Ltd. | MRVC/TA/Flood Control/226R/2026 | Preparation of Comprehensive flood control master plan for Mumbai Suburban system of Western and Central Railway | 990,000.00 |  | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Post |  | 06-06-2025 | 05-20-2026 | 365 | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/Costing and Financial Consultancy/MUTP-3A/RFP/2024 | Development of a framework for Financial & Economic Sustainability of Suburban Railway system in MMR | 5890000 |  | Consulting Services | DS (Direct Selection) |  |  | Post |  |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/TA/131 | TA study for Improving Universal Access for PWDs (Persons with Disability) | 3600000 |  | Consulting Services | DS (Direct Selection) |  |  | Post |  |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/TA/233 | Consultancy Services for the Study of the Existing Traction Supply System and to Collect and Collate All Such Working Solutions Which Will Improve the Reliability, Safety, Efficiency and Compatibility of the Existing System to the Latest Technological Advancements/Upgradations on Mumbai Suburban Railway System | 1290000 |  | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Post |  |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/Cons/OHS/225 | Occupational Health and Safety (OHS) audit and monitoring implementation of OHS plan at worksites of various projects on Central and Western Railway in MMR area of Mumbai by MRVC as per Term of Reference | 490000 |  | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Post |  |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/Cons/223 | Station Improvement-Consultancy for Detail Designing Engineering including Structural & Architectural design of Station Improvement | 1300000 |  | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Post |  |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/G/202 LOT- II | LOT- II-Procurement of 27 Nos (CR-21, WR-6) of Elevators - Supply, Installation, Testing, Commissioning of Elevators at BNDP, MLND, VK, GC, DI, GTBN, CMBR, GV, MNKRD, of CR and Santacruz, NSP, BSR, BHY of WR under Station Improvement work | 680000 |  | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/G/202 LOT- I | LOT- I-Procurement of 50 nos (CR-39, WR-11) of Escalators - Supply, Installation, Testing, Commissioning of Escalators at BNDP, MLND, VK, GC, DI, GTBN, CMBR, GV, MNKRD, of CR and Santacruz, NSP, BSR, BHY of WR under Station Improvement work | 3430000 |  | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/G/201 LOT- II | LOT- II, PROCUREMENT OF 15 Nos (CE-9, WR-6) of ELEVATORS (Design, Manufacturing, Supply, Multiple loading/ unloading, Installation, Testing, Commissioning and maintenance during warranty period) at Mira Road and Kandivali of Western Railway and Neral and Kasara of Central Railway (Ph-I). | 310000 |  | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/G/201 LOT- I | LOT- I, PROCUREMENT OF 22 Nos (CR-18, WR-10) Total - 28 Nos of ESCALATORS (Design, Manufacturing, Supply, Multiple loading/ unloading, Installation, Testing, Commissioning and maintenance during warranty period) at Mira Road and Kandivali of Western Railway and Neral and Kasara of Central Railway (Ph-I). | 1850000 |  | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/W/208B | Balance Signalling & Telecom Works related to Station Improvement works at Santacruz, Bhayandar stations of Western Railway. | 1280000 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/W/208A | Balance Signalling & Telecom Works related to Station Improvement works at Vasai Road and Nallasopara stations of Western Railway. | 1620000 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/W/211 | Signalling & Telecom Works related to Station Improvement works at Ghatkopar, Bhandup, Mulund, Dombivali, GTB Nagar, Chembur, Govandi and Mankhurd stations of Central Railway. | 1120000 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/W/206 Lot-II | MRVC/W/206/Lot-II (OHE) (Lot-II ) : OHE Works related to Station Improvement works at Santacruz, Bhayandar, Vasai Road and Nallasopara stations of Western Railway | 780000 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/W/203 Lot-II | MRVC/W/203/Lot-II (OHE) (Lot-I AT MIRA & KILE) : OHE Works related to Station Improvement works at Kandivali, Mira Road, of Western Railway. | 530000 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/W/204/CR Lot-I | Lot-I: OHE Works related to Station Improvement works at Bhandup,Ghatkopar stations of Central Railway. Lot-II: OHE Works related to Station Improvement works at Mulund, Dombivali, stations of Central Railway. Lot-IV: OHE Works related to Station Improvement works at GTB Nagar, Chembur, Govandi and Mankhurd stations of Central Railway. | 1387500 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/W/202 Lot-II | RFB-MRVC/W/202(GS)/Lot-II Station improvement: General Electrification Works related to Station Improvement works at , Santacruz, Bhayandar, Vasai Road and Nallasopara stations of Western Railway | 1410000 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/EL/STN. Imp) | RFB-MRVC/EL/STN. Imp)/Sifting of Esalator at Kandivali , Mira Road & Virar Stn. | 90000 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/W/202(GS) | General Electrification Works related to Station Improvement works at Kandivali, Mira Road, stations of Western Railway. | 1120000 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/W/202 Lot III | Lot III: General Electrification Works related to Station Improvement works at Neral, Kasara, stations of Central Railway. | 840000 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/W/202-R2 Lot IV | Lot IV: General Electrification Works related to Station Improvement works at GTB Nagar, Chembur, Govandi and Mankhurd stations of Central Railway. | 2090000 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/W/202-R2 Lot II | Lot II: General Electrification Works related to Station Improvement works at Mulund, Dombivali stations of Central Railway. | 1670000 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/W/202-R2 Lot I | Lot I: General Electrification Works related to Station Improvement works at Ghatkopar, Bhandup,stations of Central Railway. | 1520000 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/W/210 Lot II | Lot II: Station Improvements works for Vasai Road & Nallasopara (Civil works) | 12790000 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/W/210 Lot I | Lot I: Station Improvements works for Santacruz & Bhayandar (Civil works) | 18570000 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/W/209 Lot III | Lot III: Station Improvements works for GTB Nagar, Chembur, Govandi, Mankhurd (Civil works) | 18660000 |  | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Post | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/W/209 Lot II | Lot II: Station Improvements work for Mulund, Dombivali (Civil works) | 17920000 |  | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Post | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/W/209 Lot I | Lot I: Station Improvements works for Ghatkopar, Bhandup (Civil works) | 19415000 |  | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/W/201 Lot VI | Lot VI: Station Improvements works for Kandivali, Mira Road (Civil & S&T works) | 18520000 |  | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/W/201 Lot III | Lot III: Station Improvements works for Neral, Kasara (Civil and S&T) | 16125000 |  | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/W/204/Lot-III | OHE Modification and Removal of infringement in connection with Station Improvement of Stations on Mumbai Suburban Section over Central Railway at Kasara & Neral Stations | 250000 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No |  |  |  | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/TA/227 | Technical Assistance Study for Network Expansion and Other improvement works/projects needed for Mumbai suburban services to improve quality of service, capacity augmentation, safety and comfort to the commuters using suburban services and making detailed proposals for MUTP Phase-IV based on the study recommendations | 1,320,000.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Post |  | 05-31-2025 | 10-12-2025 | 14 | Cleared
Mumbai Railway Vikas Corporation Ltd. | MRVC/TA/226 | Flood Vulnerability and Mitigation Assessment for Flood Prone locations on Mumbai Suburban System of Western and Central Railway | 1,000,000.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Post |  | 04-03-2025 | 08-15-2025 | 14 | Cleared
|  | Total: | 159,857,500.00