## S000672
S000672 Madagascar-Beira Corridor Development and Trade Facilitation Project Phase 2 (PACFC-II) RN9 Mandabe – Dabara
Project Country: | Madagascar | Bank's Approval Date of the Initial Procurement Plan: | 01-21-2025
Project Sector: | Transport | Approved PP Update No.: | Version 2
AIIB Loan (USD Million): |  | Bank's Approval Date of the PP Update: | 01-16-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
AGENCE ROUTIERE | 008-AR/PACFC-AIIB | RECRUITMENT OF AN INDIVIDUAL CONSULTANT IN SOCIAL SAFEGUARDING (RECRUTEMENT D'UN CONSULTANT INDIVIDUEL EN SAUVEGARDE SOCIALE) | 70000 | 100 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 01-16-2026 | 02-23-2026 | 343 | Cleared
AGENCE ROUTIERE | 007-AR/PACFC-AIIB | RECRUITMENT OF A LOCAL FIRM FOR ACCOUNTING AND FINANCIAL AUDIT: FINANCIAL YEARS 2025 - 2026 - 2027 (RECRUTEMENT D'UN CABINET LOCAL POUR L'AUDIT COMPTABLE ET FINANCIER : EXERCICES 2025 - 2026 - 2027) | 150000 | 100 | Consulting Services | NCS (National Competitive Selection) | LCS(Least Cost Based Selection) |  | Prior |  | 06-12-2025 | 11-06-2025 | 900 | Cleared
AGENCE ROUTIERE | 006-AR/PACFC-AIIB | RECRUITMENT OF A PROJECT ASSISTANT CONSULTANT (RECRUTEMENT D'UN CONSULTANT ASSISTANT DE PROJET) | 70000 | 100 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 05-15-2025 | 06-22-2025 | 900 | Cleared
AGENCE ROUTIERE | 005-AR/PACFC-AIIB | RECRUITMENT OF AN INDIVIDUAL CONSULTANT IN ADMINISTRATION AND FINANCE (RECRUTEMENT D'UN CONSULTANT INDIVIDUEL EN ADMINISTRATION ET FINANCE) | 70000 | 100 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 05-22-2025 | 06-29-2025 | 14 | Cleared
AGENCE ROUTIERE | 004-AR/PACFC-AIIB | RECRUITMENT OF AN INDIVIDUAL ENVIRONMENTAL CONSULTANT (RECRUTEMENT D'UN CONSULTANT INDIVIDUEL EN ENVIRONNEMENT) | 70000 | 100 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 05-22-2025 | 06-29-2025 | 14 | Cleared
AGENCE ROUTIERE | 003-AR/PACFC-AIIB | RECRUITMENT OF A PROCUREMENT CONSULTANT (RECRUTEMENT DUN CONSULTANT EN PASSATION DE MARCHES) | 70000 | 100 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 01-31-2025 | 03-10-2025 | 14 | Cleared
AGENCE ROUTIERE | 002-AR/PACFC-AIIB | RECRUITMENT OF AN INDIVIDUAL CONSULTANT IN SOCIAL SAFEGUARDING (RECRUTEMENT D'UN CONSULTANT INDIVIDUEL EN SAUVEGARDE SOCIALE) | 70000 | 100 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 05-22-2025 | 06-29-2025 | 900 | Cancelled
AGENCE ROUTIERE | 001-AR/PACFC-AIIB | UPDATE OF STUDIES ON DEVELOPMENT AND ASPHALTIZATION WORKS ON THE RN9 BETWEEN MANDABE PK 363+000 AND DABARA PK 460+000 (ACTUALISATION DES ETUDES DES TRAVAUX D'AMENAGEMENT ET DE BITUMAGE LA RN9 ENTRE MANDABE PK 363+000 ET DABARA PK 460+000) | 500000 | 100 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 02-10-2025 | 07-07-2025 | 14 | Cleared
|  | Total: | 1070000