## Publication - PP Template
P000913 Reconstruction of National Highway N-5 under Pakistan’s Resilient Recovery, Rehabilitation and Reconstruction Framework Project
Project Country: | Pakistan | Bank's Approval Date of the Initial Procurement Plan: | 07-21-2025
Project Sector: | Transport | Approved PP Update No.: | Version 3
AIIB Loan (USD Million): | 500.00 | Bank's Approval Date of the PP Update: | 02-25-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
National Highway Authority | IOCT/N-5/PHASE I-A/Section-7 | Reconstruction of National Highway N-5 under Pakistan's Resilient Recovery, Rehabilitation and Reconstruction Framework Project–Phase I-A (141 KM), Section-07: Rawailpindi - Hassan Abdal Road (40 KM) | 95,520,572.00 | 90.00 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 02-20-2026 | 08-07-2026 | 730 | Cleared
National Highway Authority | CS-02 | Environmental and Social Independent Monitoring Consultant | 500,000.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 10-21-2025 | 04-02-2026 | 1095 | Cleared
National Highway Authority | CS-01 | Consultancy Services for Design Review & Construction Supervision of Reconstruction of National Highway N-5 Under Pakistan’s Resilient Recovery, Rehabilitation and Reconstruction Framework Project - Phase 1A: Widening & Improvement of Three Priority Sections of N-5 (141 Km):  Section-2 Ranipur - Sukkur Road (70 Km)  Section-7 Rawalpindi - Hassanabdal Road (40 Km)  Section-8 Nowshera-Peshawar (31 Km) | 8,120,000.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 07-28-2025 | 02-06-2026 | 1260 | Cleared
|  | Total: | 104,140,572.00