## Publication
S000697 Uzbekistan Resilient Electricity Transmission Project
Project Country: | Uzbekistan | Bank's Approval Date of the Initial Procurement Plan: | 02-25-2026
Project Sector: | Energy | Approved PP Update No.: | Version 1
AIIB Loan (USD Million): |  | Bank's Approval Date of the PP Update: | 02-25-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
National Electric Grid of Uzbekistan | NEGUAIIB02 | Invidual Consultancy Services | 24000 | 100 | Consulting Services | LCSIC (Limited Competitive Selection of Individual Consultants) |  |  | Prior |  | 02-25-2026 | 03-16-2026 | 365 | Cleared
National Electric Grid of Uzbekistan | NEGUAIIB001 | Consulting Services to Project Preparation and Early Implementation of the Uzbekistan Resilient Electricity Transmission Project | 1300000 | 100 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 02-25-2026 | 06-28-2026 | 365 | Cleared
|  | Total: | 1324000