## Publication
P000687 Rogun Hydropower Development Project - Phase 1
Project Country: | Tajikistan | Bank's Approval Date of the Initial Procurement Plan: | 01-09-2026
Project Sector: | Energy | Approved PP Update No.: | Version 1
AIIB Loan (USD Million): | 270 | Bank's Approval Date of the PP Update: | 01-09-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
Project Management Group for Energy Facilities Construction under the President of the Republic of Tajikistan | RHDP-IOCT-01 | Procurement of Civil Works for Construction of a local road of category 5 on the left bank of the Rogun reservoir (Sayidon-Labijar) | 28164600 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 01-12-2026 | 05-26-2026 | 28 | Cleared
Project Management Group for Energy Facilities Construction under the President of the Republic of Tajikistan | RHDP-QCBS-01 | Construction Supervision Consultant for Construction of a Local Road of V-th Category on the Left Bank of the Rogun Reservoir (Sayindon-Labijar) | 1835400 | 100 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 01-12-2026 | 06-08-2026 | 14 | Cleared
|  | Total: | 30000000