## Works and Goods
ANNUAL PROCUREMENT PLAN FOR FISCAL YEAR 2027 (July 1, 2026 - June 30, 2027)
WORKS/GOODS/NON-CONSULTING SERVICES (under each category, list separately all the procurement activities/packages planned to be procured during the Fiscal Year)
Name of Project and Loan No: İstanbul North Rail Crossing Project (INRAIL) - 9943-TR
Name of Project Implementing Agency: Ministry of Transport and Infrastructure - Directorate General of Infrastructure Investments
Date of Preparation of this Plan: 31/07/2026
Procurement Category (please specify Works, or Goods, or Non-Consulting Services) | Procurement Activity/Package Description | Activity Procurement Plan in STEP (Submitted/Approved/Yet to be Submitted) | Activity Reference No. | Procurement Method (RFP/RFB/RFQ) | Market Approach (National / International) | Bank Review Type (Prior/Post review) | Early Market Engagement requirements completed date (only for ICB packages > USD10 Mil) |  | E&S requirements completed date |  | Technical requirements completed date (design, specifications, drawings, cost estimates, etc.) |  | Bidding documents completed date |  | Specific Procurement Notice/invitation to bid issued date |  | Bid Submission/Opening date |  | Bid Evaluation Report including Recommendation for Contract Award completed |  | Notification of Intention of Contract Award issued date |  | Notification of contract award issued date |  | Contract signed date |  | Contract Completed date
[7 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual
Works | Package 1 / Lot 1 - Design and Construction of Infrastructure & Superstructure Works including electricfication, with four Lots, under INRAIL Project | Approved | AYGM-INRAIL-2025-YAP 01/1-2-3-4 | RFP (without Initial Selection) | International | Prior | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2026-06-10 | 2026-06-04 | 2026-06-30 | 2026-06-25 | 2026-07-21 |  | 2026-07-21 |  | 2026-10-14 | 2026-11-15 |  | 2026-12-15 |  | 2026-12-30 |  | 2027-01-30 |  | 2033-12-31
Works | Package 1 / Lot 2 -Design and Construction of Infrastructure & Superstructure Works including electricfication, with four Lots, under INRAIL Project | Approved | AYGM-INRAIL-2025-YAP 01/1-2-3-4 | RFP (without Initial Selection) | International | Prior | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2026-06-10 | 2026-06-04 | 2026-06-30 | 2026-06-25 | 2026-07-21 |  | 2026-07-21 |  | 2026-10-14 | 2026-11-15 |  | 2026-12-15 |  | 2026-12-30 |  | 2027-01-30 |  | 2033-12-31
Works | Package 1 / Lot 3 - Design and Construction of Infrastructure & Superstructure Works including electricfication, with four Lots, under INRAIL Project | Approved | AYGM-INRAIL-2025-YAP 01/1-2-3-4 | RFP (without Initial Selection) | International | Prior | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2026-06-10 | 2026-06-04 | 2026-06-30 | 2026-06-25 | 2026-07-21 |  | 2026-07-21 |  | 2026-10-14 | 2026-11-15 |  | 2026-12-15 |  | 2026-12-30 |  | 2027-01-30 |  | 2033-12-31
Works | Package 1 / Lot 4 - Design and Construction of Infrastructure & Superstructure Works including electricfication, with four Lots, under INRAIL Project | Approved | AYGM-INRAIL-2025-YAP 01/1-2-3-4 | RFP (without Initial Selection) | International | Prior | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2026-06-10 | 2026-06-04 | 2026-06-30 | 2026-06-25 | 2026-07-21 |  | 2026-07-21 |  | 2026-10-14 | 2026-11-15 |  | 2026-12-15 |  | 2026-12-30 |  | 2027-01-30 |  | 2033-12-31
Works | Package 2 / Signalization, Telecommunication Works for the Entire INRAIL Project | Yet to be Submitted |  | RFB - Plant SPD (without prequalification) | International | Prior | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2026-06-10 | 2026-09-10 |  | 2026-10-15 |  | 2026-10-15 |  | 2027-01-07 |  | 2027-02-15 |  | 2027-03-15 |  | 2027-03-30 |  | 2027-04-20 |  | 2033-12-31
Formulas:
Planned = [Actual]-26
Planned = [Planned]+15

## Consultant Firms
ANNUAL PROCUREMENT PLAN FOR FISCAL YEAR 2027 (July 1, 2026 - June 30, 2027)
CONSULTING SERVICES - Firms
Name of Project and Loan No: İstanbul North Rail Crossing Project (INRAIL) - 9943-TR
Name of Project Implementing Agency: Ministry of Transport and Infrastructure - Directorate General of Infrastructure Investments
Date of Preparation of this Plan: 31/07/2026
Procurement Activity Description | Activity Procurement Plan in STEP (Submitted/Approved/Yet to be Submitted) | Activity Reference No. | Procurement Method (QCBS/LCS/FBS/CQS) | Market Approach (National / International) | Bank Review Type (Prior/Post review) | Terms of Reference completed date |  | Request for Expression of Interest issued date |  | EOI Evaluation Report and Shortlist completed date |  | Request for Proposals document completed and issued date |  | Opening of Technical Proposals date |  | Evaluation report of Technical Proposals completed date |  | Opening of Financial Proposals (N/A for CQS) date |  | Final/Combined (Technical and Financial) Evaluation Report and recommendation completed date |  | Draft negotiated contract completed |  | Notification of Intention of Contract Award date |  | Notification of Contract Award issued date |  | Contract signed date |  | Contract Completed date
[6 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual
Construction Supervision Consultant for Civil Works under Istanbul North Rail Crossing Project | Approved | AYGM-INRAIL-2025-DAN 01 | QCBS | International | Prior | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-09 | 2026-08-06 |  | 2026-08-31 |  | 2026-10-10 |  | 2026-10-30 |  | 2026-11-15 |  | 2026-11-20 |  | 2026-12-05 |  | 2026-12-10 |  | 2026-12-25 |  | 2027-01-10 |  | 2033-12-31
Project Management Consulting (PMC) Services for the General Directorate of Infrastructure Investments (AYGM) | Approved | AYGM-INRAIL-2025-DAN 02 | QCBS | International | Prior | 2026-04-03 | 2026-04-01 | 2026-04-06 | 2026-04-16 | 2026-08-06 |  | 2026-08-31 |  | 2026-10-10 |  | 2026-10-30 |  | 2026-11-15 |  | 2026-11-20 |  | 2026-12-05 |  | 2026-12-10 |  | 2026-12-25 |  | 2027-01-10 |  | 2033-12-31
Project Implementation Oversight Consultant (PIOC) for INRAIL | Approved | AYGM-INRAIL-2025-DAN 03 | QCBS | International | Prior | 2026-04-03 | 2026-04-03 | 2026-04-06 | 2026-04-17 | 2026-08-06 |  | 2026-08-31 |  | 2026-10-10 |  | 2026-10-30 |  | 2026-11-15 |  | 2026-11-20 |  | 2026-12-05 |  | 2026-12-10 |  | 2026-12-25 |  | 2027-01-10 |  | 2033-12-31
40
Formulas:
Planned = [Planned]+40

## Indv consultants
ANNUAL PROCUREMENT PLAN FOR FISCAL YEAR 2027 (July 1, 2026 - June 30, 2027)
Individual Consultant Selection
Name of Project and Loan No: İstanbul North Rail Crossing Project (INRAIL) - 9943-TR
Name of Project Implementing Agency: Ministry of Transport and Infrastructure - Directorate General of Infrastructure Investments
Date of Preparation of this Plan: 31/07/2026
Procurement Activity Description | Activity Procurement Plan in STEP (Submitted/Approved/Yet to be Submitted) | Activity Reference No. | Procurement Method (Competitive/Direct Selection) | Market Approach (National / International) | Bank Review Type (Prior/Post review) | Terms of Reference completed date |  | Request for Expression of Interest issued date |  | EOI Evaluation report and Short List completed date |  | Invitation for negotiations issued to the most qualified/selected candidate date |  | Draft Negotiated Contract completed date |  | Notification of Intention of Contract Award issued date |  | Notification of Contract award issued date |  | Contract signed date |  | Contract Completed date
[6 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual
Recruitment of a Senior Environmental Specialist | Yet to be Submitted |  | Direct Selection | National | Post | 2027-02-01 |  | 2027-02-15 |  | 2027-03-15 |  | 2027-03-30 |  | 2027-04-15 |  | 2027-04-30 |  | 2027-05-15 |  | 2027-05-30 |  | 2033-12-31
Recruitment of an Environmental Specialist | Yet to be Submitted |  | Direct Selection | National | Post | 2027-02-01 |  | 2027-02-15 |  | 2027-03-15 |  | 2027-03-30 |  | 2027-04-15 |  | 2027-04-30 |  | 2027-05-15 |  | 2027-05-30 |  | 2033-12-31
Recruitment of an OHS Specialist | Yet to be Submitted |  | Direct Selection | National | Post | 2027-02-01 |  | 2027-02-15 |  | 2027-03-15 |  | 2027-03-30 |  | 2027-04-15 |  | 2027-04-30 |  | 2027-05-15 |  | 2027-05-30 |  | 2033-12-31
Recruitment of a Senior Procurement and Contract Management Specialist | Yet to be Submitted |  | Direct Selection | National | Prior | 2027-02-01 |  | 2027-02-15 |  | 2027-03-15 |  | 2027-03-30 |  | 2027-04-15 |  | 2027-04-30 |  | 2027-05-15 |  | 2027-05-30 |  | 2033-12-31
Recruitment of a Procurement and Contract Management Specialist | Yet to be Submitted |  | Direct Selection | National | Prior | 2027-02-01 |  | 2027-02-15 |  | 2027-03-15 |  | 2027-03-30 |  | 2027-04-15 |  | 2027-04-30 |  | 2027-05-15 |  | 2027-05-30 |  | 2033-12-31
Recruitment of a Senior Financial Management Specialist | Yet to be Submitted |  | Direct Selection | National | Post | 2027-02-01 |  | 2027-02-15 |  | 2027-03-15 |  | 2027-03-30 |  | 2027-04-15 |  | 2027-04-30 |  | 2027-05-15 |  | 2027-05-30 |  | 2033-12-31
Recruitment of a Financial Management Specialist | Yet to be Submitted |  | Direct Selection | National | Post | 2027-02-01 |  | 2027-02-15 |  | 2027-03-15 |  | 2027-03-30 |  | 2027-04-15 |  | 2027-04-30 |  | 2027-05-15 |  | 2027-05-30 |  | 2033-12-31
Recruitment of a Financial Management Specialist | Yet to be Submitted |  | Direct Selection | National | Post | 2027-02-01 |  | 2027-02-15 |  | 2027-03-15 |  | 2027-03-30 |  | 2027-04-15 |  | 2027-04-30 |  | 2027-05-15 |  | 2027-05-30 |  | 2033-12-31
Recruitment of a Social Specialist | Yet to be Submitted |  | Direct Selection | National | Post | 2027-02-01 |  | 2027-02-15 |  | 2027-03-15 |  | 2027-03-30 |  | 2027-04-15 |  | 2027-04-30 |  | 2027-05-15 |  | 2027-05-30 |  | 2033-12-31
Recruitment of a Social Specialist | Yet to be Submitted |  | Direct Selection | National | Post | 2027-02-01 |  | 2027-02-15 |  | 2027-03-15 |  | 2027-03-30 |  | 2027-04-15 |  | 2027-04-30 |  | 2027-05-15 |  | 2027-05-30 |  | 2033-12-31
Recruitment of a Social Specialist | Yet to be Submitted |  | Direct Selection | National | Post | 2027-02-01 |  | 2027-02-15 |  | 2027-03-15 |  | 2027-03-30 |  | 2027-04-15 |  | 2027-04-30 |  | 2027-05-15 |  | 2027-05-30 |  | 2033-12-31