## Publication - PP
P000910 Istanbul Seismic Risk Mitigation and Emergency Preparedness - 2
Project Country: | Türkiye | Bank's Approval Date of the Initial Procurement Plan: | 04-23-2025
Project Sector: | Urban | Approved PP Update No.: | Version 4
AIIB Loan (USD Million): | 335.00 | Bank's Approval Date of the PP Update: | 11-02-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
Istanbul Project Coordination Unit | AF2-AIIB-D-SH-04 | Catering Services for IPCU Office Building | 168,176.00 | 100.00 | Non-consulting Services | DC (Direct Contracting) |  |  | Post |  |  | 11-08-2026 | 14 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-25 | Reconstruction Works of Educational Facilities (2 schools) | 10,289,434.33 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 06-12-2026 | 08-12-2026 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-24 | Reconstruction Works of Educational Facilities (2 schools) | 10,511,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 05-29-2026 | 07-29-2026 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-D-SH-03 | Procurement of Software Renewal for IPCU | 94,599.00 | 100.00 | Goods | RFQ (Request for Quotations) |  | Lowest Evaluated Cost | Post |  |  | 06-29-2026 | 7 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-D-SH-02 | Procurement of Hardware Renewal for IPCU | 78,832.50 | 100.00 | Goods | RFQ (Request for Quotations) |  | Lowest Evaluated Cost | Post |  |  | 06-29-2026 | 7 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-D-SH-01 | Procurement of Management Information System (MIS) Software Development | 94,599.00 | 100.00 | Goods | RFQ (Request for Quotations) |  | Lowest Evaluated Cost | Post |  |  | 06-29-2026 | 7 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-CD8 | Selection of Individual Consultant (Cost and Quantity Engineer - 2026) for IPCU | 36,788.50 | 100.00 | Consulting Services | DSIC(Direct Selection of Individual Consultants) |  |  | Post |  |  | 06-24-2026 | 14 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-CD7 | Selection of Individual Consultant (Green Building Expert) for IPCU | 36,788.50 | 100.00 | Consulting Services | LCSIC (Limited Competitive Selection of Individual Consultants) |  |  | Post |  | 10-19-2026 | 11-26-2026 | 14 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-CD6 | Selection of Individual Consultant (Dispute Resolution and Arbitration Expert) for IPCU | 36,788.50 | 100.00 | Consulting Services | LCSIC (Limited Competitive Selection of Individual Consultants) |  |  | Post |  | 10-19-2026 | 11-26-2026 | 14 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-CD5 | Selection of Individual Consultant (Façade Expert) for IPCU | 36,788.50 | 100.00 | Consulting Services | LCSIC (Limited Competitive Selection of Individual Consultants) |  |  | Post |  | 10-19-2026 | 11-26-2026 | 14 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-CD4 | Selection of Individual Consultant (Fire Expert) for IPCU | 36,788.50 | 100.00 | Consulting Services | LCSIC (Limited Competitive Selection of Individual Consultants) |  |  | Post |  | 10-19-2026 | 11-26-2026 | 14 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-CD2 | Selection of Individual Consultant (Occupational Health and Safety Expert) for IPCU | 36,788.50 | 100.00 | Consulting Services | LCSIC (Limited Competitive Selection of Individual Consultants) |  |  | Post |  | 10-19-2026 | 11-26-2026 | 14 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-CD3 | Selection of Individual Consultant (Cost Controlling and ALB Evaluation Expert) for IPCU | 31,533.00 | 100.00 | Consulting Services | LCSIC (Limited Competitive Selection of Individual Consultants) |  |  | Post |  | 04-30-2026 | 06-07-2026 | 14 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-23 | Reconstruction Works of Educational Facilities (1 school) Kadıköy Muhsin Adil Binal Anatolian High School | 4,204,400.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 05-29-2026 | 07-29-2026 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB5-YAPIM-01 | Reconstruction Works of Istanbul Provincial Directorate of National Education Building | 15,766,500.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 12-31-2025 | 03-02-2026 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB5-YAPIM-02 | Reconstruction Works of Kadıköy District Governorship Building | 15,766,500.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 11-30-2025 | 01-30-2026 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-22 | Reconstruction Works of Educational Facilities | 7,725,585.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 01-15-2026 | 03-17-2026 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-21 | Reconstruction Works of Educational Facilities | 3,909,326.66 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 12-21-2025 | 02-20-2026 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-20 | Reconstruction Works of Educational Facilities | 5,481,842.08 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 07-10-2025 | 09-09-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-19 | Reconstruction Works of Educational Facilities | 7,718,164.38 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 07-10-2025 | 09-09-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-18 | Reconstruction Works of Educational Facilities | 8,839,802.92 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 07-10-2025 | 09-09-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-17 | Reconstruction Works of Educational Facilities | 4,832,804.50 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 05-14-2025 | 07-14-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-16 | Reconstruction Works of Educational Facilities | 6,575,950.95 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 05-14-2025 | 07-14-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-15 | Reconstruction Works of Educational Facilities | 10,171,242.32 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 05-14-2025 | 07-14-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-CB3 | Consultancy Services for Design of Public Buildings | 2,102,200.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Post |  | 07-15-2025 | 11-26-2025 | 14 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-CB2 | Consultancy Services for Feasibility Studies and Retrofitting Design of Public Buildings | 1,576,650.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Post |  | 06-16-2026 | 10-28-2026 | 14 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-CB1 | Consultancy Services for Reconstruction Supervision of Educational Buildings | 2,627,750.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Post |  | 02-02-2026 | 06-16-2026 | 14 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-CA3.1 | Geographic Information Systems Consultant GIS Expert for Provincial Disaster and Emergency Directorate | 52,555.00 | 100.00 | Consulting Services | LCSIC (Limited Competitive Selection of Individual Consultants) |  |  | Post |  | 02-21-2025 | 03-31-2025 | 14 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-GA4.6 | Procurement of IT Equipment for Istanbul AFAD Search & Rescue Department's Official INSARAG Exam | 94,599.00 | 100.00 | Goods | RFQ (Request for Quotations) |  | Lowest Evaluated Cost | Post | No |  | 03-30-2025 | 7 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-GA4.5 | Procurement of Operational Vehicles for Istanbul Emergency Health Directorate | 2,102,200.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 06-16-2026 | 08-16-2026 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-GA4.4 | Procurement of Underwater Search and Rescue Equipment and Vehicles for Istanbul AFAD Search & Rescue Department | 1,997,090.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 06-16-2026 | 08-16-2026 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-GA4.3 | Procurement of Four Equipped SAR Training/Operational Vehicles with SAR Training Equipment for Istanbul AFAD Training Department (Istanbul AFAD) and Istanbul National Education Directorate | 1,261,320.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 06-16-2026 | 08-16-2026 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-GA4.2 | Procurement of Training Equipment for Istanbul AFAD Volunteers | 2,102,200.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 06-16-2026 | 08-16-2026 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-GA4.1 | Procurement of Various Types of CBRN Vehicles for Istanbul AFAD (5 Nos Type-1 & 2 Nos Type-2) | 1,891,980.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 06-17-2026 | 08-17-2026 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-14 | Reconstruction Works of Educational Facilities | 10,511,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 04-07-2025 | 06-07-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-13 | Reconstruction Works of Educational Facilities | 10,511,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 04-07-2025 | 06-07-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-12 | Reconstruction Works of Educational Facilities | 9,972,318.41 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 04-07-2025 | 06-07-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-11 | Reconstruction Works of Educational Facilities | 10,511,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 04-07-2025 | 06-07-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-10 | Reconstruction Works of Educational Facilities | 12,259,365.29 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 03-15-2025 | 05-15-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-09 | Reconstruction Works of Educational Facilities | 13,711,223.32 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 03-15-2025 | 05-15-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-08 | Reconstruction Works of Educational Facilities | 14,944,281.20 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 03-15-2025 | 05-15-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-07 | Reconstruction Works of Educational Facilities | 9,052,076.09 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 02-10-2025 | 04-12-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-06 | Reconstruction Works of Educational Facilities | 13,968,317.49 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 02-10-2025 | 04-12-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-05 | Reconstruction Works of Educational Facilities | 14,638,863.11 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 02-10-2025 | 04-12-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-04 | Reconstruction Works of Educational Facilities | 11,708,997.74 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 02-10-2025 | 04-12-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-03 | Reconstruction Works of Educational Facilities | 19,997,844.93 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 02-10-2025 | 04-12-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-02 | Reconstruction Works of Educational Facilities | 25,360,379.05 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 02-10-2025 | 04-12-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB4-YAPIM-01 | Reconstruction Works of Educational Facilities | 9,450,735.81 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 02-10-2025 | 04-12-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB3-GUCL-ONAR-07 | Retrofitting Works of Educational Facilities | 3,153,300.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 06-16-2025 | 08-16-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB3-GUCL-ONAR-06 | Retrofitting Works of Educational Facilities | 3,153,300.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 06-16-2025 | 08-16-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB3-GUCL-ONAR-05 | Retrofitting Works of Educational Facilities | 2,102,200.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 06-16-2025 | 08-16-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB3-GUCL-ONAR-04 | Retrofitting Works of Educational Facilities | 2,102,200.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 06-16-2025 | 08-16-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB3-GUCL-ONAR-03 | Retrofitting Works of Educational Facilities | 2,102,200.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 06-16-2025 | 08-16-2025 | 28 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB3-GUCL-ONAR-02 | Retrofitting Works of Educational Facilities | 2,102,200.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 06-17-2025 |  | 0 | Cleared
Istanbul Project Coordination Unit | AF2-AIIB-WB3-GUCL-ONAR-01 | Retrofitting Works of Educational Facilities | 2,102,200.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 06-16-2025 | 08-16-2025 | 28 | Cleared
|  | Total: | 331,704,570.08