## Publication
P000314 Bukhara Region Water Supply and Sewerage Project - Phase 1
Project Country: | Uzbekistan | Bank's Approval Date of the Initial Procurement Plan: | 08-02-2023
Project Sector: | Water | Approved PP Update No.: | Version 15
AIIB Loan (USD Million): | 385.12 | Bank's Approval Date of the PP Update: | 05-05-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Activity Status
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP/LCS/01 | Selection of Consulting Services for: Financial Audit of “Bukhara Region Water Supply and Sewerage Project (Phase 1)” for 2020, 2021, 2022, 2023, 2024 and 2025 fiscal years | 59600 | 100 | Consulting Services | IOCS (International Open Competitive Selection) | LCS(Least Cost Based Selection) |  | Prior |  | 10-01-2021 | 05-19-2022 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP/QCBS-S/02 | Selection of a consulting company for the development of detailed design and estimate documentation for construction works by sewerage system | 6200000 | 100 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 08-24-2023 | 01-18-2024 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-S/RFB/0102 | Construction Works for Sewerage Network in Gijduvan District of Bukhara Region | 22614325 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 09-15-2025 | 12-21-2025 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-S/RFB/03 | Procurement of Design and Build of Gijduvan Wastewater Treatment Plant | 19620000 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Rated Criteria | Prior | No | 09-12-2025 | 01-04-2026 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-S/RFB/04 | Construction Works for Sewerage Network in Alat District of Bukhara Region | 24748966.53 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-30-2025 | 10-07-2025 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-S/RFB/06 | Design and Build of Alat WwTP and 2 years of O&M Assistance | 9000000 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Rated Criteria | Prior | No | 07-04-2025 | 10-25-2025 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-S/RFB/07 | Construction Works for Sewerage Network in Karakul District of Bukhara Region | 23760240.31 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-30-2025 | 10-07-2025 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-S/RFB/09 | Design and Build of Karakul WwTP and 2 years of O&M Assistance | 13990000 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Rated Criteria | Prior | No | 07-04-2025 | 11-22-2025 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-S/RFB/10 | Construction Works for Sewerage Network in Romitan District of Bukhara Region | 16075140 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 09-15-2025 | 12-21-2025 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-S/RFB/11 | Procurement of Design and Build of Ramitan Wastewater Treatment Plant | 13500000 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Rated Criteria | Prior | No | 09-12-2025 | 02-13-2026 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-S/RFB/12-01 | Procurement of Design and Build of Karaulbazar Wastewater Treatment Plant (WwTP) | 9030000 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Rated Criteria | Prior | No | 03-24-2025 | 07-30-2025 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-S/RFB/12-02 | Construction Works for Sewerage Network in Karaulbazar District of Bukhara Region | 5779876.82 | 100 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 01-17-2025 | 06-11-2025 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W/QCBS/01 | Selection of a consulting company for the development of detailed design and estimate documentation for construction works by water supply system | 12600000 | 100 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 08-16-2023 | 01-10-2024 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W/RFB/11-14 | Construction and Reconstruction Works for Water Supply and Distribution in Jondor District of Bukhara Region | 21027434.51 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 07-04-2025 | 10-15-2025 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W/RFB/15-16 | Construction and Reconstruction Works for Water Supply and Distribution in Kagan District of Bukhara Region | 28525997 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 05-20-2026 | 08-19-2026 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W/RFB/20 | Construction and Reconstruction Works for Water Supply and Distribution in Karaulbazar District of Bukhara Region | 1800000 | 100 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 09-20-2023 | 01-08-2024 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W/RFB/21 | Construction and Reconstruction Works for the Water Supply System in the Peshku District of Bukhara Region | 15995290 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 04-01-2025 | 07-03-2025 | Cancelled
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W/RFB/21-Rebid | Construction and reconstruction of the main water supply network serving the Peshku District, as well as the reconstruction of the Kudrashekh, Karakalpak and Susana water distribution unit and the corresponding water supply network | 15995290 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 05-04-2026 | 08-03-2026 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W/RFB/22 | Construction and Reconstruction Works for the Water Supply System in the Peshku District of Bukhara Region | 8334640 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 04-01-2025 | 07-03-2025 | Cancelled
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W/RFB/22-Rebid | Construction and reconstruction of the Dexdaroz, Olong, and Huja Peshku WDUs and the corresponding water supply network | 8334640 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 05-04-2026 | 08-03-2026 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W/RFB/26 | Construction and Reconstruction Works for the Water Supply System in the Romitan District of Bukhara Region | 8600000 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 10-23-2024 | 04-14-2025 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W/RFB/27 | Construction and Reconstruction Works for the Water Supply System in the Romitan District of Bukhara Region | 9700000 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 10-23-2024 | 04-14-2025 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-WS/QCBS/03 | Consulting services by assisting the Project Implementing Entity (PIE) in preparation of tender documentation, project management and construction | 5200000 | 100 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 08-31-2023 | 01-25-2024 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W-S/RFB/13-29/01/01-05 | Machines that do not Require Installation, for Water Supply and Sewerage Systems in Bukhara Region (Package 1 - Vehicles) | 2978296 | 100 | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 01-29-2024 | 06-07-2024 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W-S/RFB/13-29/01/03&05 | Machines that do not Require Installation, for Water Supply and Sewerage Systems in Bukhara Region (Package 1 - Equipment) | 504500 | 100 | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 01-26-2024 | 06-15-2024 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W-S/RFB/13-29/02 | Machines that do not Require Installation, for Water Supply and Sewerage Systems in Bukhara Region (Package 2 - Equipment) | 1030107 | 100 | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 01-29-2024 | 07-06-2024 | Archived
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W-S/RFB/13-29/03 | Machines that do not Require Installation, for Water Supply and Sewerage Systems in Bukhara Region (Package 3- Emergency Vehicle, Mobile Laboratory and Leakage Detector) | 3713446 | 100 | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 01-29-2024 | 07-06-2024 | Archived
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W-S/RFB/13-29/03/01-Rebid | Machines for Water Supply and Sewerage Systems in Bukhara Region-Lot 1: Supply of Emergency Repair Vehicles (10 units) | 3000000 | 100 | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 05-29-2026 | 08-19-2026 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-W-S/RFB/13-29/03/02-Rebid | Machines for Water Supply and Sewerage Systems in Bukhara Region-Lot 2: Supply of Dredger | 240000 | 100 | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 05-29-2026 | 08-28-2026 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | BWSP-WS/Shop/13-29/01 | Dredger for cleaning the bottom of sedimentation pond from sedimentary sludge | 50000 | 100 | Goods | RFQ (Request for Quotations) |  | Lowest Evaluated Cost | Prior |  |  | 05-24-2024 | Cleared
AIIB PCU Bukhara Region Water Supply and Sewerage Project | №BWSP-W-S/RFB/13-29/01/04 | Machines that do not Require Installation, for Water Supply and Sewerage Systems in Bukhara Region (Package 1 - Equipment) | 1240000 | 100 | Goods | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 01-26-2024 | 06-15-2024 | Cleared
|  | Total: | 313247789.17