## Publication - PP
P000811 Bukhara M37 Corridor Improvement Project
Project Country: | Uzbekistan | Bank's Approval Date of the Initial Procurement Plan: | 09-15-2025
Project Sector: | Transport | Approved PP Update No.: | Version 2
AIIB Loan (USD Million): |  | Bank's Approval Date of the PP Update: | 06-05-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
“Avtoyulinvest” Agency under the Committee for Roads | BRNIP2/QCBS/sub-component-3 Technical Audit | Technical Audit Consultant (International) for Reconstruction of the M37 "Samarkand - Bukhara - Turkmenbashi" highway on sections of 207 - 365 km (158 km+4.5 km) | 1,500,000.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 06-04-2026 | 10-29-2026 | 810 | Cleared
“Avtoyulinvest” Agency under the Committee for Roads | BRNIP2/QCBS/01 | Preparation of Environmental and Social Impact Assessment (ESIA) and Paris Alignment and Climate Finance Assessment for Bukhara Road Network Improvement Project, Phase 2, M37 National Highway Rehabilitation Project | 140,000.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 05-13-2025 | 10-09-2025 | 150 | Cleared
|  | Total: | 1,640,000.00