## S000666
S000666 Expansion and Modernization of Public School Infrastructure, Phase I
Project Country: | Uzbekistan | Bank's Approval Date of the Initial Procurement Plan: | 03-04-2025
Project Sector: | Education Infrastructure | Approved PP Update No.: | Version 4
AIIB Loan (USD Million): |  | Bank's Approval Date of the PP Update: | 01-29-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
Ministry of preschool and school education of the Republic of Uzbekistan | EMPSI/CQS01 | Engagement of a consulting firm to support environmental and social screening, risk assessment, mitigation planning, and compliance monitoring throughout project preparation and implementation. | 150000 | 100 | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) |  | Post |  | 05-20-2026 | 07-25-2026 | 1 | Cleared
Ministry of preschool and school education of the Republic of Uzbekistan | EMPSI/LCS-1 | Selection of consultants for financial auditing services | 40000 | 100 | Consulting Services | NCS (National Competitive Selection) | LCS(Least Cost Based Selection) |  | Post |  | 02-01-2026 | 05-21-2026 | 14 | Cleared
Ministry of preschool and school education of the Republic of Uzbekistan | S0881A-SERVICES-01 | for supporting the development and early implementation of the Expansion and Modernization of Public-School Infrastructure Project with the participation of the Asian Infrastructure Investment Bank | 1500000 |  | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 06-16-2025 | 11-10-2025 | 14 | Cleared
Ministry of preschool and school education of the Republic of Uzbekistan | S0881A-INDV-4 | Environmental and Social specialist | 50000 | 100 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 02-10-2026 | 03-20-2026 | 14 | Cleared
Ministry of preschool and school education of the Republic of Uzbekistan | S0881A-INDV-3 | Procurement Specialist | 17000 | 100 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 12-20-2024 | 01-27-2025 | 14 | Cleared
Ministry of preschool and school education of the Republic of Uzbekistan | S0881A-INDV-2 | Financial Management Specialist | 19000 | 100 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 12-20-2024 | 01-27-2025 | 14 | Cleared
Ministry of preschool and school education of the Republic of Uzbekistan | S0881A-INDV-1 | Project Coordinator | 26400 | 100 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 12-20-2024 | 01-27-2025 | 14 | Cleared
|  | Total: | 1802400